## RAW Data
Project_ID | Project_title | Project_state | Epic_Title | Project_Assigned_To | Iteration Path | PBI_Title | PBI_State | PBI_Assigned_To | PBI_Efforts | Epic_TotalEfforts | Epic_Completed_Efforts | Epic_Pending_Efforts | Due_Date | Anchor/Non Anchor
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | DOC Submittal | Done | Jordan James <jjames@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Structure List | Done | Jordan James <jjames@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Lighting Schedules | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Lighting Construction Notes | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Lighting General Notes | Done | Jordan James <jjames@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Complete the design | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Complete Lighting Design per Solar changes | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 15.5 | 15.5 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Special Details | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Special Details, if required | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | ITS Internal review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Lighting Internal Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Accept/reject the comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Signals - Address PS&E Shared Review Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Lighting - Address PS&E Shared Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 2 | 28.5 | 28.5 | 0 |  | FALSE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plan Sheets | New |  | 4 | 12 | 0 | 12 | 2023-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New |  | 2 | 12 | 0 | 12 | 2023-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plan sheets | New |  | 4 | 12 | 0 | 12 | 2023-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Special Provisions, Structure List, & Estimate | New |  | 2 | 12 | 0 | 12 | 2023-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plan Sheets | New |  | 6 | 18 | 0 | 18 | 2023-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New |  | 2 | 18 | 0 | 18 | 2023-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plans | New |  | 4 | 18 | 0 | 18 | 2023-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Special Provisions, Structure List, & Estimate | New |  | 2 | 18 | 0 | 18 | 2023-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Circuit Analysis | New |  | 4 | 18 | 0 | 18 | 2023-01-01 | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2024 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | 2020-ITS25A (HAR Solar Site): the solar pole location needs to be moved to match that of ITS-22 (behind cabinet, away from road). | New |  |  | 18 | 18 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Additional Lighting Design Changes | Done | Jordan James <jjames@dot.nv.gov> | 4 | 28.5 | 28.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Submittal Contract 3900 - SBMT 007.2 - 623 Group 3 Electrical | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Post DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Address UPRR Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 1 | 1 | 0 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | Post-Doc Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Change Order #1 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 6.5 | 6.5 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Address Hydraulics Conflicts | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Address LTG Schedules comments from IMD IR | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 50.5 | 50.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | NDOT 3922 Submittals - part 1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | NDOT 3922 Submittals - part 2 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | NDOT 3922 Submittals - part 3 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | 3892 Submittals No. 195, 196, & 197 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Check Schedules and Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 22 | 22 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Update Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 22 | 22 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | 74239 Splice diagrams | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Incorporate new ITS infrastructure - recent/current infrastructure | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Network Diagram | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 37.5 | 37.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | NDOT 3858 - Submittal 88 - 98 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Complete KMZ and Send to Roadway | Done | Jordan James <jjames@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | SIG Scope change | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 21.5 | 21.5 | 0 |  | FALSE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | ITS Design Changes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 28 | 28 | 0 |  | TRUE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | C3939/EA74370 RFI #3 Supplemental | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 3.5 | 3.5 | 0 |  | FALSE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Lighting Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 28 | 28 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Lighting Schedule Changes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 22 | 22 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | RWIS Coordination | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 22 | 22 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | RWIS Special Details | Done | Brian Dodds <btdodds@dot.nv.gov> | 4 | 22 | 22 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | ITS Conduit Schedules Transfer | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 22 | 22 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Contract 3922 Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | NDOT 3922 Submittals - part 3 Resubmittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | NDOT 3922 Submittals - part 1 Resubmittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Lighting Schedule Transfer | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 22 | 22 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | LTG - Move Parr SP to west side of road | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Framework | Done | Brian Dodds <btdodds@dot.nv.gov> | 2 | 9 | 9 | 0 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | PDFS Report $ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  | 1 | 60 | 9 | 51 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | NDOT 3907 Submittal #15 - Electrical #1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | SP Requests $ | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Changes Verification and Final Check | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 22 | 22 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | QA/QC - Replacement sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | 3891 Fallon - School Flashing System Submittal 24 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Contract 3922 Submittals $ | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | SUE test hole verification | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69 | 69 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Update Trench Detail | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 101.5 | 101.5 | 0 |  | FALSE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | PDFS Report | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 4 | 4 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Update Panel Schedules | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 101.5 | 101.5 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Pre PS&E Design Revisions | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 37.5 | 37.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Address SIG IR comments | Done | Brian Dodds <btdodds@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | TRUE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | DOC design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Linework & Labels - Phase 1 Lighting | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 7 | 7 | 0 |  | TRUE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | DOC design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | DOC design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Schedules - Phase 1 Lighting | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | DOC design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Cut sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | DOC design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Cover Sheet/Key map | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | DOC design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | StructList & Estimate | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Framework | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Build Features & PBIs | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 4 | 4 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Research on Solar power/Ex. Service Pedastal | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 4 | 4 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | 3863 - 6 Pair No. 22 Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | 3930 Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Prelim Design for Environmental | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | SLI Team Intermediate Coordination Meeting | New |  | 0.5 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Post-Intermediate Design Conflict Efforts | New |  | 1 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels | New |  | 2 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 2 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal General Notes | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels | New |  | 4 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal Schedule & Structure List | New |  | 2 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signals Cutting Sheets | New |  | 2 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal Special Detail | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Request TOTS Pathway Analysis | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 0.5 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Schedule & Structure List | New |  | 4 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 2 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Cutting Sheets | New |  | 2 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & Labels | New |  | 6 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 2 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 4 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 70 | 3 | 67 | 2022-11-21 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 12 | 70 | 3 | 67 | 2022-11-21 | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | ITS Linework - Spots & Dots | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | ITS Rough Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Lighting Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Cut Lighting Sheets | New |  | 2 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Design Framework | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Lighting Design - Spots & Dots | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Sheets | New |  | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Signal Spots | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Signal Rough Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate & Submittal | New |  | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Doc Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Address Shared Review Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 7 | 6 | 1 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Doc Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Address Internal Review Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 7 | 6 | 1 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Doc Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | DOC Compile and Submit | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 7 | 6 | 1 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Doc Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | DOC Estimate | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 7 | 6 | 1 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Doc Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | DOC Structure List | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 7 | 6 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | BRAT review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 1.5 | 1.5 | 0 |  | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  | 0.5 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New |  | 0.5 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 1 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 6 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 2 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 12 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 4 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New |  | 1 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | QAQC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 45 | 0 | 45 | 2023-01-05 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Post Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2024-10-28 | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | SP Justification Letter | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | SLI Conduit Trench Detail | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 81 | 81 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Lighting Conductor Replacement | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Post-DOC | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Supplemental 1 redlines | Done | Jordan James <jjames@dot.nv.gov> | 2 | 29 | 29 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | NDOT 3917 - Submittal Set 2 ( 1 of 2 ) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Linework & Labels | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 11 | 11 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Modify Structure-mount (side) detail | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | ITS Revisions | Done | Laura Vargo <lvargo@dot.nv.gov> | 6 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Lighting Revisions | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | NDOT 3917 - Submittal Set 2 ( 2 of 2 ) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | 12 EP to be created into "Address Comments" PBI's | New |  | 13 | 28 | 0 | 28 | 2024-08-07 | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Break Estimate per County | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Contract 3922 Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Contract 3922 Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Submittals P121-22-813 D2 & D3 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Contract 3922 Submittal | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 20 | 0 | 20 | 2024-10-28 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 1 | 20 | 0 | 20 | 2024-10-28 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 20 | 0 | 20 | 2024-10-28 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 20 | 0 | 20 | 2024-10-28 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 20 | 0 | 20 | 2024-10-28 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 20 | 0 | 20 | 2024-10-28 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 20 | 0 | 20 | 2024-10-28 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 2 | 20 | 0 | 20 | 2024-10-28 | TRUE
45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | On-Hold | Doc Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 20 | 0 | 20 | 2024-10-28 | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Adjust ITS Conduits for Sound Wall Crossings | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Remove Signal Work from Project | Done | Jordan James <jjames@dot.nv.gov> | 2 | 14 | 14 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Schedules | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 11 | 11 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Cut Sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 11 | 11 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Special Details & Construction Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 11 | 11 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | StructList & Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 11 | 11 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Compile & Submit - Readvertisement | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 11 | 11 | 0 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | Post-Doc Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Revisions to C.O. #1 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 6.5 | 6.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Post DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Review BRAT Report | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | FALSE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Post Doc Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 1 | 1 | 0 | 1 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | BRAT Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | Post-Doc Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Change Order #1 Changes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 6.5 | 6.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | 3900 Submittal 043 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | PS&E Shared Review - Comment & Respond | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 27 | 27 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | NDOT - 3945 Submittals Submittal 01 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Coversheet/Key Map | New |  | 1 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Linework & Cut Sheets - ITS Design | New |  | 2 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | General Notes - ITS Design | New |  | 1 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Compile and submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Framework | Done | Brian Dodds <btdodds@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Lighting Coversheet/Key Map | New |  | 1 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Linework - Lighting Design | New |  | 4 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Schedules - Lighting Design | New |  | 4 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Labels - Lighting Design | New |  | 4 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Cut sheets - Lighting Design | New |  | 6 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Construction Notes - Lighting Design | New |  | 4 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes - ITS Design | New |  | 2 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Cut sheets - Signal Design | Done | Brian Dodds <btdodds@dot.nv.gov> | 4 | 19 | 19 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | General Notes - Signal Design | New |  | 1 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Linework - Signal Design | Done | Jordan James <jjames@dot.nv.gov> | 4 | 19 | 19 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Signals Coversheet/Key Map | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Schedules - Signal Design | New |  | 6 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Construction Notes - Signal Design | New |  | 4 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Labels - Signal Design | Done | William Renter <wrenter@dot.nv.gov> | 2 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Update Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Compile and submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | General Notes & Trench Detail - Lighting Design | New |  | 1 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Schedules - ITS Design | New |  | 2 | 60 | 9 | 51 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Pre-Design Coordination | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Creating a rough workbook | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Comment on IMD SR | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Address Lighting IMD SR comments | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Comment on 30% Shared Review | New |  | 2 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Sheet Revisions | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | As-Built Search and Revise Loops | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Shared Review | New |  | 2 | 15 | 7 | 8 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E SR comments | New |  | 1 | 15 | 7 | 8 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Signals PS&E SR comments | New |  | 1 | 15 | 7 | 8 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E SR comments | New |  | 0 | 15 | 7 | 8 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Post-DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting 30% SR comments | New |  | 2 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Signals 30% SR comments | New |  | 2 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS 30% SR comments | New |  | 1 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | IMD Internal Review | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 8 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | IMD Internal Review Accept/Reject Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | IMD Internal Review Address Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 30 | 30 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Contract 3922 Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | QAQC Internal Review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 15 | 7 | 8 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | QAQC Internal Review Accept/Reject Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 15 | 7 | 8 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | QAQC Internal Review Address Comments | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 15 | 7 | 8 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Compile and submit | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Update Structure List | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New |  | 2 | 15 | 7 | 8 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 15 | 7 | 8 | 2024-10-21 | FALSE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Signal Design | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting Linework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting Schedules | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Lighting sheet cutting | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Lighting Cover Sheet | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Lighting Voltage Drop Calculations | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Lighting Construction Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Lighting General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Signal Linework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Signal Construction Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Signal Schedules | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Signal Sheet Cutting | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Signal Coversheet | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Signal general Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Post-DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Managed Lighting Control Systems Handbook Review 1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 4 | 2 | 2 | 2022-01-08 | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Post-DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Managed Lighting Control Systems Handbook Review 2 | Committed | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 4 | 2 | 2 | 2022-01-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Accept/Reject IR comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Clearing and grubbing quantities | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | Post-DOC Work | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Brat Report Review | New |  | 1 | 1 | 0 | 1 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Splice Diagrams $ | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 39.5 | 39.5 | 0 |  | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review R/W Setting Documents | New |  | 0.5 | 6.5 | 6 | 0.5 | 2023-01-17 13:30 | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | NDOT - 3945 Submittals (Submittal 02) CCTV | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | 3890, Meter Cabinet Submittal, request review and comment | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | NDOT - 3945 Submittals (Submittal 03) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Verify SP Info | Done | Brian Dodds <btdodds@dot.nv.gov> | 2 | 39.5 | 39.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Post-DOC | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | CO #3 redlines | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 0 | 29 | 29 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | 3938 WWD Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Review & address RFIs from orig advertisement. | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 11 | 11 | 0 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Pre-Design Coordination | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Project Build Out | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Address Lighting 2nd PS&E Review comments | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Address ITS 2nd PS&E Review comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Add Contract document info for existing infrastructure | Done | Jordan James <jjames@dot.nv.gov> | 2 | 39.5 | 39.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Contract 3858 Resubmittals | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Splice Diagrams | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | FH Conceptual Design | New |  | 2 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Coordination emails | New |  | 1 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SP request email | New |  | 1 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Roadway Coordination | New |  | 2 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Framework | New |  | 2 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Adjust the room size in FH interior layout file | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover Sheet | New |  | 1 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Linework Labels and Construction Notes | New |  | 4 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding calculations | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Cut sheets | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Create One-line Diagram | New |  | 1 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -1 | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets - 2 | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate IR | New |  | 6 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Accept/reject comments | New |  | 1 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Intermediate IR Comments | New |  | 4 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Include design changes, if any | New |  | 2 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 2 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC IR | New |  | 4 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Accept/reject comments | New |  | 1 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address QAQC IR comments | New |  | 4 | 7 | 0 | 7 | 2023-06-16 | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 7 | 0 | 7 | 2023-06-16 | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 2 | 7 | 0 | 7 | 2023-06-16 | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | FAA Tower Coordination | New |  | 1 | 11 | 2 | 9 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Virginia WWD Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Virginia WWD Block Diagram & Special Details | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 37.5 | 37.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | 3890, Meter Cabinet Submittal, | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | Done |  | 0.5 | 0.5 | 0.5 | 0 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Project Build-Out | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 1 | 1 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | 30% Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Project Build-Out | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Consolidate the Specs based on emails & 2 projects | New |  |  | 11 | 2 | 9 |  | FALSE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  | 1 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Research on Solar power/Ex. and new Service Pedestal | New |  | 2 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Build Features & PBIs | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | PDFS Report | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 25 | 10 | 15 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Verify avoidance & clean up trunkline | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 27 | 27 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Q1-453-22-101 Submittals - Conduit | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | SP Approval/Justification Letter | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Request Service Pedestals | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 25 | 10 | 15 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | NDOT 3893 Submittal - 019.1 - RWIS | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | 3937 Submittal No. 01 to 05 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Review As-built plans | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 25 | 10 | 15 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Framework | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Cut sheets - Signal Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | General Notes - Signal Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Signals Coversheet/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Linework - Signal Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Linework - Lighting Design $ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | General Notes - Lighting Design | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Lighting Coversheet/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Construction Notes - Signal Design | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Schedules - Signal Design $$ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 6 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Labels - Signal Design | Done | William Renter <wrenter@dot.nv.gov> | 2 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Schedules - Lighting Design $$ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 6 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Cut sheets - Lighting Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Labels - Lighting Design | Done | William Renter <wrenter@dot.nv.gov> | 2 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Construction Notes - Lighting Design | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | IMD Internal Review Address Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 20 | 20 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | IMD Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | IMD Internal Review Accept/Reject Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Address IMD SR comments | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 20 | 20 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Comment on IMD SR | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 20 | 20 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 15 | 7 | 8 | 2024-10-21 | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Update Estimate | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Update Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 60 | 9 | 51 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Update Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Update Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Update Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Compile and submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Update Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 20 | 20 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Update Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 20 | 20 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Compile and submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 20 | 20 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | QAQC Internal Review Accept/Reject Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 20 | 20 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | QAQC Internal Review | Done | Connie Ullas <cullas@dot.nv.gov> | 4 | 20 | 20 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Address PS&E SR comments | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Comment on PS&E Shared Review | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Update Estimate | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Compile and submit | Conditional | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Update Structure List | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Post-DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2024-10-28 | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Schedules - Lighting Design | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Construction Notes - Lighting Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Linework & Cut Sheets - Lighting Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | General Notes & Details - Lighting Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Framework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Address Intermediate Shared Review Comments | New |  | 0 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Lighting Coversheet/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Update Estimate & Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Structure List, Estimate, Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | DOC Plans Preparation | Done | William Renter <wrenter@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Comments | New |  | 0 | 2 | 2 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Address Changes from Specs | New |  | 0 | 12 | 12 | 0 |  | FALSE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Address Changes from Specs | New |  | 0 | 2 | 2 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Holbrook Lighting adjustments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Review DOC Special Provisions | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 37.5 | 37.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Address PS&E SR ITS comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Address PS&E SR LTG comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Submittal_Narwhal Repair of Knock-Down in Laughlin NV | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Revise Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 9.5 | 9.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Post DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | BRAT Review | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | TRUE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels | New |  | 4 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules | New |  | 2 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Cutting Sheets | New |  | 2 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Internal Review - Intermediate | New |  | 6 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 4 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Internal Review - Intermediate | New |  | 4 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Post-Intermediate Design Conflict Efforts | New |  | 1 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  | 0.5 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New |  | 0.5 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 2 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Internal Review - QA/QC | New |  | 6 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New |  | 1 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 4 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | QA/QC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Internal Review - QA/QC | New |  | 4 | 33 | 0 | 33 | 2023-07-08 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | DOC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 16 | 0 | 16 | 2023-10-23 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | DOC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 16 | 0 | 16 | 2023-10-23 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | DOC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 16 | 0 | 16 | 2023-10-23 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | DOC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 16 | 0 | 16 | 2023-10-23 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Post-DOC | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | FALSE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Framework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Linework - Lighting Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Lighting Coversheet/Key Map | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Cut sheets - Lighting Design | Approved |  | 2 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Coversheet/Key Map | New |  | 1 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | General Notes - ITS Design | New |  | 1 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Linework & Cut Sheets - ITS Design | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New |  | 2 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS 30% SR comments | New |  | 2 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Comment on 30% Shared Review | New |  | 2 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting 30% SR comments | New |  | 2 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Schedules - Lighting Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | General Notes & Trench Detail - Lighting Design | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Cut sheets - Lighting Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Labels - Lighting Design | New |  | 4 | 25 | 10 | 15 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Construction Notes - Lighting Design | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Schedules - ITS Design | New |  | 2 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes - ITS Design | New |  | 2 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Compile and submit | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 16.5 | 4.5 | 12 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Update Structure List$ | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 16.5 | 4.5 | 12 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Update Estimate | Done | William Renter <wrenter@dot.nv.gov> | 1 | 16.5 | 4.5 | 12 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | IMD Internal Review Address Comments | Committed | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 16.5 | 4.5 | 12 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | IMD Internal Review | New |  | 4 | 16.5 | 4.5 | 12 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | IMD Internal Review Accept/Reject Comments | Committed | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 16.5 | 4.5 | 12 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting IMD SR comments | New |  | 2 | 16.5 | 4.5 | 12 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Comment on IMD SR | New |  | 2 | 16.5 | 4.5 | 12 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS IMD SR comments | New |  | 1 | 16.5 | 4.5 | 12 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New |  | 2 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 30 | 16 | 14 |  | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | QAQC Internal Review Accept/Reject Comments | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 16 | 15 | 1 | 2024-07-29 | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | QAQC Internal Review Address Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 16 | 15 | 1 | 2024-07-29 | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | QAQC Internal Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 16 | 15 | 1 | 2024-07-29 | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E SR comments | New |  | 1 | 16 | 15 | 1 | 2024-07-29 | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Address Lighting PS&E SR comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 16 | 15 | 1 | 2024-07-29 | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Comment on PS&E Shared Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 16 | 15 | 1 | 2024-07-29 | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Update Estimate | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 16 | 15 | 1 | 2024-07-29 | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Compile and submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 16 | 15 | 1 | 2024-07-29 | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Update Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 16 | 15 | 1 | 2024-07-29 | TRUE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Post-DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2024-07-29 | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Submittals TOR #35 and TOR #36 | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | 3938 WWD Submittal | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | 30% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | KMZ to Roadway | Done | Jordan James <jjames@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Brat Report Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 11 | 1 | 10 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Connect New Comm Cabinets to Ex. Fiber | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 6 | 39.5 | 39.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Add Fiber info affected by Sound walls | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 39.5 | 39.5 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | CO1 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 2.5 | 2.5 | 0 |  | TRUE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | CO1 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 3.5 | 3.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | NDOT 3945 Submittal #4 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | NDOT 3911 - Submittal 09-1R No. 3.5,5,7, and 9 Bull Boxes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | NDOT 3911 - Submittal 14 - Traffic Signal Cabinet and Controller | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | 3949 001-0018 Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | 3949 039 - 043 Submittals | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | RWIS clean-up | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Update NEW AC Sites to Solar | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Site Details Update | Done | Jordan James <jjames@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Plans Updates | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Panel Schedule Updates | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Provide PS&E Shared Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Add Key Map to Sheets | New |  | 0 | 60 | 9 | 51 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Design Framework | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 10 | 10 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Service Pedestals | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | ITS Spots & Dots | Done | William Renter <wrenter@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | ITS Key Map & Cut Sheets | Done | William Renter <wrenter@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting Spots & Dots | Done | William Renter <wrenter@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Lighting Key Map & Sheets | Done | William Renter <wrenter@dot.nv.gov> | 2 | 10 | 10 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Confirm QC Comments on IMD IR | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Provide Comments IMD IR Lighting | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide IMD SR Comments | New |  | 2 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments IMD IR ITS | New |  | 0 | 34.5 | 32.5 | 2 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Parr NB Offramp ITS Redesign | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Parr NB Offramp ITS Schedule Redesign | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Parr NB Offramp Structure List & Estimate Update | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Parr NB Offramp Plot & Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 37.5 | 37.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3792 Submittals 461-466 | Done | Jordan James <jjames@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | NDOT 3833 Submittal Review Request 623N-128 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3792 Submittals 467-472 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3949 055-059 Submittals | Done | Jordan James <jjames@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3949 060 Submittal | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Contract 3929 - Submittal #22 | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Additional Pull Boxes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Additional Directional Drill runs - from Environmental | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Submittal 07 NDOT 3945 modified pull boxes | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3949 042 - 043 Submittals | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Update ITS connections | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | NDOT 3911 - Submittals 32- 34 | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | 3940 - MODIFY SIGNAL CABINET & TRAFFIC SIGNAL | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | 3940 - 623.0355 - LUMINAIRE A & UNDERPASS LUMINAIRE A, B & C | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3940 - 623.1795 - 1.5, 2 & 3 INCH CONDUIT | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3940 - NO. 6, 10, 14 CONDUCTOR & 25 COND. NO.14 CABLE & LOOP DETECTOR WIRE | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Review Specs | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3940 - TRAFFIC & PEDESTRIAN SIGNAL HEADS | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3940 - POLES | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | 3940 - POWER SUPPLY & FLASHING BEACON CONTROLLER | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Spots & Dots | New |  | 2 | 11.5 | 0 | 11.5 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Key Map & Sheets | New |  | 2 | 11.5 | 0 | 11.5 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Spots & Dots | New |  | 0.5 | 11.5 | 0 | 11.5 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Key Map & Cutting Sheets | New |  | 0.5 | 11.5 | 0 | 11.5 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Spots & Dots | New |  | 1 | 11.5 | 0 | 11.5 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Key Map & Cutting Sheets | New |  | 0.5 | 11.5 | 0 | 11.5 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Design Framework | New |  | 2 | 11.5 | 0 | 11.5 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Develop Scope & PDFS Report | New |  | 1 | 11.5 | 0 | 11.5 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  | 1 | 11.5 | 0 | 11.5 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Service Pedestals | New |  | 1 | 11.5 | 0 | 11.5 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Connect Ex. Comm Cabinets to New Fiber | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 39.5 | 39.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Re-design Trunkline | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 39.5 | 39.5 | 0 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New | Laura Vargo <lvargo@dot.nv.gov> | 2 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | Brian Dodds <btdodds@dot.nv.gov> | 1 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address PS&E SR Comments | New | Jordan James <jjames@dot.nv.gov> | 1 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 2 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 2 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG Address IR Comments | New |  | 2 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address PS&E SR Comments | New | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address PS&E SR Comments | New | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Coordination Efforts - needs acceptance criteria | New |  | 0 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | Laura Vargo <lvargo@dot.nv.gov> | 1 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | Laura Vargo <lvargo@dot.nv.gov> | 1 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | Laura Vargo <lvargo@dot.nv.gov> | 2 | 14.5 | 0 | 14.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | Post-DOC | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | TRUE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 17 | 0 | 17 | 2025-07-21 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 17 | 0 | 17 | 2025-07-21 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 17 | 0 | 17 | 2025-07-21 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E SR Comments | New |  | 2 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E SR (need A/C review) | New |  | 0.5 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC IR | New |  | 0 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC IR | New |  | 0 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New |  | 1 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 0 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 0 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New |  | 1 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 17 | 0 | 17 | 2025-07-21 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Coordination Efforts | New |  | 0 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 9 | 0 | 9 | 2025-10-20 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Post-DOC | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | BRAT review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 9.5 | 6.5 | 3 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | NDOT 3945 Submittal 09 - Geo-fabric | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | BRAT review #2 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 11 | 11 | 0 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3821 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 8 | C3821 As-built Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 8.5 | 7.5 | 1 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3821 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 9 | C3821 As-built Plotting | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8.5 | 7.5 | 1 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3821 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 8 | C3821 As-built Coordination | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8.5 | 7.5 | 1 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3821 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS | C3821 Internal Review | New |  | 1 | 8.5 | 7.5 | 1 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Populate Phase 2/Split Project | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Scope Lighting from KMZ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Linework & Labels - New and existing Lighting locations | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Cut new LTG sheets | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Lighting Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Lighting Construction notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 56 | 56 | 0 |  | TRUE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 2 | 2 | 0 | 2 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 2 | 0 | 2 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Signal Internal Review Comments | New |  | 2 | 13 | 0 | 13 | 2027-01-02 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR ITS Comments | New |  | 2 | 13 | 0 | 13 | 2027-01-02 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review comments | New |  | 1 | 13 | 0 | 13 | 2027-01-02 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR Signal Comments | New |  | 2 | 13 | 0 | 13 | 2027-01-02 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | IMD Coordination Efforts | New |  | 2 | 42 | 2 | 40 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 4 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 25 | 0 | 25 | 2026-04-13 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Lighting Cover/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Lighting General Notes | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Lighting Linework/Labels | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Lighting Schedule | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 4 | 17 | 0 | 17 | 2025-07-21 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New |  | 2 | 17 | 0 | 17 | 2025-07-21 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 4 | 17 | 0 | 17 | 2025-07-21 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New |  | 2 | 17 | 0 | 17 | 2025-07-21 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 17 | 0 | 17 | 2025-07-21 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Compile and submit | Done | William Renter <wrenter@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | Removed |  | 0 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Coversheet/Key Map | Removed |  |  | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Intermediate Compile and Submit | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Intermediate Structure List | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Intermediate Estimate | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Clearing and Grubbing/Seeding | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 0.5 | 34.5 | 32.5 | 2 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG IMD Schedules | New |  | 2 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG IMD Design/Labels/Construction Notes | New |  | 4 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Schedules - ITS Design | New |  | 0.5 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS IMD Design/Labels/Construction Notes | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 2 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 2 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Coversheet/Key Map | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 4 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New |  | 2 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 4 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG Address SR Comments | New |  | 2 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG Address IR Comments | New |  | 4 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New |  | 2 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 0.5 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  |  | 32 | 0 | 32 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | INTERMEDIATE Estimate - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Structure List - 74249 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Compile & Submit - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 56 | 56 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS IMD IR | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG IMD IR | New |  | 2 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Comment on IMD SR | New |  | 2 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG IMD IR | New |  | 2 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG General Notes | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on IMD IR | New |  | 0.5 | 29.5 | 0 | 29.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG QAQC IR | New |  | 2 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG QAQC IR | New |  | 2 | 32 | 0 | 32 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS QAQC IR | New |  | 2 | 32 | 0 | 32 |  | TRUE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS IMD Design/Labels | Removed | Shaza Elshazli <selshazli@dot.nv.gov> | 0 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Schedules - ITS Design | Removed |  | 0 | 34.5 | 32.5 | 2 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 1 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 2 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS IMD Design/Labels/Construction Notes | New |  | 1 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Coversheet/Key Map | New |  | 1 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Schedules - ITS Design | New |  | 0.5 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 2 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on IMD SR | New |  | 0.5 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on IMD IR | New |  | 0.5 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS IMD IR | New |  | 1 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Comment on IMD SR | New |  | 2 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG IMD IR | New |  | 2 | 19 | 0 | 19 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New |  | 2 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 4 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New |  | 2 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 4 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  |  | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS QAQC IR | New |  | 2 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG QAQC IR | New |  | 2 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 24 | 0 | 24 | 2025-03-03 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 0.5 | 24 | 0 | 24 | 2025-03-03 | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Signal Sheets | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 56 | 56 | 0 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Post Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-10-27 | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | ITS sheets | Done | Brian Dodds <btdodds@dot.nv.gov> | 4 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Signal Schedules | Done | Jordan James <jjames@dot.nv.gov> | 6 | 56 | 56 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | C3946 Submittal 001-004 | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Details Updates | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Design Updates | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Roadway Coordination | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Scoping | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Phase 2 Electrical needs | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 3 | 3 | 0 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3821 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 3 | C3821 As-built Process/Complications Writeup | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 8.5 | 7.5 | 1 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Signal Construction Notes | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | ITS Construction Notes | Done | Brian Dodds <btdodds@dot.nv.gov> | 2 | 56 | 56 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | 3957 Submittal 024 - Detectable Warning System | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | NDOT 3944 Submittal No. 002, Steel Pole, Type 7 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Project DevOps Build Out | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | NDOT 3945 Submittal 10 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Construction Note Cleanup & Schedules | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Build Features & PBIs | New |  | 1 | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Design Framework | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Develop Scope & PDFS Report | New |  | 1 | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Review As-Built Plans | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Linework | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - General Notes | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Linework | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - General Notes | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Lighting Design - Cut Sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Linework | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - General Notes | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Signal Design - Cut sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  |  | 2 | 0 | 2 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Framework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Justification Letter | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Requests $ | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Schedule & Structure List | New |  | 6 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | SLI Intermediate Coordination Meeting (Group Designers Only) | New |  |  | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Post Doc Design |  | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Post Doc Design |  | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New |  |  | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | QAQC Design |  | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 |  | FALSE
51160 | Project Template - do not modify | Potential | Post Doc Design |  | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Post Doc Design |  | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Post Doc Design |  | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Quantify Scope Items and Add Pricing | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Request Service Pedestals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Framework | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Review As-Built Plans | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | SP Justification Letter | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Linework - Lighting Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Cut sheets - Lighting Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Lighting Coversheet/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Linework & Cut Sheets - ITS Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS Coversheet/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Compile and submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Intermediate Internal Review | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 6 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Intermediate Shared Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Confirm Comments on Intermediate Internal Review | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Lighting Construction Notes | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Update Lighting Cover/Key Map | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Lighting Schedule | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Lighting General Notes | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Lighting Linework & Labels | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Lighting Voltage Drop | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | ITS Schedules $ | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Intermediate Compile and Submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Intermediate Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Intermediate Estimate | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Clearing and Grubbing/Seeding | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Address Internal Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Address Shared Review Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | QA/QC Structure List | Committed | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 2 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 6 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 26 | 5 | 21 | 2024-11-15 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR ITS Comments | New |  | 2 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 2 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR Lighting Comments | New |  | 1 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit1 | New |  | 2 | 17.5 | 0 | 17.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-10-20 | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | ITS Linework and Labels | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | ITS Construction Notes | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Special Details | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 42.5 | 41.5 | 1 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | ITS General Notes | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 42.5 | 41.5 | 1 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Contract 3951 Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | 3949 042-1 Re-Submittal | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Submittal 3940 623.0232 623.0236 NDOT Contract #3940 Resubmittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | NDOT Contract #3940 Submittal 623.0770 Ped button | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | NDOT 3911 - Submittal 34 - R1 | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | NDOT 3945 Submittal 10 R1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | 3949 039 - 043 Submittals | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | 3949 055-059 Submittals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Update sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
51160 | Project Template - do not modify | Potential | Doc Design |  | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Clearing, Grubbing, & Seeding | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 9.5 | 6.5 | 3 |  | TRUE
44650 | SLI/T.O. Special Projects | Potential | C3858 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 7 | C3858 As-built Plotting | Done | Jordan James <jjames@dot.nv.gov> | 2 | 9.5 | 8.5 | 1 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3858 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 5 | C3858 As-Built Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 9.5 | 8.5 | 1 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3858 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 6 | C3858 As-built Coordination | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 9.5 | 8.5 | 1 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3858 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 6 | C3858 As-Built Process/Complications Writeup | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 9.5 | 8.5 | 1 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3821 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 4 | Review files from C905 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8.5 | 7.5 | 1 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3858 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS | C3858 As-Built Internal Review | New |  | 1 | 9.5 | 8.5 | 1 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | 3956 US 95 Fallon to Trinity - Submittal 001R1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | RWIS Inset & SP-08 Updates | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Contract 3936 Submittal#13 - Electrical | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | RWIS Details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Block Diagrams | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Flashing Border signs - coordinate with SSTC | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Splice Diagrams | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Lighting Design Cleanup | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Sheet Cleanup | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 57 | 57 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Signal Details - ISNS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Compile and Submit - Again | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 39.5 | 39.5 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Add crosswalk lighting north of 10th St | Done | Jordan James <jjames@dot.nv.gov> | 2 | 11 | 11 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | DOC ITS Design - Stop sign with solar flasher. | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 14 | 14 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Adjust conduits in Avoidance Area | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 9.5 | 6.5 | 3 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Detail sheets for shallow conduit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 9.5 | 6.5 | 3 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Contract #3955 Submittals #13-20 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | NDOT 3931 Submittal #14 - Electrical #1 | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Contract No. 3956, Submittal No. 3-TI-001, 3-Inch Conduit (Metal) | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Contract No. 3956, Submittal No. 3-TI-002, Conduit (HDPE) | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Contract No. 3956, Submittal No. 3-TI-003, Solar Voltaic Array | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Contract No. 3956, Submittal No. 3-TI-004, Luminaire Type B | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | NDOT 3955 Submittal - 011 - Poles | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Contract No. 3956, Submittal No. 3-TI-005, Conductors | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Contract No. 3956, Submittal No. 3-TI-006, Loops | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Contract No. 3956, Submittal No. 3-TI-007, Special Cabinet | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Contract No. 3956, Submittal No. 3-TI-008, Pull Boxes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | RE: 3949 042-1 Re-Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Contract #3955 Submittals #24-28 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Contract 3951 Submittals | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Re-establish design scope | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 40 | 38 | 2 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | DOC ITS Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Internal Review | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Internal Review Comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Provide comments on shared Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Internal Review - ITS QA/QC - 74249 | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Internal Review - Signal QA/QC - 74249 | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Internal Review - Lighting QA/QC - 74249 | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS\2024 Sprint 11 | Professional Training for 1 Hour | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2023 Professional Training |  | Signals Lighting and ITS\2023 Sprint 12 | Professional Training for 8 Hours | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for 8 Hours | Done |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS\2024 Sprint 10 | Professional Training for 8 Hours | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2023 Professional Training |  | Signals Lighting and ITS\2023 Sprint 21 | Professional Training for 10 of Hours | Done |  | 2 | 6 | 6 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS\2024 Sprint 11 | Professional Training for (12) Hours | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 5.5 | 5.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | NDOT 3944 Submittal No. 004 - 011, Electrical | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Contract 3947 - Submittal #019-623 - 80' ITS NDOT POLE | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | 3947 SUBMITTAL #007R1-623 - HDPE 3-INCH SDR-11 & HDPE 4-INCH FUTUREPATH (BLUE & GREEN) | Done | Brian Dodds <btdodds@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | 3947 SUBMITTAL #024-623 - PULL BOXES | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Build Features & PBIs | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Develop Scope & PDFS Report | Done |  | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Review As-Built Plans | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Design Framework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | ITS Design - Spots and Dots | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | ITS Design - Cut sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | ITS Design - Coversheet/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | ITS Design - General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Lighting Design - Spots and Dots | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Lighting Design - Coversheet/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Lighting Design - Cut Sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | SP Requests $ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 12.5 | 12.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Lighting Voltage Drop | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Lighting General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Lighting Schedule & Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 6 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Lighting Linework/Labels Pt 1 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | ITS Linework/Labels Pt 1 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS Special Details | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | ITS Schedules & Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS Cover/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Coordination Efforts | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Review Utility and UPRR Conflicts | Removed | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Design Conflict Efforts | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Provide Comments Intermediate Internal Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Intermediate Estimate | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Intermediate Compile and Submit | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Intermediate Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Clearing and Grubbing/Seeding | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Shared Review Comments | New |  | 2 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | QAQC Coordination Efforts | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QAQC Internal Review | New |  | 0.5 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 4 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-11-18 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Lighting Construction Notes and Drop Circles | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS Construction Notes and Drop Circles | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Solar Power design 74346 $ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 40 | 38 | 2 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | C3858 Pull Box/Conduit As-Built Trial Project |  | Signals Lighting and ITS\2023 Sprint 6 | C3858 As-built Sheet Examples | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 9.5 | 8.5 | 1 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | StructList & Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 17 | 17 | 0 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Design Framework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 44 | 41 | 3 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | RE: 3952 Mt Rose Bike Path - Luminaires Submittal 1.2 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Contract 3951 Submittal | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Contract 3951 Submittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Contract 3936 - Electrical Submittal #3 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Contract 3951 Pole Submittals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Contract 3947 Submittal 025-623 Luminaires, Bid Item 6230266 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Contract 3936 - Submittal #17 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Analysis | New |  |  | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Update Structure List and Estimate | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Compile and submit | New |  |  | 2 | 0 | 2 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Contract 3947 Submittal 026-623 HDPE 4-INCH TSIDR 11.5, Bid Item No. 623 1850 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | FW: NDOT 3911 - Revised Submittal 7 & 8 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | 3910 Submittal #59 No. 5 Pullbox, Modified | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Contract 3947 Submittal 027-623 Modify Luminaires, Bid Item 623-0269 for approval | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | RE: Contract 3940 - Submittal - 623.0267 - Luminaire Type A | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Contract 3951 Submittal | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | 3954 Submittals 38 - 40 | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | 3954 Submittal 41-44 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3954 Submittals 45-46 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | 3954 Submittals 47-50 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | 3954 Submittals 51-54 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | FW: NDOT 3953 Submittals 058-062 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | 3954 Submittal # 57 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | BRAT review - 74360 / 74373 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Clearing and Grubbing/Seeding | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Clearing and Grubbing/Seeding | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 15.5 | 15.5 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Service Panel Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 41 | 41 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | RE: NDOT 3939 Submittal #16 - Electrical #2 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Submittal 623.0590 623.2225 steel Poles NDOT 3940 - | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | Post-DOC | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | SLI Plan Changes | Done | Jordan James <jjames@dot.nv.gov> | 4 | 13 | 13 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | Post-DOC | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Verify need for CO | Done | Jordan James <jjames@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | On-Hold |  | 0 | 15.5 | 15.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Lighting Cover/Key Map | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | On-Hold |  | 0 | 15.5 | 15.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Lighting Linework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Lighting Schedules | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Lighting General Notes | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Coordination | On-Hold |  | 0 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review Comments | New |  | 0 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Intermediate Internal Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 6 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Confirm QC Comments on Intermediate Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Intermediate Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Intermediate Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Intermediate Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Lighting & ITS Address Shared Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Lighting & ITS Address Internal Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Confirm QC Comments on QA/QC Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Provide PS&E Shared Review Comments$ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | QA/QC Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | QA/QC Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | QA/QC Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Project Buildout | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Lighting Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Lighting Construction Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Lighting One-line Diagrams | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Electrical Building Special Details | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | FW: Contract 3940 Submittal 623.0590 623.2225 steel Poles | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Lighting Construction Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Signal Construction Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Post DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Convert FH Sheets to DWG | Done | Jordan James <jjames@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | ITS cut sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Lighting Panel Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Schedule and Plan Updates | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 25.5 | 25.5 | 0 |  | TRUE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Files Search | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Framework | New |  |  | 2 | 0 | 2 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Lead Respond to IMD IR Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | IMD shared review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | NDOT 3944 Submittal 004.1 - Luminaire Type B (Resubmittal) | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Lighting Control Sheets$ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 6 | 15.5 | 15.5 | 0 |  | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Review scope | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 6.5 | 6.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Lighting Camera Sheets | On-Hold |  | 0 | 15.5 | 15.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Lighting Design - Cut Plan Sheets | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | QAQC Internal Review | Done | Connie Ullas <cullas@dot.nv.gov> | 4 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Address PS&E Shared Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Address Internal Review Comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | DOC Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | ITS Devices Added to Spreadsheet | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 15.5 | 15.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Structure List & Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | ITS Key Map & sheet cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Lighting Key Map & Sheet Cleanup | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | ITS Address Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Lighting Address Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Signal Address Review Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Address Internal Review Comments Discussion | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | RE: Contract 3951 Submittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | FW: NDOT 3939 Submittal #20 - Electrical #3 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | NDOT 3944 Submittal 033 - Load Center cabinet | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | FW: NDOT 3944 Submittal 034 - HDPE Duraline Connections for 90's | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Contract #3955 Submittals #17.1, 54 & 55 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | FW: NDOT 3939 Submittal #22 - Electrical #4 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Contract 3936 Submittal #20 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Contract 3947 Submittal 032-623 ITS Vault, Bid Item 623 0201 for approval | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Contract 3947 Submittal 033-623 ITS Vaults, Bid Item 623 0201 for approval | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | NDOT 3944 Submittal 039 - Receptacles | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3952 Mt Rose Bike Path - Meter Service Submittal 1.9 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Contract 3947 Submittal 038-623 CCTV CAMERA LOWERING DEVICE (PAR WLC 14), Bid Item 623 2950 and 623 3030 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | FW: NDOT 3939 Submittal #16 - Electrical #2 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3947 Submittal 040-623 GEO-FABRIC (PAR WLC 16) for approval | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | ITS Linework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | ITS Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Research on Solar power/Ex. Service Pedastal | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 6.5 | 6.5 | 0 |  | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & Labels | New |  | 1 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Address Shared Review and IR Comments | New |  | 2 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review and IR Comments | New |  | 2 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 2 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 1 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New |  | 1 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 15 | 0 | 15 | 2024-07-30 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts | New |  | 1 | 10 | 0 | 10 | 2024-10-29 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR and IR Comments | New |  | 2 | 10 | 0 | 10 | 2024-10-29 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Lighting Address SR and IR Comments | New |  | 2 | 10 | 0 | 10 | 2024-10-29 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 10 | 0 | 10 | 2024-10-29 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 2 | 10 | 0 | 10 | 2024-10-29 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 10 | 0 | 10 | 2024-10-29 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Post DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 1 | 1 | 0 | 1 | 2024-10-29 | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 001 623-0537 Solar Pole | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 002 623.0226 No. .3.5 mod pullbox | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 004 Luminaire Type B | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 005 Steel Pole Type 7 | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 011 No. 10 Conductor | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 012 Steel Post | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 010 No. 6 Conductor | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 009 1.5inch conduit | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 008 Modified Electrical service | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 007 Loop Detector | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 006 Steel Pole type 7 | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | 3943 Submittal 003 No 5 pull box mod | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Contract 3947 Submittal 041-623 COUPLINGS (PAR WLC 17), Bid Item 623 1850 for approval | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Post DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Relocate I-80 Fiber Hut (Near SR-439) to new location | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 7 | 7 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | Post-DOC | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Change Order #1 | Done | Jordan James <jjames@dot.nv.gov> | 4 | 4 | 4 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3947 Submittal 044-623 TRENCH DETAIL (PAR WLC 18), Bid Item 623 1820 and 623 1850 for approval | Done |  | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | FW: NDOT 3911 - Submittal 40 - 25 Conductor No.14 Cable.pdf | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Fwd: Contract 3900 - Submittal 037.1 - Electrical Group 6 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Post-DOC | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Change Order #3 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 29 | 29 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | ITS Construction Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | ITS Cover/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | ITS General Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | ITS Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | ITS Design - Cut Plan Sheets | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Lighting Legend Sheet | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Threshold Plan Special Detail | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Lighting Support Section Details | Done | William Renter <wrenter@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Lighting Raceway Routing & Mounting Details | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Lighting Terminal & J-Box Details & Design Updates | On-Hold | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | ITS RWIS Details | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS Pole Mounting Details | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS Cabinet Block Diagrams | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | FW: NDOT 3939 Submittal #24 - Electrical #5 Concrete | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Contract 3947 Submittal 048-623 Rigid Conduit (PAR WLC 19), Bid Items 623 1825 and 623 1835 for approval | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | FW: NDOT 3944 Submittal 33.1 - Load Center Cabinet | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | FW: NDOT 3939 Submittal #22 - Electrical #4 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | FW: NDOT 3939 Submittal #26 - Electrical #6 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | FW: NDOT 3944 Submittal 56 - Loop Detectors | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | FW: NDOT 3944 Submittal 55 - Modify ELE Service Breaker | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | ITS Sensor Linework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Post DOC | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Change Order #8 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Truck Parking Light pole location sketch | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 1.5 | 1.5 | 0 |  | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Service Pedestal Request | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 44 | 41 | 3 |  | FALSE
44650 | SLI/T.O. Special Projects | Potential | Update SLI Design Guide |  | Signals Lighting and ITS | 4 Hours of Markups in Design Guide with Info emails | New |  |  |  | 0 |  |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | BRAT Report Review | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Project Closeout | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS Design Updates | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | FW: NDOT 3910 Submittals #60 and #61 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | NDOT 3911 - Group 3 Submittals 51 - 57, PVC Items | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3954 Submittal 39R1 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | FW: NDOT 3907 Submittal #24 - Electrical #3 Change Order | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Contract #3955 Submittal #26.1 Solar Photovoltaic Array | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | RE: 3943 Submittal 007 Loop Detector | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | FW: NDOT 3945 Submittal 17 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Contract #3931 Submittal #18 Electrical #2 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | FW: NDOT 3945 Submittal 11 R1 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Contract #3931 Submittal #14.1 Electrical #1 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Contract No. 3956 - Titan Submittal Set 6 - Meter Service | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | 3960 Submittal 007 | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | 3960 Submittal 009 | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Contract #3955 Submittal #26.2 Solar Photovoltaic Array | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | RE: 3952 Mt Rose Bike Path - Luminaires Submittal 1.2 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | RE: 3943 Submittal 003 No.5 Pull Box Mod | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | RE: 3943 Submittal 002 - No. 3.5 Pull Box Mod | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | FW: 3947 Submittal 025R1-623 Luminaires | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | FW: NDOT 3939 Submittal #28 - Electrical #7 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Contract No. 3956, Re-Submittal for Item No. 623 1600, Solar Photovoltaic Array | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Add Luminaire Replacement Scope | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 11 | 11 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | RRFB Plan adjustments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 17 | 17 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 17 | 17 | 0 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Update ITS Linework & Labels | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 44 | 41 | 3 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Seeding/Environmental Coordination | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | DMS cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | 3892 Submittal No. 296-299, Pull Boxes | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract 3948 Submittal 046-623 Pull Boxes | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract 3948 Submittal 047-623 HDPE Conduits 623 1795, 623 1820, 623 1850 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract 3948 Submittal 048-623 Traffic Signal Cable, Bid Items 623 2045, 623 2070, and 623 2090 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | RE: 3947 Submittal 53 - 623 Strut Anchors | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Re: Contract 3947 Submittal 049-623 Trench Components (PAR WLC 20) for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract No. 3956, Resubmittal for Luminaire | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract No. 3956, Submittal for Signal Head 1W1C, Mast Arm, Submittal Group 22 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract No. 3956, Submittal for Geotextile Fabric for Trenching in Native Material | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | ITS Design - Linework | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS Design - Cut sheets | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS General Notes | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS Schedules | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS Coversheet/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract 3948 Submittal 049-623 ITS Vaults, Bid Item 623 0201 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | 3948 Submittal 050-623 Conductors, Bid Items 623 1985, 623 19 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | RE: Contract No. 3956, Re-Submittal for Item No. 623 1600, Solar Photovoltaic Array | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Labels - ITS Design | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 69 | 69 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Construction Notes - ITS Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 69 | 69 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Set Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Update Schedules | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | SP Research & Requests | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 69 | 69 | 0 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Research on Solar power/Ex. Service Pedastal | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 1.5 | 1.5 | 0 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Build Features & PBIs | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 1.5 | 1.5 | 0 |  | TRUE
54531 | EA 74449 - US-50, Middlegate | On-Hold | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Build Features & PBIs | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 1.5 | 1.5 | 0 |  | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Research on Solar power/Ex. Service Pedastal | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 1.5 | 1.5 | 0 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Framework | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 35 | 33 | 2 |  | TRUE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Project buildout | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Project Buildout | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract 3948 Submittal 058-623 Loop Detectors Bid Items 623 0825 and 623 0830 for approval | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract 3948 Submittal 059-623 Luminaires Bid Items 623 0267 and 623 0268 for approval | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract 3948 Submittal 060-623 Milbank Bid Item 623 1061 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Project Build-out | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Framework | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Project Buildout | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Framework | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Review As-Built Plans | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 4.5 | 4.5 | 0 |  | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Design Framework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 4.5 | 4.5 | 0 |  | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Design - Cut sheets | New |  |  | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Design - Cut Sheets | New |  |  | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | SP Justification Letter and Meeting | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 4.5 | 4.5 | 0 |  | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | SP Requests $ | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 4.5 | 4.5 | 0 |  | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 0.5 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 | 2024-07-30 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2024-10-29 | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2024-10-29 | FALSE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Design Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Build-Out | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Research/As-Builts | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | ITS Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | ITS General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | ITS Design (excluding trunkline) | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | ITS Schedules | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Revisions - Truck Ramp changes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  |  | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting Schedule & Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Intermediate Coordination Efforts | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 10 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 10 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Contract 3948 Submittal 061-623 Street Name Signs Bid Items 623 2200 and 623 2210 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | RRFB Schedules | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Intermediate Design Conflict Efforts | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Intermediate Review Utility and UPRR Conflicts | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Lighting Voltage Drop | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Cover/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Special Details | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Schedule & Structure List | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | General Notes | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Cutting Sheets for Design work | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Clearing and Grubbing/Seeding | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Intermediate Estimate | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Intermediate Structure List | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Intermediate Compile and Submit | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Confirm QC Comments on Intermediate Internal Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Provide Intermediate Shared Review Comments $ | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Provide Comments Intermediate Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  |  | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0.5 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Address Internal Review Comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Address Shared Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 42.5 | 38 | 4.5 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Request Service Pedestals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Review As-Built Plans | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | QA/QC Estimate | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | QA/QC Structure List | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | QA/QC Compile and Submit | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Provide Comments QA/QC Internal Review | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Confirm QC Comments on QA/QC Internal Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New |  | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts | New |  | 0.5 | 8.5 | 2 | 6.5 | 2024-09-27 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Shared Review Comments | Conditional |  | 2 | 8.5 | 2 | 6.5 | 2024-09-27 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Address Internal Review Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 8.5 | 2 | 6.5 | 2024-09-27 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 8.5 | 2 | 6.5 | 2024-09-27 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 8.5 | 2 | 6.5 | 2024-09-27 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 8.5 | 2 | 6.5 | 2024-09-27 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Post DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 1 | 1 | 0 | 1 | 2024-09-27 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Lighting Special Details | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | Removed |  | 0 | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Lighting Cover/Key Map | Done | William Renter <wrenter@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Lighting Linework and Labels | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Lighting Schedules | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Lighting General Notes | Done | William Renter <wrenter@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 0 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | ITS General Notes | Done | William Renter <wrenter@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | ITS Schedules $ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | ITS Linework/Labels/Construction Notes | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | ITS Cover/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Intermediate Shared Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Internal Review | Done | Connie Ullas <cullas@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Accept/Reject Internal Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Estimate | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Intermediate Compile and Submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Clearing and Grubbing/Seeding | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Address Intermediate Shared Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Address Intermediate Internal Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Confirm QC Comments on QA/QC Internal Review | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Provide Comments QA/QC Internal Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit (Review A/C) | New |  | 2 | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Update Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Update Estimate | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 13 | 9 | 4 | 2024-05-08 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Lighting Construction Notes $ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Lighting Cut Sheets | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | ITS Cut Sheets $ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 35.5 | 35.5 | 0 |  | TRUE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Intermediate Review Utility and UPRR Conflicts | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Intermediate Design Conflict Efforts | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 2 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 2 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0.5 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Internal Review Comments | New |  | 4 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Shared Review Comments | New |  | 2 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New |  | 1 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 2 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 17.5 | 0 | 17.5 | 2024-12-08 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts | New |  | 0.5 | 8.5 | 0 | 8.5 | 2024-10-28 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Internal Review Comments | New |  | 2 | 8.5 | 0 | 8.5 | 2024-10-28 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Shared Review Comments | New |  | 2 | 8.5 | 0 | 8.5 | 2024-10-28 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 8.5 | 0 | 8.5 | 2024-10-28 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 8.5 | 0 | 8.5 | 2024-10-28 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 8.5 | 0 | 8.5 | 2024-10-28 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Post DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 1 | 1 | 0 | 1 | 2024-10-28 | FALSE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-10-20 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 15 | 2 | 13 | 2025-10-20 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Comments | New |  | 4 | 15 | 2 | 13 | 2025-10-20 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Address Internal Review Comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 15 | 2 | 13 | 2025-10-20 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 15 | 2 | 13 | 2025-10-20 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 15 | 2 | 13 | 2025-10-20 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 15 | 2 | 13 | 2025-10-20 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 15 | 2 | 13 | 2025-10-20 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 15 | 2 | 13 | 2025-10-20 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 15 | 2 | 13 | 2025-10-20 | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Fiber Revisions - Tie in at Spooner Junction & Interconnect 12-strand | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | ITS Design - Linework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | ITS Design - Cut sheets | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | ITS Design - Coversheet/Key Map | Done | William Renter <wrenter@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | ITS Design - General Notes | Done | William Renter <wrenter@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 0 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | ITS Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | ITS Construction Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | ITS Schedules | Done | William Renter <wrenter@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Estimate | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Compile and Submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Intermediate Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | Kaur, Navneet <nkaur@dot.nv.gov> | 0 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | ITS Internal Review $$ | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Accept/reject Internal Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Intermediate Shared Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | ITS Address Review Shared Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 9 | 6 | 3 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | ITS Address Review Internal Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 9 | 6 | 3 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Accept/reject Internal PS&E Review Comments | New |  | 1 | 9 | 6 | 3 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Provide PS&E Shared Review Comments | Committed | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 9 | 6 | 3 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review | New |  | 1 | 9 | 6 | 3 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | QA/QC Compile and Submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 9 | 6 | 3 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | QA/QC Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 9 | 6 | 3 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | QA/QC Estimate | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 9 | 6 | 3 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2024-01-08 | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 11 | 0 | 11 | 2024-01-08 | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address Internal Review Comments | New |  | 1 | 11 | 0 | 11 | 2024-01-08 | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 11 | 0 | 11 | 2024-01-08 | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Comments | New |  | 1 | 11 | 0 | 11 | 2024-01-08 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Design linework and labels | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 6 | 35 | 33 | 2 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 11 | 0 | 11 | 2024-01-08 | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 11 | 0 | 11 | 2024-01-08 | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 11 | 0 | 11 | 2024-01-08 | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 11 | 0 | 11 | 2024-01-08 | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 11 | 0 | 11 | 2024-01-08 | TRUE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Framework | Conditional | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Cover/Key Map | New |  | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Schedule & Structure List | New |  | 4 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 0.5 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Design linework and labels | New |  | 6 | 31 | 3 | 28 | 2024-08-01 | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Cutting Sheets for Design work | New |  | 2 | 31 | 3 | 28 | 2024-08-01 | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | QA/QC StructList & Estimate | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | QA/QC Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | FALSE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 1 | 1 | 0 | 1 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Lead Designer Respond to IR Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Address Comments Internal Reviews - Lighting | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 26 | 26 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | 3954 Submittals 109 &112 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Contract 3948 Submittal 068-623 Steel Pole Shop Drawings for approval | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | 3943 Submittal - 077 - Solar Photovoltaic Array | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | 3943 Submittal - 078 - Signal Head | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Contract 3947 Submittal 064-623 Underground Electric Service Bid Item 623 1620 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | 3948 Submittal 057-623 Emergency Vehicle Optical Detector System Bid Item 623 0815 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Contract 3948 Submittal 063-623 Type R Controller Cabinet for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | 3954 Submittals 113 & 114 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | FW: NDOT 3905_Sub 0380_623 - Expansion Couplings 2-inch 3-inch 4-inch | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Post DOC | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Review Meeting | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 8 | 8 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Post DOC | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Update ITS Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Post DOC | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Update Schedules and Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 8 | 8 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Post DOC | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Compile CO Set | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Post DOC | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Memo | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 8 | 8 | 0 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | ROW Setting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 60 | 9 | 51 |  | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Lighting Design - Cut Sheets | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Framework | Done | William Renter <wrenter@dot.nv.gov> | 1 | 7 | 7 | 0 | 2024-02-09 12:30 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Signal Design - Coversheet/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Signal Design - Cut sheets | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Design - General Notes | On-Hold | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Design - Linework | Committed |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | ITS Cover/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS General Notes | Done | William Renter <wrenter@dot.nv.gov> | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS Linework/Labels/Construction Notes | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | ITS Schedules & Structure List | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | ITS Special Details | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Lighting Linework Update | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting Cover/Key Map | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Lighting General Notes | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Lighting Linework/Labels | Done | William Renter <wrenter@dot.nv.gov> | 4 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting Schedule & Structure List | Done | William Renter <wrenter@dot.nv.gov> | 4 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Lighting keymap/coversheet | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team Intermediate Coordination Meeting | New |  |  | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | On-Hold |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Signals General Notes | Done | William Renter <wrenter@dot.nv.gov> | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Signals Linework/Labels/Construction Notes | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Signals Schedule & Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 6 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Clearing and Grubbing/Seeding | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | Approved | William Renter <wrenter@dot.nv.gov> | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | Approved |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | Approved |  | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-10-27 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  |  | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 | 2025-07-28 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 | 2025-07-28 | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Post DOC | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Labels/Construction Notes | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 8 | 8 | 0 |  | TRUE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | DOC #3 tasks | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT review | New |  | 1 | 1 | 0 | 1 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Contract 3948 Submittal 073-623 Flashing Beacons, Bid Item 623 1104 for approval | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Contract 3948 Submittal 072-623 Traffic Signals, Bid Items 623 0735, 0740, 2475, 2420, 2530 for approval | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | RE: Contract No. 3961, Group 3 Submittal, Pull Boxes | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | FW: NDOT 3972 - Pershing Chip - Luminaire Submittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | 3892 Resubmittals No. 53-1 and 54-1 - For the Couplers only | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Contract No. 3961, Submittal for Group 6, Loop Detector | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Contract No. 3961, Submittal Group 3, Conduit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | FW: 3974 Submittal 021 Electrical Package 3 - Additional Supplies | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | FW: 3974 Submittal 020 Electrical Package 2 - Luminaire & Poles | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | FW: 3974 Submittal 019 Electrical Package 1 - Pull Boxes | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Contract #3955 Conduit and signal Head submittal | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | 3954 Submittals 119-121 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 128.5 | 128.5 | 0 |  | FALSE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Review As-Built Plans | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Project Cleanup | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | District 1/RTC-FAST Signal Coordination | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Lighting Design | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Request Service Pedestals | New |  |  | 2 | 0 | 2 |  | FALSE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Signal Address Internal Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Bring to 100% Design | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting and Signal Address Shared Review Comments | New |  | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Lighting Address Internal Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 0.5 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | Committed | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | QA/QC Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | QA/QC Estimate | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Create writeup for MicroStation Level Control | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Enter SP Photos into AMP | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 69 | 69 | 0 |  | FALSE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Trunkline - 1st pass | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | ITS Construction notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | ITS sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting Construction Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Lighting sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Splice Diagrams - Init | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS Details | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New |  | 4 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New |  | 4 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cleanup | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Lighting Additional Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | ITS Additional Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | 3940 Submittal - 122 - Sign Lighting Fixture, LED | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | 3954 Submittal 112-R1 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | 3954 Submittal #109-R1 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | FW: 3974 Submittal 032 Electrical Package 4 - Cabinet and controllers.pdf | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | 3954 Submittal 120-R1 1-1/2" Metal Conduit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | 3943 Submittal - 004R1- Luminaire type B | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | FW: 089 Submittal - NDOT 3943 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | FW: NDOT Contract #3940 Resubmittals | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | FW: NDOT 3945 Wire submittal 18 - Group 22 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | 3940 Submittal Missing Loop Lead In Cable NO Bid Item | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | FW: 3974 Submittal 034 Electrical Package 5 3" conduit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Submittal 089-1 Resubmittal - NDOT 3943 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | FW: 3974 Submittal 035 - Electrical Package 6 - Weight in Motion | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Plot & Submit to Roadway | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 9 | 9 | 0 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Miscellaneous Review for Intermediate Plan finalize | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 35 | 33 | 2 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Post DOC | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Changes to Change Order 8 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Update Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Build Features & PBIs | Done | William Renter <wrenter@dot.nv.gov> | 1 | 7 | 7 | 0 | 2024-02-09 12:30 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Review As-Built Plans | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 7 | 7 | 0 | 2024-02-09 12:30 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Request Service Pedestals | Done | William Renter <wrenter@dot.nv.gov> | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Build Features & PBIs | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 5 | 5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Review As-Built Plans | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 5 | 5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Design Framework | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 5 | 5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | ITS Special Details | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | ITS General Notes | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | ITS Schedules & Structure List$ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | ITS Linework/Labels/Construction Notes | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | ITS Cover/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Plan modifications for the new Chain up area sign | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 35 | 33 | 2 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Compile and Submit (New) | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 35 | 33 | 2 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Submittal 077-1 Resubmittal - NDOT 3943 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | ITS Linework/Labels Pt 2 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Lighting Linework/Labels Pt 2 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Supplemental #1 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 27 | 27 | 0 |  | FALSE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Repopulate Lighting Conduit schedules | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Complete population of ITS Schedules | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Merge RRFB design into ITS & Trunkline Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Supplemental #1.1 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 27 | 27 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | RWIS Details - Spooner & Zephyr Cove | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Coordination with TOTS Network Team | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 44 | 41 | 3 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Update Solar Sites | Done | William Renter <wrenter@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Solar Design Sheet Formatting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Bridge Rail Coordination and Conduit Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | TRUE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Lighting Design Updates | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | FW: 3974 Submittal 51 Electrical Package 8 Geotextile.pdf | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Contract 3948 Submittal 049r1-623 ITS Vaults r1, Bid Item 623 0201 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | NDOT Contract 3973 Submittals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Contract 3948 Submittal 068r1-623 Steel Pole Drawings r1 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | 3979 I-15 SB: Submittals 004, 005, 006 - #5 Pull Box, Conduit, Traffic Loops | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | 3792 Submittals, 462R1,471R1, 475, 476, 477, | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | FW: NDOT 3939 Submittal #32 - Electrical #9 | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Contract 3948 Submittal 074r1-623 2210 IISNS Double Face Sign r1, Bid Item 623 2200 and 623 2210 for approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | 3858 RE Submittal 94 FW: Titan Electrical - PV Panel Resubmittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Solar Array Schedules Updates | Done | William Renter <wrenter@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Field Visit - FT | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Cave Rock Detail/Inset #1 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Scoping Template & Project Buildout | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 71 | 71 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | FW: ITS Material Submittals | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | FW: 3974 I-80 Wendover - Submittal 019 Revision 1 - Electrical Package 1 - Pull boxes | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & Schedules Updates: REMOVED | New |  | 0 | 20 | 20 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | RE: Contract 3948 Submittal 073-623 Flashing Beacons, Bid Item 623 1104 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | 3940 - Submittal 011R1- 623.1056 – Modify Signal Cabinet | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Contract 3948 Submittal 046r1-623 Pull Boxes for approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Contract No. 3956, Group 5 Submittal for Solar Photovoltaic Array | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (8) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2023 Professional Training |  | Signals Lighting and ITS | Professional Training for 10 of Hours | Done |  |  | 6 | 6 | 0 |  | TRUE
52656 | Staff Training | Potential | 2023 Professional Training |  | Signals Lighting and ITS\2023 Sprint 16 | Professional Training for 10 Hours | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Solar Design Sheet Formatting (General) | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | ADA work to be in Ph.2 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Post-DOC | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Change Order #3 Plan modifications | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 8 | 29 | 29 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | ITS Design - Special Details | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 20 | 20 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Resubmittal | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 17 | 17 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Address ITS IR comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Address LTG IR Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | On-Hold |  | 0 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 1 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 7.5 | 1 | 6.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | ITS Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | ITS General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | ITS Linework/Labels/Construction Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | ITS Schedules & Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Lighting Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Lighting General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Lighting Linework/Labels/Construction Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Lighting Schedule & Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Lighting Voltage Drop | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Intermediate Coordination Efforts | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Confirm QC Comments on Intermediate Internal Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | 30% Design (1st Intermediate Design) | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Plan Construction Notes | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 14 | 14 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | 30% Design (1st Intermediate Design) | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Symbology | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 14 | 14 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | 30% Design (1st Intermediate Design) | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Plan Sheets | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 14 | 14 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Research folder created | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | As-Builts | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Service Pedestals | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Strategic Deployment Plan | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Create PMP | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Linework | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Labels | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Construction Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Plan Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\Sprint 2 | Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 8 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\Sprint 2 | Estimate | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\Sprint 1 | Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\Sprint 2 | Structure List | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Modify ITS Test Site Plans | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | EA74228 Intermediate Design to Specs | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | C3692 - WWD Change Order | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Q0-136-19-016 Airport Rd. submittal | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 9100 - Review PMP and create individual project PMP - Rick | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Review PMP and create individual project PMP - Pete | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Review PMP and create individual project PMP - Laura | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Equipment Cabinet Specification | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Equipment Cabinet Testing Procedure | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | 9100 - Equipment Cabinet Special Detail | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 81 | 81 | 0 |  | FALSE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | EA 73976 Railroad Advanced Warning Flashers Modification | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | 210005 at stage Permit in Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | 210066 at stage Permit in Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | 210094 at stage Permit in Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 3745 - Conduit Routing RFI | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 1 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 3697 - As-Builts Review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | 74235 - Sheckler Signal Intermediate Set mod | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 47 | 47 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Intermediate Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | QAQC Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | DOC Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3772 - EA 73879 - Tropicana Ph 2A |  | Signals Lighting and ITS | Add missing pull boxes to schedules | Done | Jordan James <jjames@dot.nv.gov> | 2 | 17 | 17 | 0 |  | TRUE
10994 | Done | Potential | C3772 - EA 73879 - Tropicana Ph 2A |  | Signals Lighting and ITS | Add #5 PB to Structure List & Estimate | Done |  | 1 | 17 | 17 | 0 |  | TRUE
10994 | Done | Potential | C3772 - EA 73879 - Tropicana Ph 2A |  | Signals Lighting and ITS | Clarify use of #12 conductor | Done | Jordan James <jjames@dot.nv.gov> | 2 | 17 | 17 | 0 |  | TRUE
10994 | Done | Potential | C3772 - EA 73879 - Tropicana Ph 2A |  | Signals Lighting and ITS | Add conduit quantity under appropriate column | Done | Jordan James <jjames@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
10994 | Done | Potential | C3772 - EA 73879 - Tropicana Ph 2A |  | Signals Lighting and ITS | Incorporate NVE Design into Plans | Done |  | 4 | 17 | 17 | 0 |  | TRUE
10994 | Done | Potential | C3772 - EA 73879 - Tropicana Ph 2A |  | Signals Lighting and ITS | Review/Address the County's comments | Done | Jordan James <jjames@dot.nv.gov> | 4 | 17 | 17 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3788 - 60693 - District 3 ITS Smart Zones |  | Signals Lighting and ITS | update IPD and Estimate | Done | Jordan James <jjames@dot.nv.gov> | 2 | 25 | 25 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3788 - 60693 - District 3 ITS Smart Zones |  | Signals Lighting and ITS | Submit Estimate to Manager 1 for review; update as needed | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25 | 25 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3788 - 60693 - District 3 ITS Smart Zones |  | Signals Lighting and ITS | DOC Submittal Processing | Done | Jordan James <jjames@dot.nv.gov> | 4 | 25 | 25 | 0 |  | TRUE
10994 | Done | Potential | EA 74267 - EA 74030 - I-515 & Charleston Interchange |  | Signals Lighting and ITS | Review email and provide comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 11 | 3 | 8 |  | TRUE
16329 | DOC'ed | Potential | C3805/EA 60916 - I-15 from Mesquite to NV/AZ State Line 3R (formerly EA 74149) |  | Signals Lighting and ITS | Design ramp lighting | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 8 | 24 | 24 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3805/EA 60916 - I-15 from Mesquite to NV/AZ State Line 3R (formerly EA 74149) |  | Signals Lighting and ITS | ITS Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 24 | 24 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3805/EA 60916 - I-15 from Mesquite to NV/AZ State Line 3R (formerly EA 74149) |  | Signals Lighting and ITS | Design utility trunkline | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 24 | 24 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74169 I-80 at Dun Glen to PE/HU County Line |  | Signals Lighting and ITS | Design ramp lighting | Done | Jordan James <jjames@dot.nv.gov> | 8 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74169 I-80 at Dun Glen to PE/HU County Line |  | Signals Lighting and ITS | ITS Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74169 I-80 at Dun Glen to PE/HU County Line |  | Signals Lighting and ITS | Design utility trunkline | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 32 | 32 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Q0-136-19-016 Address review comments | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 74043 S. McCarran - Address review comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 8 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Update PMPs - Pete | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 3697 Garnet Interchange - Review/Comment Garnet AGBW Signal Design | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 73976 UPRR AWS update drawings on the correct design files | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | 73650 - Ely Intermediate Resubmittal | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3805/EA 60916 - I-15 from Mesquite to NV/AZ State Line 3R (formerly EA 74149) |  | Signals Lighting and ITS | QAQC Submittal | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 24 | 24 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74169 I-80 at Dun Glen to PE/HU County Line |  | Signals Lighting and ITS | Intermediate Submittal | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Develop Alternate Luminaire and Pole Option - Ely | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 94 | 94 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 3697 Garnet Interchange - Submittal 297 Rev 1 - Record Drawings (As-Builts) for Project Close-Out Review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 1 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | 210218 at stage Permit in Review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Linework | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Labels | Done | Jordan James <jjames@dot.nv.gov> | 2 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Construction Notes | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Plan Notes | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Schedules | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Special Detail - Retroreflective border retrofit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Structure List | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Intermediate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | QAQC Submittal | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | DOC Submittal | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Create PMP | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Research Folder | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | As-builts | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 75 | 75 | 0 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - completed items only | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - completed items only | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 9 | 9 | 0 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - completed items only | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
10994 | Done | Potential | C3760 - EA 73650 - EA 60811 - Ely 3R from 1st st to Ruth and US 6 |  | Signals Lighting and ITS | Create Plan Sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 10 | 10 | 0 |  | TRUE
10994 | Done | Potential | C3760 - EA 73650 - EA 60811 - Ely 3R from 1st st to Ruth and US 6 |  | Signals Lighting and ITS | Modify Schedules and Structure List | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 10 | 10 | 0 |  | TRUE
10994 | Done | Potential | C3760 - EA 73650 - EA 60811 - Ely 3R from 1st st to Ruth and US 6 |  | Signals Lighting and ITS | Compile and Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 10 | 10 | 0 |  | TRUE
10994 | Done | Potential | C3740 - 73844 - 60713 - Fast Pkg H3 |  | Signals Lighting and ITS | 3740 RFI Question 1 | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 20 | 20 | 0 |  | TRUE
10994 | Done | Potential | C3740 - 73844 - 60713 - Fast Pkg H3 |  | Signals Lighting and ITS | 3740 RFI Question 2 | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 20 | 20 | 0 |  | TRUE
10994 | Done | Potential | C3740 - 73844 - 60713 - Fast Pkg H3 |  | Signals Lighting and ITS | 3740 RFI Question 3 | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 20 | 20 | 0 |  | TRUE
10994 | Done | Potential | C3740 - 73844 - 60713 - Fast Pkg H3 |  | Signals Lighting and ITS | 3740 RFI Question 4 | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 20 | 20 | 0 |  | TRUE
10994 | Done | Potential | C3740 - 73844 - 60713 - Fast Pkg H3 |  | Signals Lighting and ITS | 3740 RFI Question 5 | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 20 | 20 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | 30% Design (1st Intermediate Design) | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | 74107 Shared Review Comments | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 4 | 14 | 14 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 9100 Livestock Flashing Sign | Done | Jordan James <jjames@dot.nv.gov> | 8 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 9100 Wildlife Flashing Sign | Done | Jordan James <jjames@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS | Email QAQC Design Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS | Signal Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS | Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS | Structures List | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS | Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS | Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS | Peer Review | Done | Jordan James <jjames@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Update Sheet Notes | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Update Structure List | Done | Jordan James <jjames@dot.nv.gov> | 2 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 2 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3788 - 60693 - District 3 ITS Smart Zones |  | Signals Lighting and ITS | Post-PS&E Review | Done | Jordan James <jjames@dot.nv.gov> | 4 | 25 | 25 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3740 - Submittal 023 - Solar Photovoltaic Array | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit in Review 210299 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | C3703 One-Line Diagram | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | 74108 I580 "Waterloo" - PDFS Prep | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 14 | 14 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | 74108 - I580 "Waterloo" - PDFS Meeting | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 14 | 14 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | 74108 - I580 "Waterloo" - PDFS Report | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 14 | 14 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | 74153 Mt. Rose Hwy - PDFS Prep | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | 74153 Mt. Rose Hwy - PDFS Meeting | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | 74153 Mt. Rose Hwy - PDFS Report | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 8 | 8 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3788 - 60693 - District 3 ITS Smart Zones |  | Signals Lighting and ITS | Update IPD and Estimate Again | Done | Jordan James <jjames@dot.nv.gov> | 2 | 25 | 25 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | 73937 Site Visit | Done | Jordan James <jjames@dot.nv.gov> | 8 | 50 | 50 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | 73937 Site Visit Prep | Done | Jordan James <jjames@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Elks Point Signal Estimate | Done | Jordan James <jjames@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Clark County/Swenson ITS 30% Review | Done | Jordan James <jjames@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210393 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 209738 | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210426 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210116 | Done | Jordan James <jjames@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | RRFB Estimate at US-395@Lucerne | Done | Jordan James <jjames@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit Norway Drive & USA Parkway | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | 73937 Site Visit Documentation | Done | Jordan James <jjames@dot.nv.gov> | 4 | 50 | 50 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3805/EA 60916 - I-15 from Mesquite to NV/AZ State Line 3R (formerly EA 74149) |  | Signals Lighting and ITS | DOC Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS | Consultant Design Review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 8 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Revise ITS sheets with new trunk line geometry | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Change pedestal at 7th st. to new | Done |  |  | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 60888 - McCarran Blvd Safety Improvements |  | Signals Lighting and ITS | Review Submittal | Done | Jordan James <jjames@dot.nv.gov> | 2 | 2 | 2 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Intermediate Review | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74169 I-80 at Dun Glen to PE/HU County Line |  | Signals Lighting and ITS | PS&E Review | Done | Jordan James <jjames@dot.nv.gov> | 4 | 32 | 32 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Insert splice diagram | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 46 | 46 | 0 |  | FALSE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Internal review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 0 | 46 | 46 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Update Design | Done | Jordan James <jjames@dot.nv.gov> | 8 | 47 | 47 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74228 - Ely Reservation Conduit Project |  | Signals Lighting and ITS | Call RoW to determine status. | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 14 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74228 - Ely Reservation Conduit Project |  | Signals Lighting and ITS | Sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 14 | 14 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74228 - Ely Reservation Conduit Project |  | Signals Lighting and ITS | Make changes based on 60% review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 14 | 14 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3762 - Submittal No. 04 - Field Cabinets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3762 - Submittal No. 05 - CCTV | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3762 - Submittal No. 06 - Ethernet Switches | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3762 - Submittal No. 07 - Radar | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3762 - Submittal No. 12 - Light Fixtures | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS | 85% Submittal Review | Done | Jordan James <jjames@dot.nv.gov> | 8 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Address comments from Intermediate Review | Done | Jordan James <jjames@dot.nv.gov> | 2 | 47 | 47 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3762 - Submittal No. 09 - RWIS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3762 - Submittal No. 11 - DMS Sign | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Sumbit QAQC to Roadway | Done | Jordan James <jjames@dot.nv.gov> | 4 | 47 | 47 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Internal Review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 47 | 47 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Update Structure List and Estimate | Done | Jordan James <jjames@dot.nv.gov> | 4 | 47 | 47 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74228 - Ely Reservation Conduit Project |  | Signals Lighting and ITS | Make changes based on 90% review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 14 | 14 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | Incorporate Site Visit Info | Done | Jordan James <jjames@dot.nv.gov> | 4 | 50 | 50 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | Incorporate Intermediate Submittal Comments | Done | Jordan James <jjames@dot.nv.gov> | 4 | 50 | 50 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | Update Plans | Done | Jordan James <jjames@dot.nv.gov> | 16 | 50 | 50 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | Submit QAQC | Done | Jordan James <jjames@dot.nv.gov> | 4 | 50 | 50 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3762 - Submittal #8 - Service Pedestals | Done |  | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3740 - Submittal 028R1 - RWIS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Gemfield Intermediate Review 20161306 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | N. Las Vegas video detection upgrades phase 2 - 60892 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 66 | 66 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73879 - Tropicana Ph 2B - CL Portion (LVB to Maryland Pkwy) |  | Signals Lighting and ITS | Replace Signal Cabinets | Done | Jordan James <jjames@dot.nv.gov> | 8 | 18 | 18 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73879 - Tropicana Ph 2B - CL Portion (LVB to Maryland Pkwy) |  | Signals Lighting and ITS | Change Interconnect | Done | Jordan James <jjames@dot.nv.gov> | 4 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | EA 60908: City of Henderson Anthem Rose Trail 100% Review | Done | Jordan James <jjames@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | EA 73949: Gardnerville Crosswalks LPA Project 90% Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210652 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210653 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74228 - Ely Reservation Conduit Project |  | Signals Lighting and ITS | Traffic Control Meeting | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 14 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74169 I-80 at Dun Glen to PE/HU County Line |  | Signals Lighting and ITS | Update Plans | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74169 I-80 at Dun Glen to PE/HU County Line |  | Signals Lighting and ITS | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 2 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74169 I-80 at Dun Glen to PE/HU County Line |  | Signals Lighting and ITS | Submit DOC set | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 32 | 32 | 0 |  | TRUE
10994 | Done | Potential | EA 74193 - EA 60887 - McCarran @ Baring Roundabout |  | Signals Lighting and ITS | Review Lighting Study | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 2 | 2 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS | QAQC Submittal | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 8 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3795 - EA 60789 - US-50 Betterment Lighting Project |  | Signals Lighting and ITS | DOC Submittal | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 8 | 8 | 8 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | As-built search - I-15 & Cheyenne | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | 90% Estimate to Kevin for Price Checking | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Revise schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 94 | 94 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | RSA US 50 Leeteville Junction to Virginia St. | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Update Plans | Done | Jordan James <jjames@dot.nv.gov> | 8 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Update Schedules | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Update Estimate and Structure List | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS | 74192 - PDFS Preparation | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS | 74192 - PDFS Site Visit | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS | Adjust Pull Box out of ditch | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Pothole locations to Roadway | Done | Jordan James <jjames@dot.nv.gov> | 4 | 47 | 47 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | As-built Contract Document Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | 74108 - 30% Design Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 14 | 14 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Review Special Provisions | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Revise plan sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Luminaire coordination | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Compile & submit QAQC | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 94 | 94 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Review & Create breakouts where appropriate | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 46 | 46 | 0 |  | FALSE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Plan Review - Peer | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 0 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Voltage drop calcs | Done |  |  | 94 | 94 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210750 | Done | Laura Vargo <lvargo@dot.nv.gov> |  | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3765 - Submittal 032 - Steel Pole Type 7 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3765 - Submittal 033 - Steel Pole Type 7 with Safety Base | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3765 - Submittal 034 - Steel Pole Type 14 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3765 - Submittal 035 - Steel Pole Type 30 Feet | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 34 | 34 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3788 - 60693 - District 3 ITS Smart Zones |  | Signals Lighting and ITS | RFI Responses | Done | Jordan James <jjames@dot.nv.gov> | 8 | 25 | 25 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3788 - 60693 - District 3 ITS Smart Zones |  | Signals Lighting and ITS | Red-line plan set | Done | Jordan James <jjames@dot.nv.gov> | 4 | 25 | 25 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Redo estimate based on split | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Adjust quantities based on redrawing of county line | New |  | 1 | 39 | 0 | 39 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Add splice details to ITS sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Review Special Provisions | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 94 | 94 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | PDFS Report | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 46 | 46 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PMP Review & Comments | Done | Jordan James <jjames@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | 74108 - 30% Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 14 | 14 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS | 74192 - PDFS Site Visit | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Miscellaneous - PRR for Pattinari | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Detailed Drawing for Service Pedestal | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 81 | 81 | 0 |  | FALSE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Contract Document Review | Done |  |  | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 209882 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | ADA Training | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Miscellaneous - Create PROWAG Design guidelines for SLI | Approved | Laura Vargo <lvargo@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | DOC Submittal (1st iteration) | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 94 | 94 | 0 |  | TRUE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Provide Comments Intermediate Internal Review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 1 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Clearing and Grubbing/Seeding | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Intermediate Compile and Submit | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Intermediate Estimate | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Intermediate Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | On-Hold |  | 0 | 0.5 | 0 | 0.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | On-Hold |  | 0 | 0.5 | 0 | 0.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | On-Hold |  | 0 | 0.5 | 0 | 0.5 | 2025-08-12 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | ITS Design - Cut sheets | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Lighting Design - Cut Sheets | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | SP Justification Letter | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | SP Requests $ | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Design Framework | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | ITS Address Review Internal Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Lighting Address Internal Review Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 0.5 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0.5 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Confirm QC Comments on QA/QC Internal Review | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 0.5 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 0.5 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Provide Comments QA/QC Internal Review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 1 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 15 | 5 | 10 | 2025-08-27 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 15 | 5 | 10 | 2025-08-27 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Planset Cleanup | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 44 | 41 | 3 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Planset Cleanup | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Build Features & PBIs | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | NDOT Contract 3973 Submittals | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | FW: 3954 Submittal No. 50R1 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | FW: 3974 I-80 Wendover - Submittal 019 Revision 1 - Electrical Package 1 - Pull boxes | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | 3973 submittal 31 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | NDOT 3992 Submittals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | 3987 USA Pkwy ITS - Submittal 1.4 - 3-Inch Conduit | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | 3987 USA Pkwy ITS - Submittal 1.3 - ITS Vault | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | 3987 USA Pkwy ITS - Submittal 1.5 & 1.6 - 3-Inch & 4-Inch Conduit (Metal) | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | 3987 USA Pkwy ITS - Submittal 1.7 - 4-Inch Multiduct Conduit | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | 3937 WWD System Submittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | FW: Weigh in Motion Re-Submittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | FW: NDOT 3939 Submittal #39 - Electrical #10 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Contract No. 3956; Group 3 Submittal, Junction Box (Type A) | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Update Structure List & Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Compile and submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Post-DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Design Work | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 3.5 | 3.5 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Post-DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Write-up | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 3.5 | 3.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Post-DOC | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Change Order #3 - Update date | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 29 | 29 | 0 |  | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Junction Box Design Updates | On-Hold |  | 0 | 15.5 | 15.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | RWIS Design | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 23.5 | 23.5 | 0 |  | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | RWIS Coordination | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 23.5 | 23.5 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Research/find the US-50/Deer Run Signal As-builts $ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | 74108 - 30% Design Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 14 | 14 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS | 74192 - PDFS Report | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\Sprint 5 | QAQC Plans Review | Done | Jordan James <jjames@dot.nv.gov> | 8 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS | DOC Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | NDOT and Utility Trunkline Estimates | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Research Existing SLI Impact | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 67.5 | 67.5 | 0 |  | FALSE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210788 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210813 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Plan Review - Designer | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 94 | 94 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Trunkline Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - RRFB Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Signal Design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Internal Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3740 Luminaire B Submittal | Done |  | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3763 - 002 - Electrical Materials | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3724 - High Mast (LED Luminaire and Head Frame Assembly), Luminaire Type B, Sign Lighting | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3763 - 010 - Electrical Poles | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3763 - 014 - ITS Package | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3763 - 002R1 - Electrical Materials w-mule tape | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3740 - Submittal 024 - Communication Cabinet | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3740 - Submittal 025 - CCTV Camera & Lowering Device | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3740 - Submittal 026 & 027 - Encoders & Ethernet Switches, Cellular Modem & Antenna | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3740 - Submittal 028 - RWIS | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | C3760 - EA 73650 - EA 60811 - Ely 3R from 1st st to Ruth and US 6 |  | Signals Lighting and ITS | Internal Review | Done |  | 0 | 10 | 10 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3740 - Submittal 029 - Radar Detection System | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3763 - Submittal 033 - 3" Pipe Posts and Anchors | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3763 - Submittal 027 - 4" 30' Steel Pole and Anchor | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3763 - Submittal 028 - 80' Steel Pole & Anchor Bolts | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3763 - Submittal 029 - 30' ITS Pole | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3762 - Submittal 001 - Conduit & Pull Boxes | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3740 - Submittal 033 - Dynamic Message Signs | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3759 - Submittal 013 No. 8 Conductor | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3759 - Submittal 009 No. 5 Pull Box | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3759 - Submittal 010 Ped Push Buttons | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3759 - Submittal 011 Ped Push Button Extension | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3759 - Submittal 012 2-inch Conduit | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3724 Sign Lighting Submittal | Done |  | 0 | 34 | 34 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74228 - Ely Reservation Conduit Project |  | Signals Lighting and ITS | Internal Review | Done |  | 0 | 14 | 14 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210718 | Done |  |  | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3763 - Submittal 043 Fiber Submittals | Done |  | 1 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3716 - Submittal 139 - Loop detectors & sealant | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3716 - Submittal 139 - Loop detectors & sealant | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3765 - Submittal 044 (email subject line lists 043) - Misc Electrical | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 3745 Submittal #37 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3770 Submittal #22 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3770 - S041-048 & 051 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3770 Submittal 055 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3772 - Sumittals 020 - 032 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3762 - Submittal #21 - Fiber | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3772 - Sumittals 033-40, 42, 43, 48-51 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3762 - Submittal #20 - XF and Enclosures | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3765 - Submittal 062 - Loop Detectors | Done |  |  | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3770 Submittal 081 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3770 Submittals 079 & 080 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3772 39R1 and 42R1 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS | 74038 Review all bid items | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS | PDFS Report | Done | Jordan James <jjames@dot.nv.gov> | 4 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS | 74038 Address Spec Comments #1 | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS\Sprint 6 | 74038 DOC Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 32 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PDFS Report | Done | Jordan James <jjames@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74228 - Ely Reservation Conduit Project |  | Signals Lighting and ITS | TERO coordination | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 14 | 0 |  | TRUE
10990 | On Hold | Potential | District 2 (make project level) |  | Signals Lighting and ITS | Computer work | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 4 | 8 |  | FALSE
10990 | On Hold | Potential | District 2 (make project level) |  | Signals Lighting and ITS | Field Visit | Approved |  | 8 | 12 | 4 | 8 |  | FALSE
10990 | On Hold | Potential | District 2 (make project level) |  | Signals Lighting and ITS | SIte Visit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 12 | 4 | 8 |  | FALSE
16329 | DOC'ed | Potential | C3838 - EA 74193 - EA 60890 - Pyramid Lake Paiute Tribe Ltg and RRFB Safety |  | Signals Lighting and ITS | PS&E Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 1 | 0 | 1 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | PRR for Traffic signals located on SR 50 at SR 207 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 122 | 122 | 0 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - completed items only | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | CRAVE (Oct. 1st) | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - completed items only | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | CRAVE (Oct. 2nd-4th) | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 9 | 9 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 34 | 2 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Address Checking Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 54.5 | 54.5 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Address Specs' Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 2 | 75 | 75 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Update Schedules | Done | Jordan James <jjames@dot.nv.gov> | 1 | 122 | 122 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS | EA 74115 - Trunkline Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS | EA 74115 -Cut Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> |  | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS | EA 74115 - Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS | EA 74115 - Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 40 | 40 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Detail Sheet for Service Pedestal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 54.5 | 54.5 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | WWD Remove and Reset | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 8 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | PDFS Site Visit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Update Trenching Detail | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Update C3736 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Type R Cabinet Add Conduit Detail | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Ped Push Button Extension Special Detail | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Draft email for signal system replacement | Done | Jordan James <jjames@dot.nv.gov> | 2 | 4 | 4 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Work with the design team for signal system and lighting replacement approval | Done | Jordan James <jjames@dot.nv.gov> | 2 | 4 | 4 | 0 |  | FALSE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 210936 | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 0 | 66 | 66 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Estimate Breakdown | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | FALSE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | PS&E Review | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75 | 75 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS | Review CLV comments | Done | Jordan James <jjames@dot.nv.gov> | 4 | 49 | 49 | 0 |  | TRUE
10990 | On Hold | Potential | EA 73861 Fernley Shared Use Path - NO SLI |  | Signals Lighting and ITS | 73861 - Design | New |  |  |  | 0 |  |  | FALSE
10990 | On Hold | Potential | EA 73861 Fernley Shared Use Path - NO SLI |  | Signals Lighting and ITS | 73861 - Schedules | New |  |  |  | 0 |  |  | FALSE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | PDFS Report | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Address comments from Specs | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | FALSE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Determine verbage for City of Reno FHES | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 46 | 46 | 0 |  | FALSE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | PS&E Review | Done | Jordan James <jjames@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Design demarcation point for L&A lighting design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74228 - Ely Reservation Conduit Project |  | Signals Lighting and ITS | Signatures for DOC set | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 14 | 14 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Finalize Design | Done | Jordan James <jjames@dot.nv.gov> | 4 | 47 | 47 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | PS&E Submittal | Done | Jordan James <jjames@dot.nv.gov> | 2 | 47 | 47 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Address Internal Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 4 | 47 | 47 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS | EA 74115 - Interchange Lighting Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74228 - Ely Reservation Conduit Project |  | Signals Lighting and ITS | Submit DOC set | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 14 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Swenson ITS 60% Design Review - LPA | Done | Frederick Tydeman <FTydeman@dot.nv.gov> |  | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 211139 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | PDFS Site Visit | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 67.5 | 67.5 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS | 74038 SP2 Utility Plan Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 32 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Miscellaneous - Mountain Springs Lighting Site Visit | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 211100 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74176 - Cheyenne Ave ADA Improvements |  | Signals Lighting and ITS | Address PS&E Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 75 | 75 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | Address PS&E Comments | Done | Jordan James <jjames@dot.nv.gov> | 4 | 50 | 50 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | DOC Submittal | Done | Jordan James <jjames@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Address PS&E Comments | Done | Jordan James <jjames@dot.nv.gov> | 2 | 47 | 47 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | DOC Submittal | Done | Jordan James <jjames@dot.nv.gov> | 1 | 47 | 47 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS | 74038 DOC Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 32 | 32 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Redlines and Compile Set | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 57 | 57 | 0 |  | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PDFS Meeting | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PDFS Report | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Redline PDF | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Review Bid Items and Special Provisions | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Research | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | PS&E Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Prelim Linework for SUE Meeting | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Citywide School Safety Improvements Project Review | Done |  | 0 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Rest Area ITS Inventory | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | RSA for US 395 Douglas Co | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | C3811 - EA 74207 - EA 74020 - Design-Build SBX |  | Signals Lighting and ITS | CRAVE | Done | Jordan James <jjames@dot.nv.gov> | 8 | 8 | 8 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Temporary Signal Design Sheet | Done | Jordan James <jjames@dot.nv.gov> | 2 | 47 | 47 | 0 |  | TRUE
7672 | EA 74274 - Centerville - Widen B-638 and Road | On-Hold | 30% Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | PDFS Report | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 2 | 2 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS | 74038 Confirm/enact agreement for RRFB's | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Lighting Remove and Reset | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 31 | 31 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Fiber Connection @ NEC Virginia & McCarran | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 46 | 46 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | PDFS Report | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 67.5 | 67.5 | 0 |  | FALSE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Scope/Research | Done | Jordan James <jjames@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Linework | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Risk Reserve - Full signal design (estimate only) | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 94 | 94 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Hatched zone in ITS dgn | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 31 | 31 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 9100 - Current project trunkline meeting | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 9100 - Current project trunkline meeting | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 9100 - Current project trunkline meeting | Done | Jordan James <jjames@dot.nv.gov> | 1 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 9100 - Current project trunkline meeting | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3772 - RFI #6 Signal Pole Structural Impacts of larger signal signs | Done | Jordan James <jjames@dot.nv.gov> | 2 | 34 | 34 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | Set up meeting with Laura | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | Review Material Submittal emails | Done | Jordan James <jjames@dot.nv.gov> | 1 | 34 | 34 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Send out Service Pedestal Request | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | 74108 - Mission Street RRFB ROW Exhibit | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 36 | 34 | 2 |  | TRUE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS | Itemize Temporary Traffic Control | Done | Jordan James <jjames@dot.nv.gov> | 2 | 47 | 47 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Miscellaneous - RFI 3736 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | Pull Asbuilts/Google Drive | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS | EA 74115 - Cut Sheets for ITS | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 11 | 74115 - Note sheets | Done |  | 2 | 40 | 40 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Est in Ipd | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Address Kevin & Rick's comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 8 | 46 | 46 | 0 |  | FALSE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Switch to 4" multiduct | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | FALSE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 211070 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Coordinate w/ Eric for Intermediate Submittal | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 211254 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 31 | 31 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Intermediate Estimate | Done | Jordan James <jjames@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Compile Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS | Update Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 40 | 40 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Request project files | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | PDFS Research | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | Linework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | Labels | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | Structure List and Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Populate Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Structure List and Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Submit Plans | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Excel Est. | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 17 | Labels - Lighting Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | 74272 - Signals Coversheet/Key Map | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | General Notes | Done | Jordan James <jjames@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | Submittals for Review - Clark County Bid No. 605313-19 | Done |  | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3736, RFI #7, NVE Conflict | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Compile and submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Internal Review | Done | Jordan James <jjames@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Linework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Linework | Done | Jordan James <jjames@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | Compile and submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 13 | Linework | Done | Jordan James <jjames@dot.nv.gov> | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 17 | Linework - Lighting Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 13 | Labels | Done | Jordan James <jjames@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | Schedules - Lighting Design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 13 | Schedules | Done | Jordan James <jjames@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | Structure List - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Update Coversheet/Key Map | On-Hold |  | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Update Structure List | On-Hold |  | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Update Estimate | On-Hold |  | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | General Notes | On-Hold |  | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Compile and submit | On-Hold |  | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Update Construction Notes | On-Hold |  | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | C3792 - EA 73536 - Consultant Design - I-15/I-215 Phase 4 |  | Signals Lighting and ITS | Review Bid Items | Done | Jordan James <jjames@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
10994 | Done | Potential | C3792 - EA 73536 - Consultant Design - I-15/I-215 Phase 4 |  | Signals Lighting and ITS | Review plans for revisions made per SLI comments | Done | Jordan James <jjames@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
10994 | Done | Potential | C3792 - EA 73536 - Consultant Design - I-15/I-215 Phase 4 |  | Signals Lighting and ITS | Spot check plans | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | 74138 - Wildlife Warning Sign Detail | Done | Jordan James <jjames@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS | Check GCW Bid Items | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74072 - Consultant Design - Nellis Blvd 3R and ADA |  | Signals Lighting and ITS | QA/QC Review | Done | Jordan James <jjames@dot.nv.gov> | 4 | 11 | 11 | 0 |  | TRUE
10994 | Done | Potential | C3792 - EA 73536 - Consultant Design - I-15/I-215 Phase 4 |  | Signals Lighting and ITS | Compare bid item quantities | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
10990 | On Hold | Potential | SLI Improvements (make project level) |  | Signals Lighting and ITS | Naming Conventions | Approved |  | 2 | 3 | 0 | 3 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\Sprint 1 | Attend Cost Risk Assesment | Done | Jordan James <jjames@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS | Update plans/estimate for school zone flasher | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Comment on PS&E plan set | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 9 | 74115 - Compile and submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 40 | 40 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E plan set | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 46 | 46 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Internal Review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 0 | 31 | 31 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS | Sign NVE Proposals (2) | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS | Review Roadway's price check of SLI work | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Trunkline Detail Revision | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Type 7 with Receptacle Detail Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 94 | 94 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Excavation Calculator | Approved |  | 2 | 146 | 133 | 13 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address 60% Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Labels | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 31 | 31 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Linework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Labels | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74072 - Consultant Design - Nellis Blvd 3R and ADA |  | Signals Lighting and ITS | Review Bid Items | Done | Jordan James <jjames@dot.nv.gov> | 4 | 11 | 11 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | Create Flashing Warning Sign Details | Done | Jordan James <jjames@dot.nv.gov> | 4 | 122 | 122 | 0 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Finalize Flashing Warning Sign Details | Done | Jordan James <jjames@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
10994 | Done | Potential | C3792 - EA 73536 - Consultant Design - I-15/I-215 Phase 4 |  | Signals Lighting and ITS | Review Consultant's Updated Plans | Done | Jordan James <jjames@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
10994 | Done | Potential | C3792 - EA 73536 - Consultant Design - I-15/I-215 Phase 4 |  | Signals Lighting and ITS | Respond to Consultant's Questions | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS | Attend Cost Risk Assesment | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Labels | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 6 | DOC Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 6 | DOC Signal Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73879 - Tropicana Ph 2B - CL Portion (LVB to Maryland Pkwy) |  | Signals Lighting and ITS | Remove trunkline lateral at Maryland Intersection | Done | Jordan James <jjames@dot.nv.gov> | 4 | 18 | 18 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | Linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Structure List | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | Labels | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | Structure List | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS | Submit DOC to Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 54.5 | 54.5 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Intermediate 2 Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 18 | Research | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 2 | Research | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | Linework | Done | Jordan James <jjames@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | Labels | Done | Jordan James <jjames@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | Schedules | Done | Jordan James <jjames@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS | Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Linework | Done |  |  | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Finalize | Done |  | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Labels | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Update & submit estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Structure List | Done |  | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Structure List | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Compile DOC submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 46 | 46 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | RWIS site detail | Done |  | 2 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Address internal review comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Confirm conduit design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | RWIS Details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Meet w/ Roadway regarding R/W for Mission Street RRFB | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | Compile & submit QAQC2 to Roadway | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 2 | Compile & Submit Set | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 2 | QAQC Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | 74153 Internal Review of ITS Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
10994 | Done | Potential | Permit/LPA Processing 2019 |  | Signals Lighting and ITS | Permit 211341 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 13 | Linework - Signal Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 13 | Labels- Signal Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | Schedules - Signal Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | Structure List - Signal Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | 605313-19 CC215 Beltway, Tropicana to Charleston: 005-0, 006-0 | Done |  | 0 | 34 | 34 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | New Dates | Done |  | 0 | 57 | 57 | 0 |  | FALSE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3745 - Submittal #50 - 1W1C and 2W1C Signals | Done |  | 2 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3790 - Submittal #11 - Conduit, Pull boxes, service pedestals | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3788 - Group 11 - 623-2950 CCTV Lowering Device | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3788 - Group 04 - 623-1731 Transformers | Done |  | 0 | 34 | 34 | 0 |  | TRUE
10994 | Done | Potential | Material Submittal/RFI Reviews 2019 |  | Signals Lighting and ITS | C3788 - Group 17 R1 - 623-1270 Data Radio Communications Master | Done |  | 0 | 34 | 34 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | DOC Submittal (Final Iteration) | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 94 | 94 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Dates In PSAMS | Done |  | 0 | 57 | 57 | 0 |  | FALSE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Coordinate w/ TOTS for Splice Diagrams | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3795 - 191470 10-2 UF-B Cable | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Intermediate Structure List | Done | Jordan James <jjames@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 6 | Compile & Submit Set | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 6 | DOC Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS\Sprint 6 | Internal Review Revisions - Masking | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS | Resubmit DOC estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 32 | 0 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Pre-PDFS Scope & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 3 | Preliminary trunkline design to environmental | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3819 - EA 74107 - EA 60941 - US-395 North Valleys Ph1A (Parr Bridge) |  | Signals Lighting and ITS | DOC Submittal | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Address PS&E comments | Done | Jordan James <jjames@dot.nv.gov> | 4 | 46 | 46 | 0 |  | FALSE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS | C3724 - US 95 3C quantities for 72 Fiber - Needed for Change Order | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS\Sprint 2 | Complete internal review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 0 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS\Sprint 3 | RWIS Site Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 26 | 26 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | C3795 - 191470 Luminaire Type A | Done |  | 0 | 70 | 70 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Create an intercept vault detail | Done | Jordan James <jjames@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Compile & Submit #2 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 11 | Mission RRFB Advanced Warning | Removed |  | 2 | 36 | 34 | 2 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | C3795 - 191470 #24 - Underground Electrical Svc. | Done |  | 0 | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | C3855 - EA 74300 - 74085 - Design Build: I-15 Tropicana |  | Signals Lighting and ITS\Sprint 1 | Provide Feedback on CRA chart | Done | Jordan James <jjames@dot.nv.gov> | 1 | 29 | 27 | 2 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | Address QAQC Comments | Done | Jordan James <jjames@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Linework | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Labels | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Intermediate Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | Intermediate Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 3 | Compile Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Research | Done | Jordan James <jjames@dot.nv.gov> | 1 | 12 | 12 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 4 | PDFS Report | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 12 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS | Make changes based on Specs comments & resubmit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 29.5 | 29.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 2 | C3790 Material Submittal #7 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 70 | 70 | 0 |  | FALSE
10990 | On Hold | Potential | CANCELLED - CL SR 582 (Fremont) at Bruce St. and Eastern - New Signal Systems |  | Signals Lighting and ITS\Sprint 2 | Research | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 4 | 4 | 0 |  | FALSE
10990 | On Hold | Potential | CANCELLED - CL SR 582 (Fremont) at Bruce St. and Eastern - New Signal Systems |  | Signals Lighting and ITS\Sprint 2 | PDFS Visit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 4 | 4 | 0 |  | FALSE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS\Sprint 4 | Update Key Map | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Coordinate with Architecture for conduit runs feeding SP at Yard | Done |  |  | 16 | 0 | 16 | 2030-01-01 | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 3 | Research | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 6.5 | 6.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 3 | SUE Exhibit | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS\Sprint 4 | PS&E Review Meeting | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | C3772 - EA 73879 - Tropicana Ph 2A |  | Signals Lighting and ITS | Move Type 1A pole | Done | Jordan James <jjames@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
10994 | Done | Potential | C3772 - EA 73879 - Tropicana Ph 2A |  | Signals Lighting and ITS | Add conduit for future use | Done | Jordan James <jjames@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73879 - Tropicana Ph 2B - CL Portion (LVB to Maryland Pkwy) |  | Signals Lighting and ITS\Sprint 5 | Add Conduit runs across Tropicana | Done | Jordan James <jjames@dot.nv.gov> | 2 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | Miscellaneous Items 2019 |  | Signals Lighting and ITS | C3753 - City of LV Signal Punch-list Review | Done | Jordan James <jjames@dot.nv.gov> | 2 | 122 | 122 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS | Project Kickoff Meeting | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 24 | 24 | 0 |  | TRUE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 3 | Permit 211312 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
16329 | DOC'ed | Potential | EA 73937 - Jones Blvd |  | Signals Lighting and ITS | BRAT Review | Done | Jordan James <jjames@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Labels | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS\Sprint 3 | PDFS Site Visit | Done | Jordan James <jjames@dot.nv.gov> | 4 | 26 | 6 | 20 |  | TRUE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS | PDFS Report | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 6 | 20 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | ITS Schedules - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | Structure List | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | Lighting Plan - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | Lighting Schedules - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | Lighting Sheets - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 35 | 1 |  | FALSE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS | Schedule site visit for thorough review of all service pedestals within project limits | New |  |  | 26 | 6 | 20 |  | TRUE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS | Signal Plan - Intermediate | New |  | 2 | 26 | 6 | 20 |  | TRUE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS | Signal Sheets - Intermediate | New |  | 4 | 26 | 6 | 20 |  | TRUE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS | Signal Schedules - Intermediate | New |  | 4 | 26 | 6 | 20 |  | TRUE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS | Lighting Plan - Intermediate | New |  | 2 | 26 | 6 | 20 |  | TRUE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS | Lighting Sheets - Intermediate | New |  | 4 | 26 | 6 | 20 |  | TRUE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS | Lighting Schedules - Intermediate | New |  | 4 | 26 | 6 | 20 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS\Sprint 6 | Internal Review Revisions - Construction Notes/Schedule Edits | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS\Sprint 3 | Internal Review Revisions - Sheet Attribute Edits | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 32 | 32 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 3 | Service Pedestal Request Email | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 14 | Internal ITS Review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> | 0 | 40 | 40 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 3 | PDFS Report | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 7 | Schedule TC Meeting | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
10990 | On Hold | Potential | CANCELLED - CL SR 582 (Fremont) at Bruce St. and Eastern - New Signal Systems |  | Signals Lighting and ITS\Sprint 3 | Populate Features, PBIs, and add description to Epic | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 4 | 4 | 0 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Enter scope & dates | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 3 | Enter scope to TFS | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 4 | Intermediate Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 4 | Intermediate Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 6 | Intermediate Submittal | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 4 | Email R/W Util. for UPRR | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 4 | Bridge Conduit Detail | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 9 | Signal Plan - Intermediate | Done | Jordan James <jjames@dot.nv.gov> | 8 | 46 | 46 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 9 | Signal Sheets - Intermediate | Done | Jordan James <jjames@dot.nv.gov> | 4 | 46 | 46 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | Signal Schedules - Intermediate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 46 | 46 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | Compile & submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS | Service Pedestal Request | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | Update Tortoise Fence Details | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 6 | Linework | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 6 | Labels | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 6 | Linework | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 6 | Labels | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 5 | Service Pedestal Request | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Coversheet | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 6 | Key Maps | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | General Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Construction Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Construction Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Compile & Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS\Sprint 4 | Address PS&E Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 8 | Cut Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 8 | Label/Schedules/Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 8 | Cover/Notes Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 8 | Submit Estimate for Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 8 | Compile & Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 5 | Priority 1-4 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Signal Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS\Sprint 6 | Special Details Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS\Sprint 5 | PS&E Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 32 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Signal Schedules - Doc - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 69.5 | 69.5 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74072 - Consultant Design - Nellis Blvd 3R and ADA |  | Signals Lighting and ITS | Review Clark County Requests | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\Sprint 4 | Review Pothole data and Questions | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 4 | RFI-009 - 3772 Tropicana Phase 2A | Done | Jordan James <jjames@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Priority 1A &1B | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Priority 1 | Done | William Renter <wrenter@dot.nv.gov> | 4 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Priority 2 | Done | William Renter <wrenter@dot.nv.gov> | 4 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Priority 3 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Priority 4 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Priority 5 | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Priority 6 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Priority 7 | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Priority 8-9 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 71 | 71 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | SBX Doc Control Documentation | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Contract 3947 Submittal 128-623 Conduit Bridge Mounting Detail, Bid Items 623 1825 and 623 1835 for approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Contract 3947 Submittal 064r1-623 Underground Electrical Service r1, Bid Item 623 1620 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | RE: Contract 3939 Submittal #39- Electrical #10 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | 3973 Submittal 42 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Contract 3973 Submittal 47, 48, 50 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | FW: Luminaires Submittal | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | RE: 3973 submittal 31 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Spec writeup for PVC-coated RMC | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 69.5 | 69.5 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Post-DOC | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Change Order #4 - Plan Update | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 6 | 29 | 29 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | 3973 Submittal 54 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | SP Justification Letter | Done | William Renter <wrenter@dot.nv.gov> | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | ITS Design - Cut sheets | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Voltage Drop | New |  | 0.5 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Resubmit Intermediate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Signal Design Updates | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 20 | 20 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Augmented Staff Setup | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 8 | 146 | 133 | 13 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Lead Designer Response to PS&E IR comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | FW: NDOT 3981 - Par Submittal | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | FW: Luminaires Submittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Contract 3948 Submittal 059r1-623 Luminaires r1, Bid Items 623 0267 and 623 0268 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | FW: NDOT 3981 - Par/Summit Line Submittals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Priority 2 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Priority 3 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Priority 4 | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Priority 5 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Priority 6 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Priority 7 | Done | Connie Ullas <cullas@dot.nv.gov> | 4 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Priority 1 & 4 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Priority 2 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Priority 3 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Priority 5 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | 3940 - Submittals 141,142 & 143 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Bid Items and Quantities. | Done | William Renter <wrenter@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Internal Review | Done | Connie Ullas <cullas@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Accept/ Reject Internal Review Comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Address Shared Review Comments | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Address Internal Review Comments from QA/QC | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Doc Structure List | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Plot and Submit to Roadway | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | DOC Estimate | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Clearing and Grubbing/ Seeding | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | QA/QC Compile and Submit | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | QA/QC Estimate& Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Internal Review | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Accept/Reject Internal Reviews Comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Confirm QC comments on 90% shared Review | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Sign Replacement Sheet | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Contract 3951 - Submittal #77 Underground Electrical Service | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Contract 3988: Items 623.1 Submittal Group | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Contract 3947 Submittal 064r2-623 Underground Electrical Service r2, Bid Item 623 1620 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | SP Request | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 57 | 57 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | FW: NDOT 3988 Submittal 46.1 - Luminaires, Type B - Titan | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | FW: NDOT 3988 Submittal 44.1 - ITS Vault - Titan | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Calle De La Plata PBI 1 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
51820 | EA 74477 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Design Draft for SP Request | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 28 | 0.5 | 27.5 | 2024-06-02 | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Contract 3948 Submittal 059r2-623 Luminaires r2, Bid Items 623 0267 and 623 0268 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Post-DOC | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Change Order #4 - Coordination | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 29 | 29 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | 3949 623.0213 LUMINAIRE TYPE B | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | IMD #5 Internal Review | Done | William Renter <wrenter@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Lighting Linework/Labels/Construction Notes | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Lighting General Notes | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Lighting cover sheet and key map | Done | William Renter <wrenter@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Lighting Schedules & Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Linework - Signals Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 60 | 9 | 51 |  | FALSE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Pull Box Theft Mitigation | New |  |  | 57 | 33 | 24 | 2025-03-01 | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2023 Professional Training |  | Signals Lighting and ITS | Professional Training for 3 of Hours | Done | Fernando Torres <ftorres@dot.nv.gov> |  | 6 | 6 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Field visit | Done |  | 2 | 5 | 5 | 0 |  | TRUE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | IMD Shared Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 17 | 17 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Contract 3951 Submittal #79 & #80 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Missing Loop detectors | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Signal Schedule file migration/replacement | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Internal Review - Signal QA/QC - 74249 #2 | New |  | 0 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Internal Review - ITS QA/QC - 74249 - #2 | New |  | 0 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Internal Review - Lighting QA/QC - 74249 - #2 | New |  | 0 | 69 | 69 | 0 |  | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | QAQC Plan-set Clean-up | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Accept/Reject IR Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 57 | 57 | 0 |  | FALSE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Build Features & PBIs | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Develop Scope & PDFS Report | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Service Pedestals | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Review As-Built Plans | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Design Framework | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Lighting Design - Linework | New | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Lighting Design - Coversheet/Key Map | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Lighting Design - Cut Sheets | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Lighting Design - General Notes | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Framework | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | SP Justification Letter | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | SP Requests $ | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Design - Linework | New |  | 2 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | ITS Design - Cut sheets | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | ITS Design - Coversheet/Key Map | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | ITS Design - General Notes | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Update Structure List and Estimate | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Lighting Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Lighting General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | ITS General Notes | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | ITS Cover/Key Map | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New |  |  | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 24 | 0 | 24 | 2025-07-21 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-09-29 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-09-29 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Create new BB Session for Internal Review | Done | William Renter <wrenter@dot.nv.gov> | 2 | 42.5 | 38 | 4.5 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Create DRAFT procedural document to follow for Change order preparation | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Clearing and Grubbing/Seeding $ | Done | William Renter <wrenter@dot.nv.gov> | 0.5 | 16.5 | 4.5 | 12 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2024 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | SLI Review of 2022 Standard Plans | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 6 | 18 | 18 | 0 |  | FALSE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 5 | Priority 5-6 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 5 | Priority 8-9 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 4 | Priority 1-3 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 5 | Priority 11, 12, 14 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 5 | Priority 13, 15 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 5 | Priority 4-6 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 5 | Priority 1-4 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 5 | Priority 7-8 | Done | Jordan James <jjames@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 4 | Priority 5-8 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 4 | PDFS Report | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 6.5 | 6.5 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Internal Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 Linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 Labels | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Linework | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Labels | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Construction Notes | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Construction Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Coversheet | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Coversheet | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Special Details | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 4 | Keymap | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Compile Plan set | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | General Notes | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 9 | General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 5 | Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | C3800 - Submittals #4, 5, 6, and 7 | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 3 | C3788 - Material Submittal - Groups 3, 14, 16 Resubmittals | Done |  | 0 | 70 | 70 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | Program Project | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 28 | 28 | 0 |  | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 6 | Service Pedestal Request | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 6.5 | 6.5 | 0 |  | FALSE
10994 | Done | Potential | C3855 - EA 74300 - 74085 - Design Build: I-15 Tropicana |  | Signals Lighting and ITS\Sprint 7 | Review/Ammend Technical Provisions | Done | Jordan James <jjames@dot.nv.gov> | 8 | 29 | 27 | 2 |  | TRUE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 8 | LPA 60946 Swenson ITS QA/QC Review | Done | Frederick Tydeman <FTydeman@dot.nv.gov> |  | 13 | 13 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | Update Labels & Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | Resubmit Intermediate Set | Done |  | 0 | 31 | 31 | 0 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Coordination items | New |  | 4 | 16 | 0 | 16 | 2030-01-01 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | create Service Pedestal upgrade/RFI document | Done | Jordan James <jjames@dot.nv.gov> | 1 | 12 | 12 | 0 |  | TRUE
10994 | Done | Potential | EA 74136 - SR-147 (Lake Mead Blvd) fm. Nellis east of Hollywood |  | Signals Lighting and ITS | Send pole information to structures | On-Hold |  |  | 26 | 6 | 20 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3762 - Meadowood Mall Way underdeck lighting | Done |  |  | 70 | 70 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 6 | Build Ipd Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | Modify Design for K2-6 & K2-7 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | Complete Traffic Control Design & Est. | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
10990 | On Hold | Potential | EA 73650 - Ely Main Street Reconstruction Project |  | Signals Lighting and ITS\Sprint 5 | Estmate section 13th to Ogden | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
10990 | On Hold | Potential | EA 73650 - Ely Main Street Reconstruction Project |  | Signals Lighting and ITS\Sprint 8 | Estimate RRFBs - Each | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
10990 | On Hold | Potential | EA 73650 - Ely Main Street Reconstruction Project |  | Signals Lighting and ITS\Sprint 8 | 4A/4B Fiber from 10th to yard. | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | Create Supplemental #1 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 46 | 46 | 0 |  | FALSE
10994 | Done | Potential | C3855 - EA 74300 - 74085 - Design Build: I-15 Tropicana |  | Signals Lighting and ITS\Sprint 7 | Second Review of Technical Provisions | Done | Laura Vargo <lvargo@dot.nv.gov> | 8 | 29 | 27 | 2 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\Sprint 11 | PDFS Field Visit | Removed | Laura Vargo <lvargo@dot.nv.gov> | 2 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\Sprint 6 | PDFS Scoping | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | C3805 - Submittal No. 001 & 012 | Done | Laura Vargo <lvargo@dot.nv.gov> |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 5 | C3805 - Submittal No. 002 | Done | Laura Vargo <lvargo@dot.nv.gov> |  | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 6 | Make changes based on PS&E | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 6 | Research on Monitoring Device/DataLogger | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3804 - Submittals S3 & S15 | Done | Eric Macgill <emacgill@dot.nv.gov> |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3691 - Submittal #20 | Done | Eric Macgill <emacgill@dot.nv.gov> |  | 70 | 70 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS\Sprint 6 | Address Spec Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS\Sprint 6 | Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\Sprint 10 | Respond to Questions from PS&E Review | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 6 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | River Ranch Rd linework | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | Nevada Pacfic Pkwy linework | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | River Ranch Rd labels | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | Nevada Pacific Pkwy labels | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 8 | Signal Schedules | Done | Jordan James <jjames@dot.nv.gov> | 4 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 8 | Construction Notes | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | Linework | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | Labels | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | ITS Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 8 | Special Details | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS | Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS | Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 8 | Submittal | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 6 | Update Ipd Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 6 | Modify Design Site K2-3 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 6 | Permit 211312 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 7 | Review NV Energy Service Pedestal Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | LMNRA Request | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Address Internal Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 11 | Intermediate Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 13 | Intermediate Labels & Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 11 | Cover Sheet & create remaining sheet files | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 6 | Permit 211493 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 13 | 13 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Traffic Control Design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 10.5 | 10.5 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Address Spec Review Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | ITS Plan - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | ITS Plan - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 46 | 46 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 9 | Structure List - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | ITS Schedules - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 8 | ITS Sheets - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 35 | 1 |  | FALSE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 9 | Lighting linework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 10 | Lighting labels | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 10 | Lighting schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 10 | Lighting construction notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 10 | Lighting special details | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 10 | Lighting general notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | ITS Sheets - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 46 | 46 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 7 | ITS linework | Removed | Jordan James <jjames@dot.nv.gov> | 2 | 45 | 36 | 9 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 9 | Lighting Plan - Intermediate | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 7 | ITS labels | Removed | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 9 | Lighting Sheets - Intermediate | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 7 | ITS schedules | Removed | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 9 | Lighting Schedules - Intermediate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Address Intermediate Review Comments ITS28-ITS52 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 7 | ITS construction notes | Removed | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 7 | ITS special details | Removed | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 7 | ITS general notes | Removed | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 10 | Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 10 | Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 8 | 74115 - Finalize Maintenance Yard Electrical Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 10 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 10 | Lighting cover/key map | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 7 | ITS cover/key map | Removed | Jordan James <jjames@dot.nv.gov> | 2 | 45 | 36 | 9 |  | TRUE
10994 | Done | Potential | Joint Trench Project in Elko (Spring Creek) |  | Signals Lighting and ITS\Sprint 7 | Address any revisions | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 5 | 5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 9 | SUE Potholing & Limits Exhibit | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 36 | 34 | 2 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 9 | Add trench detail | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 7 | Review Signal plans | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 7 | Address review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 7 | Review Lighting plans | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 9 | Address review comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 9 | Update Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 9 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 9 | Re-compile Plan set and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 7 | BRAT Report Quantity Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 46 | 46 | 0 |  | FALSE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 7 | Add Structure Mounted Detail | Done |  | 0 | 59 | 59 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 7 | C3812 - Pole Submittals | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 7 | C3812 - Luminaire Type A | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 7 | C3812 - Submittal #008-012 | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 7 | D3 ITS Cost Estimate | Done |  | 1 | 43 | 43 | 0 |  | TRUE
10990 | On Hold | Potential | EA 60949 I-15 Bridge B954 Deck Replacement |  | Signals Lighting and ITS\Sprint 8 | Lighting Cover/Key Map | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 9 | 9 | 0 |  | FALSE
10990 | On Hold | Potential | EA 60949 I-15 Bridge B954 Deck Replacement |  | Signals Lighting and ITS\Sprint 8 | Lighting Linework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 9 | 9 | 0 |  | FALSE
10990 | On Hold | Potential | EA 60949 I-15 Bridge B954 Deck Replacement |  | Signals Lighting and ITS\Sprint 8 | Linework Labels | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
10990 | On Hold | Potential | EA 60949 I-15 Bridge B954 Deck Replacement |  | Signals Lighting and ITS\Sprint 8 | Lighting Construction Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
10990 | On Hold | Potential | EA 60949 I-15 Bridge B954 Deck Replacement |  | Signals Lighting and ITS\Sprint 8 | Lighting General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3829 / EA 74038 - Fernley RRFBs |  | Signals Lighting and ITS\Sprint 7 | Revise PPB & resubmit plans | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 32 | 32 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS\Sprint 7 | Revise DOC set to show full PPB updates | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
10990 | On Hold | Potential | EA 73650 - Ely Main Street Reconstruction Project |  | Signals Lighting and ITS\Sprint 8 | 2A Estimate - 13th to Bell - ADA lighting only | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
10990 | On Hold | Potential | EA 73650 - Ely Main Street Reconstruction Project |  | Signals Lighting and ITS\Sprint 8 | 1B Estimate - 1st to 13th - all items | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
10990 | On Hold | Potential | EA 73650 - Ely Main Street Reconstruction Project |  | Signals Lighting and ITS\Sprint 8 | 1A Estimate - 13th to Bell - All items | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
10990 | On Hold | Potential | EA 73650 - Ely Main Street Reconstruction Project |  | Signals Lighting and ITS\Sprint 8 | 2B Estimate - 1st to 13th | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 8 | 74115 - Add TOTS equipment to ITS sheets | Done |  | 2 | 40 | 40 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 15 | 74192 - RWIS network connection design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3855 - EA 74300 - 74085 - Design Build: I-15 Tropicana |  | Signals Lighting and ITS\Sprint 8 | TPs Reviewer 1 - Section 19.1-3 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 29 | 27 | 2 |  | TRUE
10994 | Done | Potential | C3855 - EA 74300 - 74085 - Design Build: I-15 Tropicana |  | Signals Lighting and ITS\Sprint 8 | TPs Reviewer 2 - Section 19.1-3 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 29 | 27 | 2 |  | TRUE
10994 | Done | Potential | C3855 - EA 74300 - 74085 - Design Build: I-15 Tropicana |  | Signals Lighting and ITS\Sprint 8 | TPs Reviewer 1 - Section 19.4-6 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 29 | 27 | 2 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | K2-1 updates | New |  | 2 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 8 | Permit 211771 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 8 | Permit 211762 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0 | 13 | 13 | 0 |  | FALSE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | Linework | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 7 | Labels | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 8 | Lighting Schedules | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 8 | Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | C3855 - EA 74300 - 74085 - Design Build: I-15 Tropicana |  | Signals Lighting and ITS\Sprint 8 | TPs Reviewer 2 - Section 19.4-6 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 29 | 27 | 2 |  | TRUE
10994 | Done | Potential | Joint Trench Project in Elko (Spring Creek) |  | Signals Lighting and ITS\Sprint 10 | Add SW Gas alignment | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 5 | 5 | 0 |  | TRUE
10990 | On Hold | Potential | SLI Improvements (make project level) |  | Signals Lighting and ITS | Pedestrian Push Button Symbol Review | Approved |  |  | 3 | 0 | 3 |  | FALSE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 Const. Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 Lighting Special Details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 Lighting General Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 ITS Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 ITS Linework | Done | Jordan James <jjames@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 ITS Labels | Done | Jordan James <jjames@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 ITS Const. Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 ITS Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 ITS Special Details | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 ITS General Notes | Done | Jordan James <jjames@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS | PS&E2 enter comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | SP Request for K2-1 | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS\Sprint 9 | Address PS&E Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS\Sprint 9 | Compile and Submit DOC | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 9 | PDFS Report | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 1 | 1 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS labels | Approved |  | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS schedules | Approved |  | 6 | 121 | 25 | 96 | 2022-04-25 | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\Sprint 9 | Intersection Lighting Evaluation | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\Sprint 12 | Complete PDFS Report | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 42 | 39 | 3 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | Complete ITS linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 23 | 23 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | ITS Construction notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 23 | 23 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General notes | Approved |  | 1 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 12 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS | EA 74115 - Cover | Done |  | 2 | 40 | 40 | 0 |  | TRUE
10990 | On Hold | Potential | EA 60949 I-15 Bridge B954 Deck Replacement |  | Signals Lighting and ITS\Sprint 9 | Lighting Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 9 | 9 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 11 | Utility Conflict Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 74 | 74 | 0 |  | TRUE
10994 | Done | Potential | Joint Trench Project in Elko (Spring Creek) |  | Signals Lighting and ITS\Sprint 10 | Extend limits - 2300' past Elko Vista Dr. | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 5 | 5 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | 74153 Intermediate Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 10 | Address comments from Specs | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | C3855 - EA 74300 - 74085 - Design Build: I-15 Tropicana |  | Signals Lighting and ITS\Sprint 13 | Address TOTs comments | Done |  | 2 | 29 | 27 | 2 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\Sprint 10 | Final review of Special Provisions and Estimate | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Preliminary Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Build Features & PBIs | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 5.5 | 1 | 4.5 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Address ITS IR comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Address LTG IR Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 2 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Address SIG IR Comments | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Respond to QC Comments on PS&E Shared Review (need A/C review) | New |  | 2 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 20 | 0 | 20 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | ITS Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | ITS General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | ITS Linework/Labels/Construction Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | ITS Schedules & Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | ITS Special Details | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Lighting Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Lighting General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Lighting Linework/Labels/Construction Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Lighting Schedule & Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Lighting Voltage Drop | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Intermediate Coordination Efforts | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Confirm QC Comments on Intermediate Internal Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Provide Comments Intermediate Internal Review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Signal Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Signals General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Signals Linework/Labels/Construction Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Signals Schedule & Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Clearing and Grubbing/Seeding | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Intermediate Compile and Submit | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Intermediate Estimate | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Intermediate Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 2 | 8 | 0 | 8 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 8 | 0 | 8 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 2 | 8 | 0 | 8 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 8 | 0 | 8 | 2027-12-01 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 25 | SP Justification Letter | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Build Features & PBIs | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Design Framework | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Develop Scope & PDFS Report | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Request Service Pedestals | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Find and Review As-Built Plans | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 33 | 33 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | ITS Address Review Internal Comments | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Lighting Address Internal Review Comments | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Signal Address Internal Review Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 4 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Respond to QC Comments on PS&E Shared Review (need A/C review) | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Respond to QC Comments on QA/QC Internal Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Provide Comments QA/QC Internal Review | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Address ITS IR comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Address LTG IR Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Address PS&E Shared Review Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | DOC Compile and Submit | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | ITS Devices Added to Spreadsheet | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 6 | 6 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Review DOC Special Provisions | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 6 | 6 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | ITS Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | ITS General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | ITS Linework/Labels/Construction Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | ITS Schedules & Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Lighting Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Lighting General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Lighting Linework/Labels/Construction Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Lighting Schedule & Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Lighting Voltage Drop | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Intermediate Coordination Efforts | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Confirm QC Comments on Intermediate Internal Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Confirm QC Comments on Intermediate Shared Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Provide Comments Intermediate Internal Review | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Provide Intermediate Shared Review Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Intermediate Compile and Submit | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Intermediate Estimate | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Intermediate Structure List | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  |  |  | 0 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  |  | 0 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  |  |  | 0 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  |  |  | 0 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  |  |  | 0 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Build Features & PBIs | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Design Framework | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 16.5 | 16.5 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | ITS Address Review Internal Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | ITS Address Review Shared Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Lighting Address Internal Review Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Lighting Address Shared Review Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | QA/QC Coordination Efforts | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Confirm QC Comments on PS&E Shared Review (need A/C review) | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Confirm QC Comments on QA/QC Internal Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Confirm Specs review comments - QAQC Submittal | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Provide Comments QA/QC Internal Review | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Provide PS&E Shared Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 6 | 6 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | QA/QC Compile and Submit (Review A/C) | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Review & Update Schedules | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | QA/QC Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | SP Justification Letter | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | SP Requests $ | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Scope Summary and Survey to D2 | New |  |  | 8 | 2 | 6 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Signal Design - Cut sheets | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Signal Design - General Notes | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Design - Linework | New | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Signal Design - Coversheet/Key Map | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New |  | 2 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Schedule & Structure List | New |  | 6 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Signals General Notes | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Signal Cover/Key Map | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 39.5 | 5 | 34.5 | 2024-12-13 | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Provide IMD#5 Shared Review Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 57 | 57 | 0 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Cut Sheets ITS design | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Cut Sheets Design Lighting | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | 3983 - Submittal 025 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | 3982 Submittal 38 & 39 For Your Review & Approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | 3982 Submittals 45 thru 49 for Your Review & Approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | 3982 Submittals 50, 51 and 52 for Your Review & Approval | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | Post-DOC | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Make updates/changes to signal sheets | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 13 | 13 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Address Internal Review Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Summarize Scope and submit to D2 for evaluation | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 8 | 2 | 6 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2024 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Submit request forms for changes and new sheets to Specifications | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 18 | 18 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | FW: NDOT 3981 - Par/Summit Line Submittals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Post-DOC | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Change Order #6 - Plan update and coordination | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 29 | 29 | 0 |  | FALSE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | Develop Standardized Construction Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 1 Cover Sheet | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 1 Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 2 Cover Sheet | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 3 Cover Sheet | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 2 Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 3 Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Field Visit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
10994 | Done | Potential | Joint Trench Project in Elko (Spring Creek) |  | Signals Lighting and ITS\Sprint 10 | Review, Remove "Preliminary" Stamp, & Recompile | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 5 | 5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Lighting study | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 11 | Service Request | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 1 Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 2 Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 3 Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 3 Location Table | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 3 Schedules | Removed | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 1 Location Table | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | District 1 Traffic Signal Remains, Eliminate Advanced Warning Sign TYPICAL | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | District 1 Modify Timing TYPICAL | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | District 1 Convert to Passive TYPICAL | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | District 1 Modify to Static TYPICAL | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | Modify TYPICALS for District 2 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | Modify TYPICALS for District 3 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Estimate | Done |  | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Finalize | Done |  | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Compile & submit | Done |  | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 10 | District 2 RFI | Removed |  | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | 2020 Scoping effort for 3R Projects |  | Signals Lighting and ITS\Sprint 10 | District 3 RFI | Removed |  | 1 | 12 | 10 | 2 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 10 | ASWS District 2 Location Table | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Address UPRR comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
10994 | Done | Potential | C3811 - EA 74207 - EA 74020 - Design-Build SBX |  | Signals Lighting and ITS\Sprint 11 | Submittal DU12S1 Review | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 8 | 8 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 11 | 74222 Address Spec comments from QAQC Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | ITS linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 12 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 12 | 12 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 12 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | Signals linework | Done | Jordan James <jjames@dot.nv.gov> | 1 | 12 | 12 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | Lighting linework | Done | Jordan James <jjames@dot.nv.gov> | 1 | 12 | 12 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 10 | Print PDF and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 12 | 12 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 11 | 74115 Maintenance Yard Connection - Notes & Detail | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 40 | 40 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | Service Pedestal Request | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | LMNRA Permit Coordination | Done |  | 0 | 57 | 57 | 0 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74153 Splice diagrams | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Splice Diagram Coordination | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 56 | 56 | 0 |  | TRUE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 11 | Permit 211966 | Done | Jordan James <jjames@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 11 | Permit 211909 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 13 | 13 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\Sprint 11 | Review Preliminary Set | Done | Jordan James <jjames@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | Complete Signals linework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 23 | 23 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | Complete Lighting linework | Done | Jordan James <jjames@dot.nv.gov> | 4 | 23 | 23 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Lighting Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Lighting Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Signal Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Signal Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | Update Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 23 | 23 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | Review & revise service pedestal requirements | Done | Jordan James <jjames@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - ITS Labels | Done | Jordan James <jjames@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | Update Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 23 | 23 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - ITS Schedules | Done | Jordan James <jjames@dot.nv.gov> | 2 | 36 | 34 | 2 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | Print PDF and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 23 | 23 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Intermediate Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Intermediate Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal labels | Approved |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Intermediate Submittal to Rdwy | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting labels | Approved |  | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal schedules | Approved |  | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting schedules | Approved |  | 6 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | Signal Construction notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 23 | 23 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | Lighting Construction notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 23 | 23 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General notes | Approved |  | 1 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General notes | Approved |  | 1 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | Signals Cover/Key Map | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 23 | 23 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | Approved |  | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update ITS Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 23 | 23 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | Structure List and Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 Lighting Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 13 | Structure List and Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 13 | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 11 | Permit 211771 resubmittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
10994 | Done | Potential | EA xxx - I-580/Virginia NB Offramp Signal |  | Signals Lighting and ITS\Sprint 13 | I-580 Create Preliminary Estimate | Done | Jordan James <jjames@dot.nv.gov> | 2 | 2 | 2 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3842 / EA 74135 - EA 60849 - EA 60918 - Schurz 3R |  | Signals Lighting and ITS | Follow up for items relating to communication cabinet, antenna, & coaxial cable. | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 12 | 74115 Address Specs QAQC comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 40 | 40 | 0 |  | TRUE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS | 60957 Northridge Drive Reconstruction 60% Design Review | Done |  | 2 | 13 | 13 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 13 | PS&E Review & Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 11 | Beatty Yard LEA form 721 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 11 | 74202 Email to District 3 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 21 | 74160 Provide comments for PS&E Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\Sprint 12 | 73518 Communication Cabinet Antenna Modifications | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\Sprint 12 | 73518 Ethernet Switch | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74072 - Consultant Design - Nellis Blvd 3R and ADA |  | Signals Lighting and ITS\Sprint 11 | Review Specs | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | PDFS Report | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 35 | 35 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 22 | 74160 Address PS&E Lighting Comments | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 22 | 74160 Submit DOC set | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 13 | Review Intermediate Submittal | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS\Sprint 12 | Remove sentinel signs - Change order #1 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 94 | 94 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS\Sprint 12 | Recompile & submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 94 | 94 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 13 | Address Spec Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\Sprint 19 | Request Service Pedestal | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 12 | Split District 2 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 12 | Complete revisions | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 12 | Update Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Master Cover Sheet & Master Construction Notes Sheet | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - ITS Cover Sheet | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 12 | 74108 - Lighting Cover Sheet | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Signal Cover Sheet | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | 74160 Internal Review of Lighting | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 15 | 74115 - Address Rick's comments from Internal Review | Done | Jordan James <jjames@dot.nv.gov> | 2 | 40 | 40 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | ITS Estimate from Oddie Ave to Slime Wash | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 15 | 15 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74072 - Consultant Design - Nellis Blvd 3R and ADA |  | Signals Lighting and ITS\Sprint 12 | Detailed Changes to Specs | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 13 | Permit 210927 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74316 Review project Scope RE: ROW Utility Coordination | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 41 | 4 | 37 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\Sprint 13 | 73518 Pre-Bid Meeting | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS | ASWS - Address comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 16 | ASWS - Update structure list & estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 ITS Construction Notes | Done | Jordan James <jjames@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | 74250 Lighting Cover sheet | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | 74250 Lighting Keymap | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | 74250 Lighting Linework | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | 74250 Lighting Labels | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Add Underdeck Lighting | Approved |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | 74250 Lighting Construction Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | 74250 Lighting Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | 74250 Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | 74250 Submit R/W Utility Request | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 13 | 74222 Address PS&E Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 13 | 74222 Update Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 8 | 8 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3838 - EA 74193 - EA 60890 - Pyramid Lake Paiute Tribe Ltg and RRFB Safety |  | Signals Lighting and ITS | Review BRAT report | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 1 | 0 | 1 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 14 | Address sheet comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 14 | Guardrail out of UPRR RoW, Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Lighting Labels | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | 74108 - Signal Labels | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | Update Trenching Detail | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | 74272 - Lighting Coversheet/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 18 | 74272 - ITS Coversheet/Key Map | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Linework | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Labels | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Cover/Keymap | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | 74261 - Signals - Directional drilling | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | 74261 - Lighting - Directional drilling | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | 74261 - ITS - Directional drilling | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 14 | 74115 Splice Diagrams | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 15 | 74115 - Address PS&E & TOTS comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 40 | 40 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 13 | Const./General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 13 | Special Details | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | Service pedestal requests | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 35 | 35 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | Cost Estimate for SLI | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 14 | Email to D3 for photos | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3845/EA 74222 - Rye Patch Interchange 3R |  | Signals Lighting and ITS\Sprint 13 | 74222 Compile & Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 8 | 8 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 15 | 60950 PS&E Review & Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 15 | 60950 PS&E Revisions | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 15 | 60950 Update Structure List & Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS\Sprint 14 | Permit 210926 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
10990 | On Hold | Potential | Permit/LPA Processing (make project level) |  | Signals Lighting and ITS | Permit 210927 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> |  | 13 | 13 | 0 |  | FALSE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 14 | Address Kevin's Comments - Seeding Areas | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 13 | 74250 Compile & Submit Intermediate Plans | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 67.5 | 67.5 | 0 |  | FALSE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Construction & General Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Intermediate Compile & Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | Address comments from Specs | Done | Jordan James <jjames@dot.nv.gov> | 1 | 23 | 23 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | 74261 - Signals - Address comments from Intermediate Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | 74261 - Lighting - Address comments from Intermediate Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | 74261 - ITS - Address comments from Intermediate Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | 74261 - Signals - Clean up design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | 74261 - Lighting - Clean up design | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
16329 | DOC'ed | Potential | C3822 / EA 60896 - I-580/Patriot L&A Project |  | Signals Lighting and ITS\Sprint 14 | Review BRAT Report | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | 74261 - ITS - Clean up design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | Add Special Details | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | Update Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 16 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\Sprint 16 | 73518 BRAT Review | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74280 - EA 60939 - I-11 Crumb Rubber Overlay from E Paradise Hill Dr to Henderson Spaghetti Bowl |  | Signals Lighting and ITS\Sprint 14 | BRAT Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 15 | Intermediate Shared Review | Done | Jordan James <jjames@dot.nv.gov> | 2 | 45 | 36 | 9 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | 74250 Address Intermediate Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 20 | US-50 FH Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS | US-50 FH General Scope | Done |  | 1 | 36.5 | 35.5 | 1 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | 30% Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | I-80 FH Framework $$ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 6 | 6 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | 30% Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | I-80 FH General Scope | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 20 | US-50 FH Conceptual design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | 30% Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | I-80 FH Conceptual Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | 74250 Complete Panel Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | 74250 Design items to address | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | ITS Plan - Intermediate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 22 | 21 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | ITS Schedules - Intermediate - 74204 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 22 | 21 | 1 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 15 | 74192 - Address Intermediate Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 14 | 74192 - Update Estimate | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 22 | 74192 - Review Cell Modem spec to confirm Firewall is included | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 15 | 74192 - Update Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 15 | PS&E Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 15 | 60950 Confirm 07/14/20 edits | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 18 | 18 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 16 | 74153 Move Svc. Ped. behind Ex. Util. pole | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 9 | 9 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 14 | 74115 - Comment on PS&E Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 40 | 40 | 0 |  | TRUE
10990 | On Hold | Potential | SLI Improvements (make project level) |  | Signals Lighting and ITS | Add Pedestrian push button symbol to the symbols sheet for the next standard plans | New |  | 1 | 3 | 0 | 3 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | Lighting Plan - Intermediate - 74204 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 22 | 21 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | Lighting Schedules - Intermediate - 74204 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 22 | 21 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | Structure List - 74204 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 22 | 21 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | Compile & Submit - 74204 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 22 | 21 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | Estimate - 74204 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 22 | 21 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | Framework - 74204 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 22 | 21 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | ITS Sheets - Intermediate - 74204 | Done | Jordan James <jjames@dot.nv.gov> | 1 | 22 | 21 | 1 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 16 | Contract Search for TTS | Done | Jordan James <jjames@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 15 | Lighting Sheets - Intermediate - 74204 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 22 | 21 | 1 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS\2024 Sprint 3 | Professional Training for 6 of Hours | Done | Fernando Torres <ftorres@dot.nv.gov> |  | 5.5 | 5.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Lighting design for US-395 D2 access near I-580 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Review Teams SLI Users Group Folder | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Intermediate Internal Review Comment Revisions | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 44 | 41 | 3 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Build Features & PBIs | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Review As-Built Plans | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Design Framework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | ITS Design - Linework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 19 | 19 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Address IMD Shared Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | 3982 Submittal #069 - Weigh-In-Motion System (6 Lane Configuration) for your Review & Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | 3982 Submittals 70, 71, 72 and 73 for Your Review and Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Accept/Reject Internal Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Accept/Reject Intermediate Internal Review Comment | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | 3982 Submittals 74, 75 and 76 for Your Review and Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | 3982 Submittals 077 and 078 for Your Review and Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | 3982 Submittals 79, 80, 83 & 84 for Your Review & Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | RE: NDOT 3992 Submittals | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | NDOT 3892: 013 ITS Vault Ground Rod & Clamp; Submittal Cover Sheet - NVDOT - Universal_623 0201_623 0201-005-0 (2) | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | 3983 - Submittal 039 Luminaires | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | FW: NDOT 3983 US395 North Valleys Submittal 037 ITS POLES | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Solar Power Supply SLI DG Section Review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Existing SLI Inventory and KMZ file | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 32 | 18 | 14 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | RE: Contract 3973 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | 3982 Submittals 86, 87 & 88 for Your Review & Approval | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Reduced Scope | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Schedules - Lighting Design | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 9 | 9 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Reduced Scope | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | General Notes - Lighting Design | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Reduced Scope | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Cut sheets - Lighting Design | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Reduced Scope | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Labels - Lighting Design | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Reduced Scope | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Lighting Coversheet/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Reduced Scope | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Linework - Lighting Design | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 9 | 9 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Reduced Scope | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Construction Notes - Lighting Design | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Review Specs | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Review Specs | New |  | 4 | 20 | 0 | 20 | 2027-12-01 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Include Solar design and detail sheets | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | ITS Design and Labels | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Signal Design - Labels | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  |  | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | ITS General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  |  | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | ITS Cover/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Signals Schedules | Done | Alesha Jackson <ajackson@dot.nv.gov> | 6 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Signals Special Details | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Signals General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Signal Cover/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Intermediate Coordination Efforts | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 4 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 6 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Field Review Items | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 71 | 71 | 0 |  | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New |  | 0.5 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject IR comments | New |  | 1 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  |  | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  |  | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  | 0.5 | 6 | 0 | 6 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 6 | 0 | 6 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 6 | 0 | 6 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 6 | 0 | 6 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 6 | 0 | 6 | 2026-05-10 | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Create MISC file writeup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments PS&E Internal Review | New |  | 6 | 26 | 0 | 26 | 2026-07-27 | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2024 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Update 2022 CAD with Draft Changes | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 18 | 18 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2024 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Create new fiber optic grounding detail drafts | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 18 | 18 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Details for 30' Posts & Type 7 mod pole | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Modify design based on field visit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Post-Final SR Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Generate 40:1 and 100:1 alignments | New |  | 1 | 32 | 18 | 14 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Preliminary Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Build Features & PBIs | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 5.5 | 1.5 | 4 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Identify Misaligned LED Luminaires | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 32 | 18 | 14 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | CCPW 215 Decatur to I-15 Phase 2 - Sign Luminaire Retrieval System Submittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Contract 3948 Submittal 172-623 Pedestrian Push Button, Bid Item 623 0770 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | FW: 3981 - Summit Line Submittal No. 9 & 10 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | GCW design: Update ITS Schedules | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Add ITS Splice Details$ | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Signal Design - Linework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2024 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Finalize New Details | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 18 | 18 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2024 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Finalize Existing Details | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 18 | 18 | 0 |  | FALSE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Priority 3 & 4 Additions | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 71 | 71 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Change Order Preparation Draft 2 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Address internal review comments for lighting | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 73 | 73 | 0 |  | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Internal Review Comments - Ltg+Signals | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | WWDS and Splice Details Updates | Done | Connie Ullas <cullas@dot.nv.gov> | 4 | 71 | 59 | 12 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Field Visit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | General Notes - Signal Design | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Linework - Signal Design | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Signals Coversheet/Key Map | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Cut sheets - Signal Design | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Schedules - Signal Design | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Labels & Construction Notes - Signal Design | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Schedules - Lighting Design | New |  | 4 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Cut sheets - Lighting Design | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Labels & Construction Notes - Lighting Design | New |  | 4 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Linework - Lighting Design | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | General Notes - Lighting Design | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Lighting Coversheet/Key Map | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS Coversheet/Key Map | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS Schedules | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Labels & Construction Notes - ITS Design | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS General Notes | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS Design - Cut sheets | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | ITS Design - Linework | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Preliminary Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Design Framework | New |  | 2 | 5.5 | 1.5 | 4 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Lighting Voltage Drop | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | ITS Voltage Drop | New |  | 0.5 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Update Structure List | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Create Estimate | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Compile and submit | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Clearing and Grubbing/Seeding - ITS and Lighting | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Preliminary Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | SP Research & Requests | New |  | 2 | 5.5 | 1.5 | 4 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | IMD Internal Review Accept/Reject Comments | New |  | 1 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | IMD Internal Review | New |  | 4 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Comment on IMD SR and Accept/Reject Comments | New |  | 2 | 48.5 | 0 | 48.5 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | IMD Internal Review Address Comments | New |  | 4 | 20 | 0 | 20 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Address IMD SR comments | New |  | 2 | 20 | 0 | 20 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Compile and submit | New |  | 2 | 20 | 0 | 20 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Update Estimate | New |  | 1 | 20 | 0 | 20 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Update Structure List | New |  | 2 | 20 | 0 | 20 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review Accept/Reject Comments | New |  | 1 | 20 | 0 | 20 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review | New |  | 4 | 20 | 0 | 20 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Comment on QAQC SR and Accept/Reject Comments | New |  | 2 | 20 | 0 | 20 |  | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review Address Comments | New |  | 4 | 11 | 0 | 11 | 2026-10-19 | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address QAQC SR comments | New |  | 2 | 11 | 0 | 11 | 2026-10-19 | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 2 | 11 | 0 | 11 | 2026-10-19 | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New |  | 2 | 11 | 0 | 11 | 2026-10-19 | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 11 | 0 | 11 | 2026-10-19 | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Details | New |  | 2 | 20 | 0 | 20 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Address internal review comments for ITS | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | update Splice Diagram | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Address internal review comments. | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 10 | 10 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | 3987 USA Pkwy ITS - Submittal 5.1 - Expansion-Deflection Joints | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | FW: NDOT 3978 Submittal #21 - Pull Boxes & Conduit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | FW: NDOT 3978 Submittal #22 - Type 7 Poles | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | FW: NDOT 3983 US395 North Valleys Submittal 061 Automatic Vehicle Classification System | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | 3954 Submittals 45R1 and 46R1 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | 3954 Submittal 153 Solar Pole Weigh in Motion | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | 3982 REVISED Submittal 73 for Your Review and Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | RE: 3982 Submittals 74, 75 and 76 for Your Review and Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Create LEA request for new pedestals | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 2 | 34 | 2024-09-23 | FALSE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Preliminary Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | SP Justification Letter | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 5.5 | 1.5 | 4 |  | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Internal Review Comments - Signals Schedules | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Signal Schedules - 2.0 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 60.5 | 50.5 | 10 | 2026-03-08 | TRUE
62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | Potential | Post-DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2026-10-19 | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Districts 2 & 3 Field Recommendations from Kevin & Laura Wise | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 26 | Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Make Changes from D1 Review Meeting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Preliminary Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 19 | Design Framework | New |  | 2 | 5.5 | 1 | 4.5 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Preliminary Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | SP Research & Requests | New |  | 2 | 5.5 | 1 | 4.5 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Preliminary Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | SP Justification Letter | New |  | 0.5 | 5.5 | 1 | 4.5 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Labels & Construction Notes - Lighting Design | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Cut sheets - Lighting Design | New |  | 0.5 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Schedules - Lighting Design | New |  | 2 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Lighting Coversheet/Key Map | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | General Notes - Lighting Design | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Linework - Lighting Design | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Lighting Voltage Drop | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | ITS Design - Linework | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS Schedules | New |  | 2 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS Design - Cut sheets | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | ITS Voltage Drop | New |  | 0.5 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | ITS General Notes | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Labels & Construction Notes - ITS Design | New |  | 2 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS Coversheet/Key Map | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Compile and submit | New |  | 2 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Create Estimate | New |  | 2 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Clearing and Grubbing/Seeding - ITS and Lighting | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Update Structure List | New |  | 2 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | IMD Internal Review | New |  | 2 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | IMD Internal Review Accept/Reject Comments | New |  | 1 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Comment on IMD SR and Accept/Reject Comments | New |  | 2 | 28 | 0 | 28 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Details | New |  | 2 | 18 | 0 | 18 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | IMD Internal Review Address Comments | New |  | 2 | 18 | 0 | 18 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Address IMD SR comments | New |  | 2 | 18 | 0 | 18 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Compile and submit | New |  | 2 | 18 | 0 | 18 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Update Estimate | New |  | 1 | 18 | 0 | 18 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Update Structure List | New |  | 2 | 18 | 0 | 18 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review | New |  | 4 | 18 | 0 | 18 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review Accept/Reject Comments | New |  | 1 | 18 | 0 | 18 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Comment on QAQC SR and Accept/Reject Comments | New |  | 2 | 18 | 0 | 18 |  | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Doc Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address QAQC SR comments | New |  | 2 | 9 | 0 | 9 | 2026-07-21 | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Doc Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review Address Comments | New |  | 2 | 9 | 0 | 9 | 2026-07-21 | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Doc Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 9 | 0 | 9 | 2026-07-21 | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Doc Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 2 | 9 | 0 | 9 | 2026-07-21 | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Doc Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New |  | 2 | 9 | 0 | 9 | 2026-07-21 | TRUE
62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | Potential | Post Doc Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2026-07-21 | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Make Changes from D2 Review Meeting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Make Changes from D3 Review Meeting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | SLI CADD Standard needs | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Add plan sheets LT16 & LT17 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Upload Pictures to AMP | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 33 | 33 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | 3949 Submittal LVP SAND BLUE DIAMOND PIT for conduit trench backfill | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | RE: Contract 3948 Submittal 172-623 Pedestrian Push Button, Bid Item 623 0770 for approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | 3982 Submittal #117 - 6231850 4-Inch Multiduct HDPE Complete for Your Review & Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | RE: 3987 USA Pkwy ITS - Submittal 5.1 - Expansion-Deflection Joints | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | 74316 Incorporate information from C3673 | New |  | 2 | 41 | 4 | 37 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | 74108 - Confirm Waterloo SP Panel | New |  | 2 | 29.5 | 0 | 29.5 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 15 | 74192 - Submittal to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 21 | 74192 - PS&E Review & Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 18 | 74192 - Address SPECS comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 15 | 74115 - Calculate and add Clearing & Seeding to plans | Done | Jordan James <jjames@dot.nv.gov> | 1 | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 15 | 74115 - Schedules Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 15 | 74115 - Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 40 | 40 | 0 |  | TRUE
16329 | DOC'ed | Potential | C 3849 - EA 74115 - I-80 at Emigrant Pass - Add Truck Climbing Lane |  | Signals Lighting and ITS\Sprint 15 | 74115 Remove T06-T08 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 40 | 40 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | How to Clearing & Grubbing / Seeding for Trenching | Approved |  | 1 | 146 | 133 | 13 |  | FALSE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 16 | 73976 Layered Cover Sheet, Title sheets, location schetches | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 29.5 | 29.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3792 Submittal No. 243 Pull Boxes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | RRFB Linework & Labels | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | RRFB Construction & General Notes | Done | Jordan James <jjames@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | RRFB Schedules & Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | RRFB Intermediate Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 26 | 26 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Compile and Submit Intermediate Design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 16 | 74153 Potholing Exhibit | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
10994 | Done | Potential | C3848 - EA 74202 - I-80 Osino interchange to Grays Creek 3R project |  | Signals Lighting and ITS\Sprint 16 | Address PS&E Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 20 | *Address Spec Comments for Intermediate | Removed | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 22 | 21 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | Intermediate Review - Specs, Comments, & responses | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 22 | 21 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | Complete Schedule population | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | Address comments from Intermediate review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | Address comments from Intermediate review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | Structure List - 74204 | Removed | Victoria Jeffery <vjeffery@dot.nv.gov> |  | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | QA/QC Estimate - 74204 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | Compile & Submit - 74204 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | ITS cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | Lighting cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 16 | Update Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 16 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 16 | Address Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 16 | Check Schedules and Structure List | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 16 | Check General Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Intermediate Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 1 | 23 | 23 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | Clean Up Signal Sheets | Done |  | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 9 | Re-compile Plan set and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | Check Estimate | Done |  | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | Check Structure List Quantities | Done |  | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | Clean Up Lighting Sheets | Done |  | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | Make sure trench detail is current | Done |  | 0 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | Check Lighting General Notes | Done |  | 1 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | Check Signal General Notes | Done |  | 1 | 49 | 49 | 0 |  | TRUE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | 30% Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\Sprint 16 | 30% ITS Linework & Labels | Done | Jordan James <jjames@dot.nv.gov> | 2 | 6 | 6 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | 30% Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\Sprint 16 | 30% Framework | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | 30% Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\Sprint 16 | 30% Structure List | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | 30% Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\Sprint 16 | 30% Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | 30% Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\Sprint 16 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 16 | Intermediate Review and Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0 | 46 | 46 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 16 | Field Visit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\Sprint 16 | 74243 PDFS Report | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | 74153 Update Estimate and Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | 74153 Address Intermediate Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 9 | 9 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 16 | Adjust DMS Location | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 16 | 60950 update schedules and add pole schedule | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 16 | 60950 DOC Design review and internal QAQC | Done | Jordan James <jjames@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS\Sprint 16 | 60950 Update Estimate and Submit DOC Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3829 - 029 - Titan Electric - Submittal Set 1 | Done |  |  | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS\Sprint 18 | 74160 Add seeding | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | 74153 Adjust trunkline design per SUE Mtg. Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 16 | 73976 Update plan set from field inspection | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3792 - Submittal 236R | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | EA 60950 - I-80 near Lockwood DMS |  | Signals Lighting and ITS | Verify email receipt from D2 for Cell Modem Consent | Done | Eric Macgill <emacgill@dot.nv.gov> |  | 18 | 18 | 0 |  | TRUE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS | Verify email receipt from D2 for Cell Modem Consent | Done | Jordan James <jjames@dot.nv.gov> |  | 21 | 21 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3824 - Conduit Submittal No. 41 | Done |  |  | 70 | 70 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | 74250 Address Specs Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74301 Lighting - Framework | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 18 | Framework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 19 | Linework & Labels | Done | Jordan James <jjames@dot.nv.gov> | 4 | 24 | 24 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | 74153 Calculate Clearing & Grubbing/Seeding | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Schedules | Done | Jordan James <jjames@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Address Intermediate comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | ITS detail sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Address Intermediate comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 18 | Address Specs Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Cover Sheet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | Special Details | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 19 | Const/General Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 19 | Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 19 | Structure List & Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 18 | Cover Sheet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 19 | Special Details | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 19 | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 24 | 24 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | 74153 Splice Diagram Request | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 9 | 9 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 17 | 74153 ITS Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3829 - 031 - Titan Electric - Submittal Set #4 | Done |  | 1 | 70 | 70 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 18 | 74250 Comment on Intermediate Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3799 - Submittal-006_Resubmittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3829 Submittal 034 Titan Electric | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3819 - 085 - Electrical Group 10 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3824 -Ely CMAR - Traffic Signal Submittal #52 | Done |  |  | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 18 | Adjust sheet numbering | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74153 Create LT02 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74153 Lighting Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | 74153 Plan set SHEET INDEX | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 74153 Update Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | 74153 Lighting Clean up | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74153 SP1 Panel Schedule | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74153 Create ITS01A | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74153 ITS Construction Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 18 | Populate existing utilities from provided as-builts. | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74153 ITS Sheet Cleanup | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74153 - ITS Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 74153 Update Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | 74153 - Special Details for RWIS sites | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | 74153 Solar Calculations | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 74153 Plot & submit DOC plans | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | ITS Network Communication Evalutation Request | Done | Jordan James <jjames@dot.nv.gov> | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 18 | Misc items 1 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 18 | Guardrail, cattleguard, & fence | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 18 | Adjust conduit runs & box placement | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 18 | Sheet indices, title sheets, & Location control | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Signals - Mast Arm signs | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Signals - Address comments from PS&E Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Signals - Panel Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74120 - EA 73797 - Consultant Design - I-515 Viaduct Rehab |  | Signals Lighting and ITS\Sprint 18 | 74120 Review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 1 | 1 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 18 | 74250 Pothole Exhibit | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 22 | 74192 - Service Pedestal Panel Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 22 | 74192 - Update Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 24 | 74192 - Plot plans & submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 22 | 74192 - Additional flashing beacons | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 59 | 59 | 0 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | PS&E Review - Plans, Comments, & Responses | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 20 | *Address Spec Comments for Intermediate | Removed | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 20 | Add items into PMP | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 146 | 133 | 13 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | 74153 Address PS&E Specs comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 17 | 9100 - Revisions to DOC set | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 17 | 9100 - PostDOC Review cleanup | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 605430-19 CC215 Windmill to Pecos Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3811 - 15.037 Submittal DU1 Utility Work Materials | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3824 - Ely CMAR - Traffic Signal Equipment & Components Submittals 53 to 56 | Done |  |  | 70 | 70 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | 74250 Convert Horse flashing signs to Solar | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | 74250 Additional lighting b/t Occidental & 6-Mile Canyon | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 67.5 | 67.5 | 0 |  | FALSE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | Sue/Utility Conflicts | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | Enter ALL PBIs for ALL projects that you are lead designer | Done | Jordan James <jjames@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74153 Complete Project Review | Done | Jordan James <jjames@dot.nv.gov> | 4 | 41 | 41 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Lighting - Address comments from PS&E Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | ITS - Add NVE connection point to plans | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | 74261 - ITS - Address comments from PS&E Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Check Final Structure List Quantities | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Update Final Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS | Address Specs Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Signals - New Signal Island | Done | Jordan James <jjames@dot.nv.gov> | 0 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Signals - Add note 13 to sheet T04 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Verify Network Connection Evaluation | New |  | 0 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Verify Network Analysis Info | New |  | 0 | 121 | 25 | 96 | 2022-04-25 | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Signals - Structures Coordination | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | 74320 Address Spec Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | QAQC Linework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | QAQC Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | QAQC Schedules | Done | Jordan James <jjames@dot.nv.gov> | 2 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | QAQC MISC File + Construction Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | QAQC General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 21 | 21 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3817 - Electrical Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 20 | PRR-CL-Sunset Rd and Boulder Hwy-Traffic signal conduits and ITS facilities (FAST) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | QAQC Special Details | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | QAQC Submittal | Done | Jordan James <jjames@dot.nv.gov> | 2 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | QAQC Plan Set Reviewer "A" | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | QAQC Plan Set Reviewer "B" | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | QAQC Quantity Check | Done | Jordan James <jjames@dot.nv.gov> | 1 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | QAQC Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | QAQC Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | DOC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | DOC Maintenance Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | DOC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | DOC Quantity Check | Done | Jordan James <jjames@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | DOC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | DOC Submittal | Done | Jordan James <jjames@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 20 | Address plan comments from project meeting on 2020-09-28 at 1300 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Find As-Builts | On-Hold | Jordan James <jjames@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Redesign southern interchange at I-80/McCarran | New |  | 1 | 121 | 25 | 96 | 2022-04-25 | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 23 | Address Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 20 | Provide PS&E Review Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 23 | Check Schedules and Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 23 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 23 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 22 | 74320 Panel Schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - New Linework - Trunkline | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - New Labels - Trunkline | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - Setup Framework | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Inter - New Schedules | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Inter - New Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - New General Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - Special Details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Inter - New Structure List | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Inter - Compile and Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New General Notes | Done | Jordan James <jjames@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - New Structure List | Done | Jordan James <jjames@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New Lighting Construction Notes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New Lighting Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - Lighting Special Detail(s) | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New Lighting Labels | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New Lighting Linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | Inter - Setup Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - New Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New ITS Labels | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - ITS Special Details | Done | Jordan James <jjames@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New ITS Linework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New ITS Schedules | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New ITS Construction Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | QA/QC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Address Review Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 11 | 11 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | QA/QC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Update EVOD Design | Done | Jordan James <jjames@dot.nv.gov> | 2 | 11 | 11 | 0 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 22 | 74108 Ornamental Lighting Removal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 48.5 | 48.5 | 0 |  | TRUE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | QA/QC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Check Schedules and Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 11 | 11 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | QA/QC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11 | 11 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | QA/QC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 11 | 11 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Update Structure List | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | QA/QC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Review special provisions | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 11 | 11 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 20 | Update SLI Trench Detail | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | 3949 Submittal No 121-1 623.0213 LUMINAIRE TYPE B | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | RE: 3982 REVISED Submittal 73R2 for Your Review and Approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | RE: 3982 REVISED Submittal 76R2 for Your Review and Approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | NDOT 3973 Submittals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | 3982 Submittals 119 through 125 for Your Review & Approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 128.5 | 128.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | 3982 - Submittal 134 for Your Review & Approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 128.5 | 128.5 | 0 |  | FALSE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Misc. | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Project buildout | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 1 | 1 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2023 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | RE: 3949 Submittal No 121-1 623.0213 LUMINAIRE TYPE B | Removed |  | 0 | 128.5 | 128.5 | 0 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Update internal Review comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New |  | 2 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals General Notes | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Schedule & Structure List | New |  | 6 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  |  | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SLI Intermediate Coordination Meeting (Group Designers Only) | New |  |  | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2024-10-21 | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New |  |  | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Update wiring block diagram | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Cave Rock Vault changes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | QA/QC Shared Review - Comment & Reply | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Address QA/QC Internal Review Comments - ITS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Build Features & PBIs | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 10 | 7 | 3 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Develop Scope | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 10 | 7 | 3 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Request Service Pedestals | Committed | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 10 | 7 | 3 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Review As-Built Plans | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 10 | 7 | 3 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Design Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 10 | 7 | 3 |  | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Build out AC power system, schedules, and notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Create Alignment file | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 34.5 | 32.5 | 2 |  | FALSE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Clean up Schedules #1 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Lighting construction Notes | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | Removed |  | 0 | 34.5 | 32.5 | 2 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | FW: NDOT 3987 Submittal #24 - Luminaires | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | FW: NDOT 3973 Submittals 43 & 46 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Update project frame and update reference file. | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | FW: Please see attached submittal 078 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | FW: NDOT 3983 US395 North Valleys Submittal 076 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | FW: NDOT 3983 US395 North Valleys Submittal 075 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Voltage Drop Calculation $ | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 16 | 15 | 1 | 2024-07-29 | TRUE
54531 | EA 74449 - US-50, Middlegate | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Request Service Pedestals | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 31 | 3 | 28 | 2024-08-01 | FALSE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SP Justification | Committed | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 40 | 0 | 40 |  | TRUE
64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | On-Hold | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SP Request | Committed | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 40 | 0 | 40 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Update ITS Design | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | update ITS schedules | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Update Estimate and structure list and review and update the ITS plan sheets | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 73 | 73 | 0 |  | TRUE
52656 | Staff Training | Potential | 2023 Professional Training |  | Signals Lighting and ITS | Professional Training for 12 of Hours | Done |  |  | 6 | 6 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (8) of Hours | Done |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2023 Professional Training |  | Signals Lighting and ITS\2023 Sprint 16 | Professional Training for 10 Hours | Done |  | 1 | 6 | 6 | 0 |  | TRUE
52656 | Staff Training | Potential | 2023 Professional Training |  | Signals Lighting and ITS\2023 Sprint 16 | Professional Training for 10 Hours | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) Hours | New | Fernando Torres <ftorres@dot.nv.gov> |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2023 Professional Training |  | Signals Lighting and ITS | Traffic Conference Training - 20 hours | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> |  | 6 | 6 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Internal review 2 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | create new Bluebeam session | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 73 | 73 | 0 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Update ITS Design - Non-fiber, Pull Box Theft | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | WWD Updates from TAPCO | Done | Connie Ullas <cullas@dot.nv.gov> | 4 | 71 | 59 | 12 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  |  | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 2 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 2 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Sheets | New |  | 2 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review IMD Specs | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | IMD Shared Review - Comments | New |  | 2 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lead respond to IMD internal review comments | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review ITS Sheets | New |  | 4 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 37.5 | 0 | 37.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 37.5 | 0 | 37.5 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | FW: NDOT 3983 US395 North Valleys Submittal | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | FW: NDOT 3983 US395 North Valleys Submittal 86 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | 3982 Submittal 175 and 179 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | FW: NDOT 3983 US395 North Valleys Submittal 090 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | 3982 Submittal 182 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | 3982 Submittal 183 and 184 For REVIEW & APPLROVAL | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Fwd: P557-23-016 - Submittal Set 1 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | 3982 Submittal 204 for Your REVIEW & APPROVAL | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 2 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cleanup | New |  | 2 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS Details | New |  | 2 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  |  | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New |  | 4 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Post-DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Post-DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 0.5 | 0 | 0.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New |  | 4 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review QAQC Specs | New |  | 1 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Sheets | New |  | 2 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QAQC Shared Review - Comments | New |  | 2 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lead respond to QAQC internal review comments | New |  | 1 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review ITS Sheets | New |  | 4 | 35.5 | 0 | 35.5 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Trunkline Design | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 37.5 | 0 | 37.5 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | 3977 Submittal 016 for Your REVIEW & APPROVAL | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Signal Schedules and Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | SLI Rev #2 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 27 | 27 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | SLI Rev 2 Project Review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 27 | 27 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | RE: NDOT 3983 US395 North Valleys Submittal 075 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | 3977 Submittal 017, 019, 020, and 021 for Your REVIEW & APPROVAL | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | 3982 REVISED Submittal 73R3 for Your Review & Approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | 3982 REVISED Submittal 76R3 for Your Review and Approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | GCW Design: Add Labels | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Planset Cleanup | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | 3977 Submittal 022, 024, 025, 026, and 028 for Your REVIEW & APPROVAL | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2023 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Update D1_P3 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 71 | 71 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | address comments for internal review 2 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 73 | 73 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Construction Notes & Sheet Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | 3977 Submittal 018 For Your REVIEW & APPROVAL | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | 3982 Revised Submittals 119R1 and 125R1 for Your Review & Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | FW: NDOT 3978 Submittal #27 - Signal Heads | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | RE: NDOT 3978 Submittal #21 - Pull Boxes & Conduit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | FW: P557-23-016 - Submittal Set 2 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Fw: 3892 Submittal 347 - ITS Vault Flat Steel Lift System | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | FW: NDOT 3983 US395 North Valleys Submittal 093 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | FW: NDOT 4501 Submittal 29 - Electrical Service.pdf | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | FW: NDOT 4501 Submittal 28 - Pull Boxes & Conduit.pdf | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | 3892 Submittal No. 353 - 80ft ITS Pole | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | 3892 Submittals No. 354-358 (Change Order #11) | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | 30% Coordination Efforts | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | LEA Review and Response | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Update labels | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 34.5 | 32.5 | 2 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Item 6090380 NDOT 4501 Submittal 32 - Solar Powered Warning Light.pdf | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | ITS Design Updates | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | Accept/Reject Internal Reviews Comments 2 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Update WWDS | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 73 | 73 | 0 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | QAQC Internal Review Address Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 20 | 20 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SLI Rev #2 additional work | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 27 | 27 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | SLI REV #3 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 27 | 27 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Calle De La Plata PBI 2 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 29 | 26 | 3 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | signal Linework | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Signal cover sheet and key map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | QA/QC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Design Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 11 | 11 | 0 |  | FALSE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Finish Lighting linework | New |  | 6 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Finish ITS linework | New |  | 6 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 75% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 3 | 3 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Print PDF and Submit | New |  | 1 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
10994 | Done | Potential | C3855 - EA 74300 - 74085 - Design Build: I-15 Tropicana |  | Signals Lighting and ITS | Address TP-19 Review Questions | New |  | 2 | 29 | 27 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | 74108 - Estimate & Structure List | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 48.5 | 48.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | 74108 - Compile & Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 48.5 | 48.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | 30% Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\Sprint 19 | Complete email to RoW for new SP near this location | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 6 | 6 | 0 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 20 | US-50 Research | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3837 - 005 - Flexguard | Done | Gurpreet Singh Rai <grai@dot.nv.gov> |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | C3837 - 007 | Done |  |  | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 24 | 74192 - Complete revisions of SP#3 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Respond to VE Recommendation | Done | Jordan James <jjames@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 20 | Contracts and As-built Drawing Search for multiple projects | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 20 | Compile & Submit DOC#2 Set | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 20 | DOC#2 Signal Adjustments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 20 | DOC#2 Lighting Adjustments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74281 - I-15 from CA/NV State line to Jean Interch. |  | Signals Lighting and ITS\Sprint 20 | Adjust lighting schedules for DOC #2 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 20 | Adjust Cover Sheet, Title Sheets & Location sketch | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 20 | Recompile & check | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 20 | Collaboration/assist for cover sheets | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 20 | Review Specifications submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 20 | PS&E Review Comments entered into shared review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | EA 74267 - EA 74030 - I-515 & Charleston Interchange |  | Signals Lighting and ITS\Sprint 20 | Create comments for 75% review meeting | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 11 | 3 | 8 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 - Special Details for Fiber Hut | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
10994 | Done | Potential | EA 74160 - I-80 Elko Interchange 3R |  | Signals Lighting and ITS | 74160 Internal Review of Signals | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 20 | 74192 - Move full RWIS DESIGN to W. side | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 22 | 74192 - Move full RWIS SCHEDULES to W. side | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 - ITS Block Diagrams | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 - Revise ITS10 DMS design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 22 | 74192 - Update ITS05A to reflect changes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 22 | 74192 - ITS Block Diagrams | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | Review Special Provisions | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 22 | 21 | 1 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | Download As-built files | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0 | 146 | 133 | 13 |  | FALSE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | Adjust Design for Sue Mitigation | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 21 | Create Underdeck Lighting Typical Section | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 24 | 24 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 23 | Adjust Service Pedestal Design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 45 | 36 | 9 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 74153 Specification Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | Review Specs | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | PDFS Report | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 2 | 2 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | Historical Document Research File Update | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 21 | Address PS&E Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 21 | Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 24 | 24 | 0 |  | TRUE
10994 | Done | Potential | EA 74287 I-515 Bridges Replacement (Eastern Ave and Desert Inn Rd) |  | Signals Lighting and ITS\Sprint 22 | Compile & Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 24 | 24 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | Enter Comments Intermediate Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 21 | 74192 - RWIS Pole & Pad shift | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 59 | 59 | 0 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 22 | Linework & Labels - US-50 fiber hut | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 22 | Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 22 | Structure List and Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 2 | US-50 FH Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 22 | Special Details | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 22 | Add base FH design | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 24 | Coordinate the pad design with Design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 22 | Coordinate with Hydraulics for design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 22 | Compile and Submit - QA/QC | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | QA/QC Estimate | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 17 | 14 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | QA/QC Structure List | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 17 | 14 | 3 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | DOC Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Schedules - Lighting & ITS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | PRR - Subpoena - Plumb lane Single Point Urban Interchange | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3831 Submittal #17 - Electrical #1 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3831 Submittal #18 - Electrical #2 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | P411-19-016 - Neon Campus | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT Contract 3822 Submittal #18 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3831 Submittal #18 - Electrical #2 | Done |  |  | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 21 | 74192 - RWIS Pad/SP Coordination & Design Update | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 21 | 74250 Review SP#2 DAA/721A | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 67.5 | 67.5 | 0 |  | FALSE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 22 | 74192 - Address comments from the PS&E review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 22 | 74108 - 2nd Intermediate Submittal to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 Design addition - "Road Closed Ahead" Flashing signs | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Inter - Service Pedestal Request | Done | Jordan James <jjames@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\Sprint 24 | Signals - Advanced Warning Detail | Done | Jordan James <jjames@dot.nv.gov> | 1 | 76 | 76 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | Address Intermediate Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 22 | Pothole locations | Done |  | 1 | 116.5 | 60.5 | 56 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 22 | Clearing & Grubbing/Seeding | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 7 | US-50 FH - Complete and Submit Tower FAA Application/Permit Request | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 36.5 | 35.5 | 1 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 22 | 74153 - Complete Concrete Pad design revisions & request pad details from Rdwy | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 25 | US-50 FH - General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 1 | US-50 FH - Construction Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 Comment on PS&E Review | Done | Jordan James <jjames@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\Sprint 26 | 74164 Lighting Linework & Labels | Done | Jordan James <jjames@dot.nv.gov> | 2 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\Sprint 26 | 74164 Cover/Key Map | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 1 | 74164 Lighting Schedules | Done | Jordan James <jjames@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 1 | 74164 Lighting Construction Notes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 1 | 74164 Lighting General Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 1 | Compile & Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 1 | 74164 Structure List & Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\Sprint 26 | 74164 Lighting Special Details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 23 | 74192 - Pad Raised Foundation Special Details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 25 | US50 FH Cover Sheet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 23 | Review Special Provisions | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | Provide Project Information to Atkins Team | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 17 | 17 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 74320 Compile and Submit QAQC | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 26 | 26 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 74320 Update Structure List & Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\Sprint 23 | 74192 - Pole 05A Special Detail | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
10994 | Done | Potential | C3772 - EA 73879 - Tropicana Ph 2A |  | Signals Lighting and ITS\Sprint 23 | Address Signal RFI | Done | Jordan James <jjames@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | Traffic Counts | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 17 | 17 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Update Structure List & Review Specifications | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | 74320 Update Panel Schedule | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 74153 - ITS Schedules | Done | Jordan James <jjames@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | ITS Concrete Pad details - additional revisions per KM | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 ITS Construction Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 ITS Sheet Cleanup | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | ITS Cabinet Foundation Special Detail | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | NDOT 3831 Submittal #21 - Electrical #3 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | Design File Review$ | Done | Jordan James <jjames@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | Project PBI Buildout$ | Done | Jordan James <jjames@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Service Pedestal Request | Done |  | 1 | 19 | 19 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3837 - 058 - No. 5 Pull Box | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3837 - 059 - Luminaire Type B | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3843 - 020 -623.003 CP ASL200 CLSM1, 3843 - 017 -623.001 Group 3 Submittals, 3843 - 019 -623.002 Sand Bedding | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3837 - Submittal 061 - 3-inch conduit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3837 - Submittal 062 - Luminaire Type C | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3837 - Submittal 063 - Luminaire Type A | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3843 - 024 -623.005 Special Pull Box Contract 3843 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3843 - 025 -623.006 ITS Vault, Ground Rod, Copper Wire, Cadwald Material, & Ball Markers | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3843 - 027 -623.008 4-inch SCH PVC Conduit, 3843 - 026 -623.007 1 1-2 inch SC PVC Conduit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3843 - 021 -623.004 2-inch Conduit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3837 - Submittal 060 - Loop Detector | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3843 - 029 -623.010 No. 5 Pull Box, 3843 - 028 -623.009 No. 5 Pull Box Modified | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3843 - 031 -623.012 No. 7 Pull Box Mod, 3843 - 030 -623.011 No. 7 Pull Box | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 - ITS References - Update to new ExUtl file | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 - Update the Clearing & Grubbing | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | 74153 Lighting Construction Note Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | 3799 Submittal 051 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | Existing Lighting Panel Schedule Research | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 24 | Cost Risk Assesment | Done |  | 2 | 116.5 | 60.5 | 56 |  | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 23 | Develop Bollard Detail | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 41 | 41 | 0 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\Sprint 25 | Provide/Address comments for shared review | Done | Jordan James <jjames@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 25 | Make changes based on PS&E #3 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 25 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 24 | Update Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\Sprint 25 | Clean up alignments for Eureka section | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 29.5 | 29.5 | 0 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Review prelim special provisions for project | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 1 | Address QAQC Comments to FH7-FH20, FH22-FH23, FH25-FH27 sheets | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 24 | Provide QAQC Comments | Done | Brenda.eliaszarate <Brenda.eliaszarate@hdrinc.com> | 0 | 36.5 | 35.5 | 1 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\Sprint 26 | PDFS Report | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 1 | 1 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3821 - Submittal 054-Group 6 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3821 - Submittal 055 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3821 - Submittal 057 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3821 - Submittal 058 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3821 - Submittal 064 | Done |  |  | 70 | 70 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Update estimate & plot/submit QAQC plans | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Q0-311-20-016 Mushroom Flasher Dual Circuit - Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Lighting Cover/Key Map | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Lighting Schedule & Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Lighting Construction Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Lighting General Notes | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Lighting Special Details | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Lighting Voltage Drop | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 25 | Cover sheet & Key Map | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 25 | Framework files $ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 25 | Construction Notes / General Notes / Trench Detail | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 25 | ITS Design & Sheets | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 25 | Bore Profiles | Removed |  | 0 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 25 | Plot & Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 16 | 16 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Structure List & Specification Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | District 1 - Pull Box design changes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Final cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 24 | Provide QAQC Comments | Done | Austin.hoekstra <Austin.hoekstra@atkinsglobal.com> | 0 | 36.5 | 35.5 | 1 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Address Intermediate Review Comments ITS01-ITS27 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\Sprint 25 | Compile & submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 31 | 31 | 0 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 25 | Add Generator and Propane tanks to Linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 1 | Update Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 2 | Update Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 26 | Review Special Provisions | Done | Jordan James <jjames@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 1 | Address QAQC Comments to ITS sheets | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\Sprint 24 | QAQC Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\2021 Sprint 14 | QAQC Plan Revisions | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 26 | Address design QAQC Comments (ORANGE) | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 26 | Plot & submit plans | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\Sprint 26 | Address QAQC Comments to FH1-FH6, FH21, FH24 sheets | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Intermediate Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Reply to project support Request | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 16 | 16 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3821 - Submittal 057R01 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3833 Electrical Submittals | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3824 - Ely CMAR - Electrical Submittals | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3831 Submittal #23 - Electrical #4 | Done |  |  | 70 | 70 | 0 |  | FALSE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Seeding/Clearing & Grubbing | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3821 - Submittal 064R01 - Group 16 REVISED | Done |  |  | 70 | 70 | 0 |  | FALSE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Update Callahan SP | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | 74320 Advanced Warning - Design Addition | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | 74320 Special Details | Done | Jordan James <jjames@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | District 1 - Heavy Lid Design Details | Done |  | 2 | 146 | 133 | 13 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3851 - Submittal #11 - DMS Sign and Cabinet | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3831 Submittal #24 - Electrical #5 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3843 - 060 - 623.015 623 0545 Steel Pole Type 1A Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 061 - 623.016 Steel Pole Type 1B Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 063 - 623.018 Steel Pole Type 14, 3843 - 062 - 623.017 Steel Pole Type 7 Submittals | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 064 - 623.019 Steel Pole Type 35B Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 065 - 623.020 Steel Pole Type 30A | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 066 - 623.021 Steel Pole Type 35 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 067 - 623.022 Steel Pole Type 35A Submittals. | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 068 - 623.023 Steel Pole 30-foot Submittals | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 069 - 623.024 Luminaire Arm 15 foot Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 070 - 623.025 10-ft Camera Extension Pole Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Emailing: 3843 - 072 - 623.027 Luminaire Type B, 3843 - 071 - 623.026 Luminaire Type A Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3851 - Submittal #8 - ITS Vault | Done |  |  | 70 | 70 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS | Submit Service Pedestal Request to NDOT Right of Way | Done | Jordan James <jjames@dot.nv.gov> | 1 | 21 | 21 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Lighting Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Lighting Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 6 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Lighting Linework | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Complete Lighting Linework and Labels | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Lighting Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Lighting General Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | ITS Linework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | ITS Construction Notes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Structure List$ | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | signal cut sheets | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | lighting linework | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | lighting cover sheet and key map | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | lighting cut sheets | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | ITS linework | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | ITS Cover sheet and key map | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | ITS cut sheets | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Compile & submit | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | DMS & Sentinel sign | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | NDOT Yard Fiber Hut connection | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Project Closeout | New |  | 1 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 24.5 | 0 | 24.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Analysis | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | SLI Intermediate Coordination Meeting (Group Designers Only) | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Schedule & Structure List | New |  | 6 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Post Doc Design |  | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Post Doc Design |  | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Post Doc Design |  | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Post Doc Design |  | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Post Doc Design |  | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Cut Sheets | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Framework | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Justification Letter | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Requests $ | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Compile and submit | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Update Structure List and Estimate | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Build Features & PBIs | New |  | 1 | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Design Framework | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Develop Scope & PDFS Report | New |  | 1 | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Request Service Pedestals - Copy | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Review As-Built Plans | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New |  |  | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 |  | TRUE
67161 | Project Template - Eric 5 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lead Designer Response to IMD IR comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review Comments & Responses | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Specs Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 5.5 | 0 | 5.5 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 5.5 | 0 | 5.5 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 5.5 | 0 | 5.5 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 5.5 | 0 | 5.5 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 5.5 | 0 | 5.5 | 2026-02-16 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Design - Coversheet/Key Map | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Lighting Design - Cut Sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Design - General Notes | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Lighting Design - Linework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | SP Justification Letter | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Compile and submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Update Structure List and Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Build Features & PBIs | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Design Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Develop Scope & PDFS Report | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Request Service Pedestal | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review As-Built Plans | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0 | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review Comments & Responses | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Internal Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | GCW Design: Fiber Design Linework | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | SLI Rev #4 (RFI 019) | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 27 | 27 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Update/Add ITS Cabinet Block Diagrams | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Update ITS WWD Special Details | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | 2nd PS&E Review - Shared Review - Comment & Respond | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | PS&E #2 Specifications/Specials Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Address shared Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Clearing and Grubbing | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | PS&E #2 IMD Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 8 | 69.5 | 69.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | 3954 Submittal No. 168 | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | FW: NDOT Contract #3905 - Submittal 0053R1 - Underpass Luminaire Type A - Resubmittal | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Submittal NDOT Contract #4502 - 623 submittals #036 thru #042 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | FW: NDOT 3961 - AVC Submittal Set | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Linework - Signals Design | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Construction Notes & Labels - Signal Design | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Schedules - Signal Design | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | General Notes - Signal Design | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 30 | 30 | 0 |  | FALSE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Revise Signal Sheet Cuts and Construction Notes | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 30 | 30 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Muller Signal Project Evaluation | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Submittal Exchange Submittal Submittal of SL JUNCTION BOX (A) | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 44 | 44 | 0 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Voltage drop $ | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 34.5 | 32.5 | 2 |  | FALSE
67161 | Project Template - Eric 5 | Potential | Doc Design |  | Signals Lighting and ITS | Plot & Submit to Roadway - Copy | New |  | 1 | 24.5 | 0 | 24.5 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | New Item - Submittal 00623-012-0 - NDOT 3983 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | QA/QC Share review comment. | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Field visit. | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Specs Review | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Submittal 00623-004-0 - NDOT 3983 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Submittal 00623-005-0 - NDOT 3983 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Submittal 00623-002-0 - NDOT 3983 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | update ITS key map and Review all ITS plans sheet. | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Intermediate Share Review comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 10 | 10 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Special Trench detail | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Bid item final review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Address share review comments. | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 10 | 10 | 0 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | IMD 2 Internal Review - Signals and Lighting | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | IMD 2 Internal Review Signals & Lighting Address Comments | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | SP Justification Letter | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 19 | 19 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | SP Requests $ | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 19 | 19 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Respond to & Address internal review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 69.5 | 69.5 | 0 |  | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | 30% Coordination Efforts Pt. 2 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 19 | 19 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Lighting Voltage Drop | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Lighting Cover/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Lighting Linework/Labels | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Lighting Schedule | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Lighting General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Provide Comments Intermediate Internal Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review and PS&E Shared Review - Comment Revisions | New |  | 4 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | FW: NDOT 4501 Submittal 34 - Luminaires.pdf | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | 3996 Group 3 Submittals (38, 39, 40) | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | FW: SUBMITTAL #41 - CONDUCTOR | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | FW: NDOT 4501 Submittal 29.1 - Electrical Service.pdf | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | P557-23-016 Submittal Set 3 - Solar Package & Pull Box Resubmittal | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | FW: SUBMITTAL #42 - SOLAR LIGHTS.pdf | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | FW: SUBMITTAL #43 - POLES | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Contract P613-23-016 Wright Way RRFBs - Submittal Set 2 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | 3977 Submittal S017R1 and S024R1 for your REVIEW & APPROVAL | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | 3977 Submittal S042 for your REVIEW & APPROVAL | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm PS&E Internal Review Comments | New |  | 0.5 | 26 | 0 | 26 | 2026-07-27 | FALSE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Removal of Lighting at Shafter Interchange | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 13 | 9 | 4 | 2024-05-08 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  |  | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  |  | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 26 | 0 | 26 | 2026-07-27 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LGT IR Comments | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Add Service pedestals to AMP | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 34.5 | 32.5 | 2 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 26 | ITS Schedules | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 26 | Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 26 | SR 430 Office Alignment | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 26 | Address Key Map Revisions from QAQC comments (PURPLE) | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 26 | Address Reference file QAQC comments (GREEN) | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | 9100 - US-395 from CA/NV Line to Stead Blvd & SR430 from N. Virginia St/Panther Valley Dr. to N. McCarran - ITS Joint Trench design |  | Signals Lighting and ITS\Sprint 26 | Address Sheet revisions from QAQC comments (BLUE) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 74150 - I-80, HU 3R Fm Pumpernickel Intchg to Valmy Intchg |  | Signals Lighting and ITS\Sprint 26 | Update NVE design and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 45 | 36 | 9 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS | 74164 Address RSA Report | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 42 | 39 | 3 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Submit Service Pedestal Request to Right of Way $$ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS | 74164 ITS Linework & Labels$ | On-Hold | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\Sprint 26 | 74164 Lighting Service Pedestal Requests$ | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Create special detail for high mast pull boxes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\2021 Sprint 14 | Additional work to address comments for Phased construction | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 45.5 | 44.5 | 1 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Signals Linework | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Signals Construction Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Construction Notes Sheet | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Complete Signals Linework and Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Complete ITS Linework and Labels | Done | Jordan James <jjames@dot.nv.gov> | 8 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Signals Schedules | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | ITS Schedules | Done | Jordan James <jjames@dot.nv.gov> | 6 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Signals General Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | ITS General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Coordinate with SSTC for sign structures | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Complete Structure List | Done | Jordan James <jjames@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Complete Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Signals Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | ITS Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Construction Notes and Trench Detail | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Coordinate with TOTs for ITS communication | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Update Estimate | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Update Structure List | Done | Brian Dodds <btdodds@dot.nv.gov> | 2 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Address internal review - Signals | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Address internal review - Lighting | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Address internal review - ITS | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 39.5 | 39.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Check Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 39.5 | 39.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 39.5 | 39.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | NDOT 3831 Submittal #24 - Electrical #5 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Service Pedestal Request $$ | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25 | 25 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | NDOT 3821 - Submittal 063 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | PDFS Report to Scoping | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New Linework - ITS Sites | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - Block Diagrams $$ | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 1 | Inter - New Labels - ITS Sites | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 2 | 9100 Service Pedestal Adjustments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 2 | 9100 FH07 Creation | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 36.5 | 35.5 | 1 |  | TRUE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS | 74243 Service Pedestal Request | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Incorportate NV Energy Plans into Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | NDOT Contract 3833 Submittal review Package 1 of 2 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Additional information request | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0 | 17 | 17 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | NDOT Contract 3833 Submittal review Package 2 of 2 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | 3792 Submittal No.'s 321-326 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | NDOT Contract 3833 Submittal review package 3 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Brat Report Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 15 | 7 | 8 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | NDOT 3831 Submittal #17 - Electrical Revised | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Create Price Comparison | Done | Jordan James <jjames@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Internal Bid Item/Quantity Review | Done | Jordan James <jjames@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Cover/Key Map $ | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 21 | 21 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | QA/QC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Cut Sheets | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 21 | 21 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - Location Control Sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Inter - Sheet Creation 1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Inter - Sheet Creation 2 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Inter - Sheet Creation 3 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - Sheet Creation 4 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | 30% ITS Design | Committed | Laura Vargo <lvargo@dot.nv.gov> | 2 | 8 | 2 | 6 |  | TRUE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Inter - Special Detail Sheet for RWIS Sites | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Submit Service Pedestal Request (ITS & Lighting) | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Framework Setup | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Revise Estimate with PS&E comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Revise Plan Sheet with PS&E comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | Network Connection Analysis Request | Done | Laura Vargo <lvargo@dot.nv.gov> | 0 | 17 | 17 | 0 |  | TRUE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | PDFS Report Review and Comment | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 20.5 | 20.5 | 0 |  | FALSE
16329 | DOC'ed | Potential | C3808 - EA 74235 - US-50/Sheckler |  | Signals Lighting and ITS\2021 Sprint 2 | Complete changes to the plan docs for change order | Done | Jordan James <jjames@dot.nv.gov> | 2 | 47 | 47 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | ITS Design, Labeling, & Construction Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 17 | 17 | 0 |  | TRUE
25500 | EA xxxxx - I-80 East Vista to USA Parkway Widening | On-Hold | 30% Design |  | Signals Lighting and ITS\2021 Sprint 2 | Submit high level estimate for scoping effort | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 2 | 2 | 0 |  | FALSE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | RWIS Pad Design/ ITS Special Details/ ITS General Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | ITS Schedules | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Sheet Layout, Cover sheet, & Cut ITS sheets | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 2 | NDOT Contract 3833 SLI review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Lighting Design, Labels, & Construction Notes | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Lighting Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Sheet Layout, Cover sheet, & Cut LIGHTING sheets | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Inter - Clearing and Grubbing | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Inter - Create Schedule Sheets | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 33833 Submittal Cover Sheet - NVDOT - Universal_00623N_00623N-035 (1).pdf | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | 3849 Submittals 013, 012 - Electrical Group 3 HDPE Conduit, Electrical ITS Vaults & Pull Boxes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 2 | 9100 US 50 Fiber Hut Create foundation detail | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 36.5 | 35.5 | 1 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 2 | 9100 US50 Fiber Hut - Create Bollard Special Detail | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 36.5 | 35.5 | 1 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | NDOT 3821 - Submittal 057R02 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Q1-508-20-101 - S003 - Counter Loops | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | C 3842 Electrical Pole Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Framework Setup | Done | Jordan James <jjames@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Update framework files & review SP locations | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 74 | 74 | 0 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | Send Roadway Design SLI Scope for the project | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
42344 | C 3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | DOCed | C3876 - EA 74320 - SR-305/Broyles Ranch Road (BM) New RRFB & lighting | Victoria Jeffery <vjeffery@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 3 | 74320 Compile & Submit PS&E | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 26 | 26 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Coordinate with Lyon County & update SP information | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 67.5 | 67.5 | 0 |  | FALSE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Send Roadway Design SLI Scope for the project | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
10994 | Done | Potential | EA 74350 - SR 613 Summerlin Parkway, Las Vegas Nevada, 3R project |  | Signals Lighting and ITS\2021 Sprint 6 | Send Roadway Design SLI Scope for the project | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 3 | 3 | 0 |  | TRUE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 4 | Compile and Submit Intermediate Design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 4 | RRFB Linework & Labels $ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 4 | Cover Sheet | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 4 | RRFB Intermediate Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 4 | RRFB Construction & General Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 4 | RRFB Schedules & Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 4 | Special Details | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 4 | Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3824 - Ely CMAR - Electrical Submittals | Done |  |  | 70 | 70 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 3 | 74243 Speed Feedback Cost Estimate | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 32 | 32 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Contract 3833 Traffic Signal Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3833 Submittal Review Request | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3833 Submittal review request | Done |  |  | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\2021 Sprint 3 | Recompile & submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\2021 Sprint 3 | Supplemental #1 sheet changes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\2021 Sprint 3 | Solar Array items | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Bid item review for Change Order | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | C3842 Electrical Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Contract #3849 - Submittal 012.1 - Revised Electrical Group 3 HDPE Conduit | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | NDOT 3831 Submittal #29 - Electrical #6 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | NDOT 3821 - Submittal 064-1 Ethernet Switch | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Contract 3833 Submittal 53 to 57 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | 3824 - Ped Push Button Post Resubmittal #71.2 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | 3792 Re-Submittal No. 108R1 Preformed Transformer Pad | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | 3792 Re-Submittal No. 0144R1 Lead-In Cable for Loop Detectors | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | 3792 Re-Submittal 326R1 ITS Vault | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | 3792 Submittal No. 331, 332,333 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Inter - New Mapping | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 36 | 36 | 0 |  | FALSE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\2021 Sprint 4 | Create/Submit Supplemental #1 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | P411-19-016 - Material Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | DRAFT Change Order | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | New Service Pedestal Request $ | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Signal Coversheet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Signal Construction Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | General Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Signal Linework and Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Cut Sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Schedules | Done | Jordan James <jjames@dot.nv.gov> | 4 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Special Details | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | RRFB Linework and Labels | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | ITS Construction Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Structure List | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25 | 25 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 4 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 25 | 25 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Address Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 25.5 | 25.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3799 Submittals 68 69 70 | Done |  | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3799 - Submittal No. 67 | Done |  |  | 70 | 70 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | RTC Lemmon DDI Design Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 74 | 74 | 0 |  | TRUE
45035 | C 3821 - EA 74043 - Southwest McCarran Improvements | DOCed | C3821 - EA 74043 - Southwest McCarran Improvements | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Mayberry Signal Modifications | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 46 | 46 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3833 High Mast Lowering Device 623N-058 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3833 Submittal review Package 2 of 2 | Done |  |  | 70 | 70 | 0 |  | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Design .kmz file to depict proposed NVE connections | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 41 | 4 | 37 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3792 Submittal No. 0351, 0352, 0353, 0354 | Done |  |  | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 9 | 74164 Address Intermediate Review comments (Design LT01-LT05) | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 42 | 39 | 3 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3792 Re-Submittal 326R1 ITS Vault | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Submittal Cover Sheet - NVDOT - Universal_00623N_00623N-043-1 (1) | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3845 Submittal #16 | Done |  |  | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\2021 Sprint 5 | Create/Submit Supplemental #5 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
10994 | Done | Potential | EA 74261 - Signal at River Ranch Rd (Fernley) and one other signal |  | Signals Lighting and ITS\2021 Sprint 5 | Review plans for Supplemental #5 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 76 | 76 | 0 |  | TRUE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address Specs' Comments | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | 30% Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Develop Scope | Done | Jordan James <jjames@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Provide/Address Comments in Shared Review | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | 74309-Review SP Location at SR160/SR159 | Done |  | 0 | 36 | 36 | 0 |  | FALSE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Comment on PS&E Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Coordinate w/ Roadway for disturbance areas | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Review & Finalize Change Order | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Framework | Committed | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 8 | 2 | 6 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | 30% Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | High Mast Estimate | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 10 | 10 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Conflict analysis | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\2021 Sprint 5 | Supplemental #1 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 9 | Special Detail- Speed Feedback Sign Review/Updates | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 8 | 74164 Service Pedestal Relocate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3831 Submittal #17 - Electrical Revised R2 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Contract 3849 Submittal 039 Fiber Optics. | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3849 submittals 021 & 022 Electrical | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3842 Electrical Submittals revisions | Done |  |  | 70 | 70 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | PDFS submittal | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 23 | 23 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Coordinate Fiber Connection | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 25.5 | 25.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3833 Submittal Cover Sheet - NVDOT 623N-060 | Done |  |  | 70 | 70 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 5 | Provide/Address Shared Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Separate Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25 | 25 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | I-80 Fiber Hut Linework & Labels | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | I-80 Fiber Hut Schedules & Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | I-80 Fiber Hut Cover Sheet / Sheet Layout | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | I-80 Fiber Hut Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Address Spec Comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 67.5 | 67.5 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | I-80 Fiber Hut Compile & Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Service Pedestal Requests | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 23 | 23 | 0 |  | FALSE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Address PS&E Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 31 | 31 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | NDOT 3833 Submittal Cover Sheet - NVDOT - Universal_00623N_00623N-059-1 (1) | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3845 Revised Submittal #16 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> |  | 70 | 70 | 0 |  | FALSE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 7 | 74164 Enter/Address comments in Shared Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Updates to Std Plans (Materials Request) | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | I-80 FH Generate FH sheets | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 21 | 21 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Check HM Design with L&A design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Framework - 74239 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 35 | 35 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | ITS Sheets - Intermediate - 74239 | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 35 | 35 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | ITS Schedules - Intermediate - 74239 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 35 | 35 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | ITS Plan - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 35 | 35 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | ITS Details - QAQC- 74239 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Lighting Schedules - Intermediate - 74239 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 35 | 35 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Lighting Sheets - Intermediate - 74239 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 35 | 35 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Lighting Plan - Intermediate - 74239 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 35 | 35 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Address comments from Crew911 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 67.5 | 67.5 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Structure List - 74239 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 35 | 35 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Estimate - 74239 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 35 | 35 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Compile & Submit - 74239 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 35 | 35 | 0 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Update Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Structure List Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Comment on PS&E Review | Done | Jordan James <jjames@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | DOC Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 6 | PDFS Cost Estimate | Removed | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 6 | Service Pedestal Request | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | QA/QC Specs Revisions | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | 30% Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | PDFS Report | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 1 | 1 | 0 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | 74349 Framework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | 74349 Lighting Linework/Labels | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | 74349 Lighting Construction Notes/General Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Review phase 1 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Update Sheet Files for ITS & Lighting | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 42.5 | 41.5 | 1 |  | TRUE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | 3 Quote- Intermediate Design Layout | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | 3 Quote- Intermediate Schedules | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | lighting cutting sheets | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 34.5 | 32.5 | 2 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Update Meter Into design | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Update Schedule | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 4 | 42.5 | 38 | 4.5 |  | TRUE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Muller Signal Project Estimate | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 29 | 26 | 3 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Project Special Provisions Review Training | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Analysis | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | SLI Intermediate Coordination Meeting (Group Designers Only) | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Schedule & Structure List | New |  | 6 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Post Doc Design |  | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Post Doc Design |  | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Post Doc Design |  | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Post Doc Design |  | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Post Doc Design |  | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Cut Sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Framework | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Justification Letter | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Requests $ | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Compile and submit | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Update Structure List and Estimate | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Build Features & PBIs | New |  | 1 | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Design Framework | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Develop Scope & PDFS Report | New |  | 1 | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Request Service Pedestals | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Review As-Built Plans | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New |  |  | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 |  | TRUE
69407 | Project Template - Eric1 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Analysis | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | SLI Intermediate Coordination Meeting (Group Designers Only) | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Schedule & Structure List | New |  | 6 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Post Doc Design |  | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Post Doc Design |  | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Post Doc Design |  | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Post Doc Design |  | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Post Doc Design |  | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Cut Sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Framework | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Justification Letter | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Requests $ | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Compile and submit | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Update Structure List and Estimate | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Build Features & PBIs | New |  | 1 | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Design Framework | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Develop Scope & PDFS Report | New |  | 1 | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Request Service Pedestals | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Review As-Built Plans | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New |  |  | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 |  | TRUE
69531 | Project Template - Eric2 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Analysis | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | 74349 Lighting Schedules & Structure List | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
10994 | Done | Potential | C3866/EA 74192 - Caliente US-93 3R fm Minnie St to SR-319 |  | Signals Lighting and ITS\2021 Sprint 6 | BRAT Report Review | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 59 | 59 | 0 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | 74349 Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | 74349 Compile and Submit Intermediate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | 74349 Cover Sheet/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Build Features & PBIs - Jordan | Done | Jordan James <jjames@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Build Features & PBIs - Pete | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Build Features & PBIs - Victoria | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Build Features & PBIs - Laura | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Build Features & PBIs - Gurpreet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Build Features & PBIs - Austin | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | Build Features & PBIs - Brenda | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | 30% Lighting Design | Committed | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 8 | 2 | 6 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Fiber Optic Sensing | New |  | 2 | 41 | 4 | 37 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3858 Submittal 05-1 Electrical Group 3 - Conduit | Done |  |  | 70 | 70 | 0 |  | FALSE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Conduit Run Revisions | Done | Jordan James <jjames@dot.nv.gov> | 4 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Coordination w/ Roadway | Done | Jordan James <jjames@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Address Shared Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Check Schedules and Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Update, Compile and Resubmit | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 11 | 11 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Linework and Labels - Signal Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Estimate- Signal Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Structure List - Signal Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Signals Coversheet/Key Map | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Construction Notes - Signal Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | General Notes - Signal Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Cut sheets - Signal Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Cut sheets - Lighting Design | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 6 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Linework and Labels - Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Estimate - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Lighting Coversheet/Key Map | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Structure List - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 2 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Schedules - Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Construction Notes - Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Verify Construction Notes | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Compile and submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Address Intermediate shared Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | ITS - Address PS&E Shared Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Address Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Update Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Address Review Comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3833 SLI Submittal Review Request 61-69 | Done |  | 1 | 70 | 70 | 0 |  | FALSE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | ITS Coversheet/Key Map | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Cut sheets - ITS Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Construction Notes - ITS Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | General Notes - ITS Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Schedules - ITS Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Structure List - ITS Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Estimate - ITS Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Linework - ITS Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Schedules - Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Estimate - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Construction Notes - Lighting Design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | General Notes - Lighting Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Structure List - Lighting Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Lighting Coversheet/Key Map | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Linework - Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Cut sheets - Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Compile and submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Framework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Address Intermediate Shared Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 28 | 28 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Review Shared Review Set | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 22 | 22 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Update Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 28 | 28 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 28 | 28 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Check Schedules and Update Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 28 | 28 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Lighting Design Changes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 22 | 22 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Address Shared Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 22 | 22 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 22 | 22 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Update Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Check Schedules and Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Schedules - Lighting Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Estimate - Lighting Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Lighting Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | General Notes - Lighting Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Structure List - Lighting Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Lighting Coversheet/ KeyMap | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Lighting Linework and Labels | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 20.5 | 20.5 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Review Shared Review Set | New |  | 0 | 0 | 0 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Address Review Comments | New |  | 0 | 0 | 0 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 0 | 0 | 0 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | Done |  | 1 | 6.5 | 6.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Compile and Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 6.5 | 6.5 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Provide Comments in Shared Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Address QAQC Internal Review comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 7 | 7 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Address Shared Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 7 | 7 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Compile and Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 7 | 7 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Framework | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Compile & Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 20.5 | 20.5 | 0 |  | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design (Only 30% ITS & LTG Plans & Rough Estimate) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Compile and submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design (Only 30% ITS & LTG Plans & Rough Estimate) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Lighting Linework and Labels | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 16 | 16 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design (Only 30% ITS & LTG Plans & Rough Estimate) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | ITS Linework and labels | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 16 | 16 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design (Only 30% ITS & LTG Plans & Rough Estimate) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | Review special provisions | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Check Schedules and Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Update Estimate | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Compile and Submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 18 | 18 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Address Internal Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 15.5 | 15.5 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Review Shared Review Set | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 18 | 18 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Compile and Submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Compile and Submit - QA/QC | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Structure List and Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Create FHxx Sheets - 1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Trench Detail | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Coordinate with Hydraulics for design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Linework, Labels & Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Framework | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Conceptual design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Compile and Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 7 | 7 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Contract 3833 Submittal Review 623N-019-2 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | NDOT 3849 Submittal - 022.1 - Electrical Light Fixtures revised | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 6 | RTC Lemmon DDI Review Comment Response | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 74 | 74 | 0 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Review Adaptive Lighting Concept of Design Report | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | 74349 ITS Linework/Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | 74349 ITS Schedules and Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | 74349 ITS Construction Notes & General Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | 74349 ITS Cover/Key map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | 74349 ITS Service Pedestal Request | Removed | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | ITS Coversheet/Key Map | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Cut sheets - ITS Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Construction Notes - ITS Design | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Schedules - ITS Design | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Structure List | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Linework & Labels - ITS Design | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Schedules - Lighting Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 10 | Estimate - Lighting Design | Removed |  | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Construction Notes - Lighting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | General Notes - Lighting & ITS Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Linework & Labels - Lighting Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Cut sheets - Lighting Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 10 | Check Estimate | Removed |  | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 10 | Verify Construction Notes | Removed |  | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 10 | Check Structure List | Removed |  | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Compile and submit | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 10 | Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 15 | Address QAQC Shared Review Comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 16 | Compile and Submit | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | 74302 Send Details to UPRR | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | I-80 Fiber Hut FH Sheet Revisions | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 51.5 | 51.5 | 0 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | Signal Linework/labels/construction notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | Signal Schedules | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | ITS Linework/labels/construction notes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | ITS Schedules | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | ITS Special Details & General Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | Intermediate Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | Plot & submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 15 | Comment on Intermediate Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 11 | Internal Review on Intermediate Submittal | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 17 | Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 17 | Address ITS Intermediate Review Comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 17 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 22 | Address ITS PS&E Review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 17 | Address Signal Intermediate Review comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 12 | Address Signal Intermediate Internal Review comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 12 | Address ITS Intermediate Internal Review comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 22 | Address Signal PS&E Review comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 22 | Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 23 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | Framework file | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | Signal Special Details & General Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Address LTG IMD IR comments - LT01-LT09 | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 4 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Address LTG IMD IR comments - Sheets | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Address ITS IMD SR Comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Address ITS IMD IR comments - Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Structure List & Estimate | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Lighting Sheet Layout/Cover Sheet/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Lighting Special Details & General Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Lighting Linework/labels/construction notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Lighting Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 6 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Plot | Done | Jordan James <jjames@dot.nv.gov> | 1 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Intermediate Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Address Lighting 1st PS&E Review comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Address ITS 1st PS&E Review comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Comment on 1st PS&E Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | ITS Linework/labels/construction notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 8 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | ITS Schedules & Structure List | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | ITS Special Details & General Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | ITS Sheet Cover Sheet/Key Map | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedules | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/labels/construction notes | New |  | 4 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details & General Notes | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Coordinate Intermediate Review w/ Specifications | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Internal Review of Intermediate Submittal | New |  | 4 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review comments | New |  | 4 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS Intermediate Review Comments | New |  | 2 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Comment on Intermediate Review | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Intermediate Review comments | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review comments | New |  | 4 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Coordinate PS&E Review w/ Specifications | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New |  | 2 | 21 | 0 | 21 | 2025-02-24 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E Review comments | New |  | 2 | 21 | 0 | 21 | 2025-02-24 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New |  | 1 | 21 | 0 | 21 | 2025-02-24 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 21 | 0 | 21 | 2025-02-24 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 21 | 0 | 21 | 2025-02-24 | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | I-80 Fiber Hut Specs Coordination | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 9 | 74243 Compile and Submit QAQC | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 14 | 74243 Comment on Shared Review | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 9 | 74243 Address Comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 9 | 74243 QAQC Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 14 | Address Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 15 | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 9 | 74164 QAQC Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 13 | Review Shared Review Set* | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 14 | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Framework - 74360 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 23 | 23 | 0 |  | FALSE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | SLI Intermediate Coordination Meeting (Group Designers Only) | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Schedule & Structure List | New |  | 6 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Post Doc Design |  | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Post Doc Design |  | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Post Doc Design |  | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Post Doc Design |  | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Post Doc Design |  | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Cut Sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Framework | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Justification Letter | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Requests $ | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Compile and submit | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Update Structure List and Estimate | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Build Features & PBIs | New |  | 1 | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Design Framework | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Develop Scope & PDFS Report | New |  | 1 | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Request Service Pedestals | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Review As-Built Plans | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New |  |  | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 |  | TRUE
69655 | Project Template - Eric3 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Doc Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Analysis | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | SLI Intermediate Coordination Meeting (Group Designers Only) | New |  |  | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals General Notes | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New |  | 2 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Schedule & Structure List | New |  | 6 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Intermediate Design |  | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 38.5 | 0 | 38.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Post Doc Design |  | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Post Doc Design |  | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Post Doc Design |  | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Post Doc Design |  | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Post Doc Design |  | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | ITS Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Cut Sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Framework | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Justification Letter | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | SP Requests $ | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Compile and submit | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Update Structure List and Estimate | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Build Features & PBIs | New |  | 1 | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Design Framework | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Develop Scope & PDFS Report | New |  | 1 | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Request Service Pedestals | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Review As-Built Plans | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Coversheet/Key Map | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - General Notes | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Linework | New |  |  | 2 | 0 | 2 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New |  |  | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 |  | TRUE
69779 | Project Template - Eric4 | Potential | QAQC Design |  | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 |  | TRUE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Linework and labels updates | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | update construction notes. | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Update lighting design. | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Update ITS design according to 3292 and 3578 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | TRUE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | ITS Schedules & Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Clearing and Grubbing/Seeding | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 19 | 19 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Preliminary Compile and Submit | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Preliminary Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Preliminary Estimate | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 19 | 19 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Calle De La Plata PBI 3 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 29 | 26 | 3 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | 3-Quote- General Notes | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Download As-built file for 3683 (Starr) | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | New Item - Submittal 00623-018-0 - NDOT 3983 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | 3982 Submittals 234 thru 237 for Your Review & Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | FW: NDOT 4501 Submittal 35 - Poles.pdf | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | New Item - Submittal 00623-021-0 - NDOT 3983 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | 3982 - Submittals 241 thru 245 for Your Review & Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | 4501 Submittal 36 - Automated Vehicle Classification System | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | 4501 Submittal 37 - Loop Detectors | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | update lighting schedules. | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Update ITS schedules. | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Update structure list and final bid item review. | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Recompile & submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 0 | 7 | 7 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Structure List & Estimate | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Update Clearing and Grubbing/ Seeding | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 35.5 | 35.5 | 0 |  | TRUE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Replace conductors | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 6 | 35.5 | 35.5 | 0 |  | TRUE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | Build Features & PBI's | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Design Framework | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | ITS Cover/Key Map | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | ITS General Notes | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | ITS Linework/Labels/Construction notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | ITS Schedules & Structure List | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Detail Search for PHB | Done |  | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Lighting General Notes | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Lighting Linework/Labels/Construction Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Create PHB Detail | Committed | Fernando Torres <ftorres@dot.nv.gov> | 4 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile & Submit | New |  | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Intermediate Estimate | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Cut Sheets | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 2 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 0.5 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 19 | 9 | 10 | 2024-05-08 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Voltage Drop | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 2 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 0.5 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 10.5 | 0 | 10.5 | 2024-10-14 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 1 | 9 | 0 | 9 | 2024-12-30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 1 | 9 | 0 | 9 | 2024-12-30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 0.5 | 9 | 0 | 9 | 2024-12-30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 0.5 | 9 | 0 | 9 | 2024-12-30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 9 | 0 | 9 | 2024-12-30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 1 | 9 | 0 | 9 | 2024-12-30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 9 | 0 | 9 | 2024-12-30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 0.5 | 9 | 0 | 9 | 2024-12-30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 2 | 9 | 0 | 9 | 2024-12-30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 9 | 0 | 9 | 2024-12-30 | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | GCW design: Mark up fiber conduit plans | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | 3982 REVISED Submittal 45R1 for Your Review & Approval | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | New Item - Submittal 00623-021-1 - NDOT 3983 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | New Item - Submittal 00623-024-0 - NDOT 3983 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | FW: NDOT 3978 Submittal #33 - Modify Electrical Service | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | FW: NDOT 3978 Submittal #35 - Equipment Cabinet | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Structure List - 74346 | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Framework - 74346 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Compile & Submit - 74346 $ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Estimate - 74346 $ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | UPRR Special Details | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | NDOT 3842 Electrical Submittals | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Comment on Intermediate Review (1st Submittal) | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Add Kingslane RRFB to ITS Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 48.5 | 48.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | TRUE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Compile & Submit - 74360 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | StructList & QA/QC Estimate - 74360 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Lighting Schedules - Intermediate - 74346 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Lighting Plan - Intermediate - 74346 | Done | Brian Dodds <btdodds@dot.nv.gov> | 4 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Lighting Sheets - Intermediate - 74346 | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 40 | 38 | 2 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Lighting Schedules - Intermediate - 74360 | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 4 | 23 | 23 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Lighting Plan - Intermediate - 74360 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 23 | 23 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Lighting Sheets - Intermediate - 74360 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 23 | 23 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Structure List - 74360 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 23 | 23 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Estimate - 74360 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 23 | 23 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Compile & Submit - 74360 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 23 | 23 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Lighting cleanup | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Complete Schedule population | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | IMD address review comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | DOC StructList & Estimate- 74360 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Compile & Submit - 74360 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Signal Plan - Intermediate - 74346 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Signal Sheets - Intermediate - 74346 $ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Signal Schedules - Intermediate - 74346 | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 40 | 38 | 2 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Address comments from PS&E#3 review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Compile & Submit - 74204 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Structure List & Estimate - 74204 | Done | Jordan James <jjames@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Build Features & PBIs - Victoria2 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Build Features & PBIs - Laura2 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Build Features & PBIs - Jordan2 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | Build Features & PBIs - Pete2 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Address IMD SR Lighting Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 6 | 48.5 | 48.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Address IMD SR ITS comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 6 | 48.5 | 48.5 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | PS&E Review & Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Add Slow Trucks Sign with Flashers | Done | Jordan James <jjames@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Quantify Scope Items and Add Pricing | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 9 | 9 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3842 - Submittal Set 6 RDS | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3842 - Submittal Set 6 - 1 of 2 Lum B | Done |  |  | 70 | 70 | 0 |  | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/labels/construction notes | New |  | 8 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules | New |  | 4 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details & General Notes | New |  | 1 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Additional Doc items needed for SLI Standalone project | New |  | 8 | 21 | 0 | 21 | 2025-02-24 | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3858 Submittal 14-1 Electrical Group 3 - Pull Boxes and Junction Boxes/Splice Boxes | Done |  |  | 70 | 70 | 0 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Address Signal IMD SR comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 48.5 | 48.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Coordinate w/ Hydraulics for Conflicts | Done | Jordan James <jjames@dot.nv.gov> | 1 | 48.5 | 48.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Trunkline Adjustments | Done | Jordan James <jjames@dot.nv.gov> | 4 | 48.5 | 48.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | NDOT Contract 3833 Submittal Review Request - Sent to TOTS | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 7 | I80 Fiber Hut Construction Notes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | I80 Fiber Hut General Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 8 | 74164 Address Intermediate Review comments (Schedules/Notes/Structure List LT06-LT13) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 42 | 39 | 3 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3857 Electrical Submittal #1 - Poles, PB, Pedestal, Lum B | Done |  |  | 70 | 70 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Address Intermediate Shared Review Comments | New |  | 0 | 0 | 0 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Address Intermediate Internal Review Comments | New |  | 0 | 0 | 0 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 0 | 0 | 0 | 0 |  | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Internal Review of QAQC Submittal | New |  | 2 | 21 | 0 | 21 | 2025-02-24 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address QAQC Internal Review comments | New |  | 4 | 21 | 0 | 21 | 2025-02-24 | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Address ITS IR comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Address LTG IR comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Address PS&E SR SIG comments | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Comment on 2nd PS&E SR | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Address LTG IMD SR Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Comment on Intermediate Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Address Lighting PS&E SR comments & R/W Utilities concerns | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 7.5 | 7.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Comment on PS&E Shared Review | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 7.5 | 7.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 7.5 | 7.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 7.5 | 7.5 | 0 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 22 | Address Signal QAQC Internal Review comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 22 | Address ITS QAQC Internal Review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Calculate Clearing & Grubbing/Seeding | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Lighting General Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Comment on Intermediate Shared Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Address Lighting PS&E Review comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal QAQC Review comments | New |  | 0 | 11 | 11 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Upgrade RWIS Pad to include more Solar Poles | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Address ITS PS&E Shared Review comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Comment on PS&E Shared Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Plot & Submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Structure List & Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Cover/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Signal Special Details & General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Signal Linework/labels/construction notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Signal Schedules | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Framework file | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Plot & submit to Roadway | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Intermediate Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Structure List | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Address Signal Intermediate Internal Review comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Plot & Submit to Roadway | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 1 | Structure List & Estimate | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Plot & Submit to Roadway | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 10 | 10 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Structure List & Estimate | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 10 | 10 | 0 |  | TRUE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | DOC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Address PS&E Shared Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 3.5 | 3.5 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | DOC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | Done |  | 1 | 3.5 | 3.5 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Update Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Compile and Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Address Intermediate Review comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Update Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 9 | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Review Shared Review Set | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Address Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Compile and Submit | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | ITS cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 27 | 27 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Address ITS comments from Intermediate reviews | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Structure List & Estimate - QA/QC 74239 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Address Lighting Intermediate comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Compile & Submit - 74239 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | ITS Sheet cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Lighting Schedules | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Lighting cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Address comments from PS&E reviews - Lighting | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Structure List - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | QA/QC Estimate - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | IMD Specs Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Compile & Submit - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69 | 69 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Internal Review - Intermediate - 74239 | Done | Jordan James <jjames@dot.nv.gov> | 4 | 35 | 35 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Address comments from PS&E review - | Done | Brian Dodds <btdodds@dot.nv.gov> | 2 | 27 | 27 | 0 |  | TRUE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Intermediate Internal Review ITS | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Address Intermediate Internal Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Doc Submittal - 74341 | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Internal Review - Lighting QA/QC - 74341 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 9 | 9 | 0 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Intermediate Internal Review ITS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Intermediate Internal Review Lighting | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Address Internal Review Comments ITS | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Address Internal Review Comments Lighting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | QAQC Internal Review ITS & Lighting | Done | Jordan James <jjames@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | QAQC Address Internal Review Comments ITS & Lighting | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Structure List - 74239 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | DOC Estimate - 74239 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Compile & Submit - 74239 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 27 | 27 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Structure List - 74249 | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Doc Specs Review - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 22 | Doc Estimate - 74249 | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Compile & Submit - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 10 | Intermediate Internal Review ITS | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 11 | Intermediate Address Internal Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 32 | 32 | 0 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Address comments from QA/QC/PS&E review | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Internal Review - Lighting IMD - 74249 | Done | Jordan James <jjames@dot.nv.gov> | 4 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Redo ITS Schedules - 74249 | Done | Brian Dodds <btdodds@dot.nv.gov> | 6 | 56 | 56 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | ITS cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Address comments from QA/QC review | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Lighting cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 20 | Address comments from QA/QC review | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Signal cleanup 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 69.5 | 69.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Internal Review - ITS IMD - 74249 | Done | Jordan James <jjames@dot.nv.gov> | 6 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Internal Review - Signal IMD - 74249 | Done | Jordan James <jjames@dot.nv.gov> | 6 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 9 | ITS Schedules - QA/QC - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69 | 69 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | ITS Details Cleanup - Doc - 74249 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 69.5 | 69.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Coordinate with Roadway for Earthwork | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 21 | 21 | 0 |  | TRUE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Doc Submittal - 74341 | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Address comments from PS&E review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | QA/QC Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Lighting cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Intermediate Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Lighting Schedules - Intermediate - 74341 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 16 | 16 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | QA/QC Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Address comments from Intermediate review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 6 | 6 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Doc Submittal - 74341 | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Compile & Submit - 74341 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | QA/QC Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Complete Schedule population | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Intermediate Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Lighting Design - Intermediate - 74341 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 16 | 16 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Doc Submittal - 74341 | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Structure List - 74341 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | QA/QC Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | QA/QC Estimate - 74341 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Doc Submittal - 74341 | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Lighting cleanup | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Complete Schedule population | Done | Jordan James <jjames@dot.nv.gov> | 4 | 41 | 41 | 0 |  | TRUE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Intermediate Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Framework - 74341 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 16 | 16 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Intermediate Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Compile & Submit - 74341 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 16 | 16 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Intermediate Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Estimate - 74341 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 16 | 16 | 0 |  | FALSE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 12 | Internal Review- Reviewer | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 12 | Internal Review- Address ITS Comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Create Underground/Above Ground sheets for Signals | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 25.5 | 25.5 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Adjust Conduit Trenching | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 25.5 | 25.5 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Add seeding and clearing & grubbing | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Battery backup system | Done | Jordan James <jjames@dot.nv.gov> | 2 | 25.5 | 25.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | NDOT D1 Highmast Luminaire | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review | Approved | Victoria Jeffery <vjeffery@dot.nv.gov> | 0 | 36 | 36 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | 30% Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | KMZ File (Ex. SPs + New Scope) | Done | Jordan James <jjames@dot.nv.gov> | 4 | 10 | 10 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject Internal Review Comments | Approved | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 36 | 36 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | 30% Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Initiate High Mast Scope | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 10 | 10 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Build Features & PBIs - Victoria3 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Build Features & PBIs - Laura3 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Build Features & PBIs - Jordan3 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Build Features & PBIs - Pete3 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Build Features & PBIs - Gurpreet2 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Address Shared Review Comments | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 17 | 14 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Provide Comments Intermediate Internal Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 25.5 | 25.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | RTC Lemmon DDI Review Comment Response #2 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 74 | 74 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Intermediate Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 8 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Intermediate Internal Review Address ITS Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | NVE CADD Files | Done | Jordan James <jjames@dot.nv.gov> | 1 | 90.5 | 90.5 | 0 |  | TRUE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | 30% Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | Submit PDFS Report | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 3 | 3 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Internal Review | Done | Jordan James <jjames@dot.nv.gov> | 8 | 90.5 | 90.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Address Lighting Internal Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 8 | I-80 Break out FH sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Internal Review | On-Hold |  | 8 | 116.5 | 60.5 | 56 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | FW: NDOT 3978 Submittal #36 - Solar Photovoltaic Array | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | 3982 - Submittal 258 No 1_0 Conductor for Your Review & Approval | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | 3982 - Submittal 77R1 - Alternate Manufacturer for Your Review & Approval | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | GCW Design: Cut sheets | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Create Block Diagram ITS | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Update Lighting Design | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Review quantities sent from construction crew. | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 73 | 73 | 0 |  | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Field Visit | New |  | 2 | 36 | 2 | 34 | 2024-09-23 | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Signal Design - Cut sheets | New |  |  | 2 | 0 | 2 |  | FALSE
51160 | Project Template - do not modify | Potential | Preliminary 30% Design |  | Signals Lighting and ITS | Lighting Design - Cut Sheets | New |  |  | 2 | 0 | 2 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Preliminary 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Design - Linework | Done | Alesha Jackson <ajackson@dot.nv.gov> |  | 19 | 19 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject PS&E Shared Review comments | New |  | 1 | 16.5 | 0 | 16.5 | 2026-05-10 | FALSE
51170 | EA 74474 / 61083 - IR580 Washoe to Mt Rose Hwy 3R | DOCed | QA/QC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Specification internal review | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 73 | 73 | 0 |  | TRUE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | update lighting cut sheets. | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 34.5 | 32.5 | 2 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Special Details Update | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Update General Notes | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Cutting Sheets for Design work | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Internal review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 42.5 | 38 | 4.5 |  | TRUE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | 3-Quote- Cutting Sheets for Design work | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | 3-Quote-Internal Review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Address Internal Review comments.. | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 34.5 | 32.5 | 2 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Migrate & Check Schedules & Calculations | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | FW: NDOT 4500 - Submittal 0035 - Conductor | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | FW: NDOT 4500 - Submittal 0034 - Pull Boxes | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | FW: NDOT 4500 - Submittal 0032 - Multiduct Conduit | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | FW: NDOT 4500 - Submittal 0031 - HDPE Conduit | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | FW: NDOT 4500 - Submittal 0030 - Schedule 40 Conduit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | FW: NDOT 4500 - Submittal 0033 - ITS Vaults | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | FW: P557-23-016 Submittal Set 3 - Solar Package & Pull Box Resubmittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Create an ATC Signal Cabinet Standard Plan/Special Detail | Committed | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | 3858 CO#4 - PBI 1 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 15 | 7 | 8 |  | TRUE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Scoping | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | 74249 Ph2 - PBI 1 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 3 | 3 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | New Item - Submittal 00623-026-0 - NDOT 3983 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2024 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Update Standard Plans per NDOT Shared Review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 18 | 18 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Review Roadway Site Changes | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | GCW Design: Prelim Quantities | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | GCW Design: Update Key Map | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 0.5 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | GCW Design: Add Construction Notes | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 71 | 59 | 12 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Confirm QC Comments | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 29 | 26 | 3 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Confirm QC Comments | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Address Review Internal Comments | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 42.5 | 38 | 4.5 |  | TRUE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Address Review Internal comments | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Create exhibit that shows location of signal loops that need to be replaced after milling | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 2.5 | 2.5 | 0 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Add New Scoping to proejct | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Lighting schedules | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Lighting construction notes and general notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Service pedestal Request. | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph1 Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Revision #7 additional underground and cabling at US 395 &Gilman | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 6 | 6 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | FW: NDOT 4500 - Submittal 0051 - Special Cabinet and 1W1C Signal Head | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | 3858 C.O.4 - PBI #2 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 15 | 7 | 8 |  | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Trunkline Connection to Carson Spooner intersection | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | FW: NDOT 4500 - Submittal 0050 - Meter Pedestals | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2026 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Create New Chain Sign Detail | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 4 | 2 | 2 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | General Notes ITS | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Lighting Construction Notes and Drop Circles | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Signals Construction Notes and Drop Circles | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | IMD Compile and Resubmit | Committed | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15 | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | FW: NDOT 4500 - Submittal 0046 - Solar PV Array | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | FW: NDOT 4500 - Submittal 0044 - Signal Head 2W1C, Post Top | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | FW: NDOT 4500 - Submittal 0043 - Intelligent Traffic Signs | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | 3982 Submittal 60R2 for Your Review & Approval | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | 4501 - Submittal 032R1 – Solar Powered Warning Light | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | New Item - Submittal 00623-027-0 - NDOT 3983 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Review Plans for PS&E Submittal & Compile and Submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 9 | 6 | 3 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Update Structure List - IMD Submittal 2 | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 71 | 59 | 12 |  | FALSE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for 3 Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Review signal scope | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Signal schedules. | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Signal construction notes. | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Signal General Notes | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Construction notes | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | ITS Schedules | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 50 | 50 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | SLI Rev 7 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 27 | 27 | 0 |  | FALSE
71927 | Communication Building Design | Actively Working | Project Management | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Project DevOps Build Out | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 1 | 1 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for 3 Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Service pedestal request. | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 7 | 7 | 0 | 2024-02-09 12:30 | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | RFI 003 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 9.5 | 6.5 | 3 |  | TRUE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Shared Review Comments & Responses | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Framework | Committed | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Initial Review of Site & Request Service Pedestal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 1 | 61 |  | TRUE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review Comments | New |  | 2 | 13 | 0 | 13 | 2027-01-02 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Shared Review Comments | New |  | 1 | 13 | 0 | 13 | 2027-01-02 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 13 | 0 | 13 | 2027-01-02 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 13 | 0 | 13 | 2027-01-02 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Ph. 2 Signal Preliminary Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 42 | 2 | 40 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Schedules | New |  | 2 | 42 | 2 | 40 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Ph. 2 Lighting Preliminary Design | Approved | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 42 | 2 | 40 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | ITS Preliminary Design | Approved | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 42 | 2 | 40 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedules | New |  | 2 | 42 | 2 | 40 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules | New |  | 2 | 42 | 2 | 40 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 42 | 2 | 40 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 42 | 2 | 40 |  | FALSE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | SSTC coordination for TER DMSes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | ITS sites - construction notes & details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 57 | 33 | 24 | 2025-03-01 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS design | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 57 | 33 | 24 | 2025-03-01 | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | RFI 29 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 27 | 27 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | RFI 30 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 27 | 27 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | RFI 32 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 27 | 27 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | RFI 33 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 27 | 27 | 0 |  | FALSE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS\2024 Sprint 11 | Professional Training for 5 Hours | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 5.5 | 5.5 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Change Order for Rev7 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 0.5 | 27 | 27 | 0 |  | FALSE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS | Professional Training for (?) of Hours | New |  |  | 5.5 | 5.5 | 0 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | RWIS Sites Prelim | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 10 | 7 | 3 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Trunkline Refinement | Committed | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 10 | 7 | 3 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | SP Identification & Justification | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 10 | 7 | 3 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Structural list | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | 30% Estimate | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ORD Development | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph1 Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | attaching the final locations of the poles and pull boxes for RRFB at Kingslane to the plans | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 6 | 6 | 0 |  | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Add Type 7 mod poles & details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 40 | 38 | 2 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | RE: NDOT 3978 Submittal #33 - Modify Electrical Service | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | FW: NDOT 4500 - Submittal 0050 - Meter Pedestals Resubmittal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Signals Special Details 2.0 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | DGN for SUE | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Signal Design - Modifications | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | 30% Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Review scoping and as-built | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 7 | 7 | 0 | 2024-02-09 12:30 | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | FW: NDOT 4500 - Submittal 0059 - Luminaires Type B | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | FW: NDOT 4500 - Submittal 0055 - AVCS | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | FW: NDOT 4500 - Submittal 0054 - Poles | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | IMD 2 Internal Review - ITS | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Splice Details Updates | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | IMD 2 Internal Review Accept/Reject Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 71 | 59 | 12 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Lighting voltage drop | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Compile and Submit | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Estimate Update | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Structure List | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 42.5 | 38 | 4.5 |  | TRUE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | 3-quotes Estimate | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 29 | 26 | 3 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | 3-quote Structure List | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 29 | 26 | 3 |  | FALSE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Field Visit Planning & Coordination | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Project Build Out | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 38 | 10 | 28 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | RFI 34 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 27 | 27 | 0 |  | FALSE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Intermediate Coordination Efforts | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Design Framework | New |  | 2 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 38 | 10 | 28 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Address Internal Review Comments | On-Hold |  | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Internal Review | On-Hold |  | 8 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Address Internal Review Comments | On-Hold |  | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Compile and submit | On-Hold |  | 1 | 116.5 | 60.5 | 56 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3858 Submittal 14-1R Electrical Group 3 - Pull Boxes and Junction - Splice Boxes | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3858 Submittal 18-1 Electrical Group 1 - Poles | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Cont. 3828 Weigh in Motion and Traffic Signal Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3833 Submittal Review request 623N-059-2 | Done |  |  | 70 | 70 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | 30% Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Scope Verification | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 2 | 2 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3860 Submittals | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3833 - 623N-070 System Integrator Resume | Done |  |  | 70 | 70 | 0 |  | FALSE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS\2021 Sprint 10 | Adjust sheets to add work back in for NW signal pole. | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 94 | 94 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | 30% Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | PDFS Report to Dennis | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | 30% Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | SP Request to R/W | Done | Jordan James <jjames@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | NDOT 3857 Submittal #16 - Electrical #2 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Contract 3857 Electrical Submittal #1 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | 3866 Group 7 Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | 3866 Group 16 Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | 3866 Group 6 and 13 Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | DOC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | Provide Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Internal Review on QAQC Spec Plan Set | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 67.5 | 67.5 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | DOC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Address DOC Internal Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | 3866 Group 6 and Group 11 Submittals | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Plan Updates | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\2021 Sprint 12 | Plan Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 116.5 | 60.5 | 56 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Submittal Review Request Contract 3833 | Done |  | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Submittal Review Request 623C-090 Contract 3833 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | 30% Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Send SP Request | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 2 | 2 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3860 Montello crossing | Done |  |  | 70 | 70 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Add keymaps to all sheets$ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 90.5 | 90.5 | 0 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 10 | Structure List - Lighting Design | Removed |  | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Lighting Coversheet & Key Map | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Special Details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Add ITS Sites | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 90.5 | 90.5 | 0 |  | TRUE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | 74309 - Convert SR-159/160 Intersections DGN to DWG | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 36 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Intermediate Internal Review | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 4 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Intermediate Internal Review Address Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Compile and submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Structure List | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | General Notes & Trench Detail | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Lighting Schedules | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Construction Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Lighting Linework & Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Coversheet/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Cut sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 29.5 | 29.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Address Specs and Shared Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 19.5 | 19.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review Address Comments | On-Hold |  | 0 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review | On-Hold |  | 0 | 19.5 | 19.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Check Schedules and Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 19.5 | 19.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Update Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 19.5 | 19.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Address Shared Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Review Shared Review Set | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Update Estimate and Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Submittals 3866; Caliente to Panaca, Group 4 Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Address Comments from PS&E | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 67.5 | 67.5 | 0 |  | FALSE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 16 | AGI 32 Analysis* | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 9 | 74349 ITS Design update | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 66.5 | 65.5 | 1 |  | FALSE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 10 | 74164 Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 42 | 39 | 3 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 12 | Coordination with City of Fallon -2 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Clearing and Grubbing | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | Address ITS Internal Review Comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Framework | Conditional |  | 1 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels | New |  | 1 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Cover Sheet | New |  | 0.5 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 2 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Construction Notes | New |  | 2 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedules and Structure List | New |  | 2 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules and Structure List | New |  | 2 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile & Submit | New |  | 2 | 21.5 | 0 | 21.5 | 2024-06-02 | FALSE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Change Order 2 Pt. 1 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | FALSE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 10 | Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | RWIS Detail - ITS Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | ITS Design Coordination | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Update signal pole schedule | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3849 Submittal - 022.1 - Electrical Light Fixtures - Response to rejection | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3856 - Submittal #34 - Fiber Optic Cable | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3856 - Submittal #33 - Patch Panel | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3856 - Submittal #35 - Integrated Fiber Optic Splice Termination Unit | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | C3828 - 6 Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | 3863 SS2 | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | NDOT 3863 Submittal #3 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Contract 3833 Submittal Review Request | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Move Wildlife flashers | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 67.5 | 67.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | 30% Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Revised SP Request to R/W | Done | Jordan James <jjames@dot.nv.gov> | 1 | 10 | 10 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | 3866; Caliente to Panaca ¦ Group 3 Electrical Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | 3847 Fernley Bike Path - Pull Box Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3866 - STBC-093-3(003) - Submittals for TC Plan & TC Supervisor | Done |  | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | SBX Doc Control: Submittal-15.167.002 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | SBX Doc Control: Submittal-15.167.003 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | SBX Doc Control: Submittal-15.167.004 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | SBX Doc Control: Submittal-15.167.005 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | SBX Doc Control: Submittal-15.167.006 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | SBX Doc Control: Submittal-15.167.007 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | 30% Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 10 | PDFS Report Update | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 3 | 3 | 0 |  | FALSE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Changes to Conceptual Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Address Lighting Internal Review Comments (Service Panel Schedules) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | ITS Sheet Cutting | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | VOID previous sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Coordinate Dual-Mast-Arm Signal Pole | Done | Jordan James <jjames@dot.nv.gov> | 2 | 25.5 | 25.5 | 0 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | PDFS Report | Done | Jordan James <jjames@dot.nv.gov> | 2 | 2 | 2 | 0 |  | FALSE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Pothole Locations | Done | Jordan James <jjames@dot.nv.gov> | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\2021 Sprint 11 | Check Voltage Drop Calcs | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedules & Structure List | New |  | 2 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | General Notes & Special Details | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Design, Labels, & Construction Notes | Approved |  | 6 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Cover/Keymap | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Sheets | New |  | 2 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate & Submittal | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Cover/Keymap | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | General Notes & Special Details | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedules & Structure List | New |  | 2 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Sheets | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Design, Labels, & Construction Notes | Approved |  | 6 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address LTG IMD SR comments | New |  | 4 | 12 | 0 | 12 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address LTG IMD IR comments | New |  | 1 | 12 | 0 | 12 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Signal PS&E Review comments | New |  | 2 | 13 | 0 | 13 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal QAQC Review comments | New |  | 2 | 13 | 0 | 13 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Signal Internal QAQC Review comments | New |  | 2 | 13 | 0 | 13 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New |  | 2 | 13 | 0 | 13 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New |  | 1 | 13 | 0 | 13 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Internal Review on QAQC Submittal | New |  | 2 | 13 | 0 | 13 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 13 | 0 | 13 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 13 | 0 | 13 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 12 | 0 | 12 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 12 | 0 | 12 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-10-27 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New |  | 1 | 11.5 | 0 | 11.5 | 2025-10-27 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS QAQC IR comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-10-27 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address LTG QAQC IR comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-10-27 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E Review comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-10-27 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 11.5 | 0 | 11.5 | 2025-10-27 | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 11.5 | 0 | 11.5 | 2025-10-27 | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Add 14 PBIs - 7 for adding notes for DG and 7 for adding notes for standard plans | New |  |  | 146 | 133 | 13 |  | FALSE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Statewide ITS Spreadsheet | New |  | 0.5 | 11.5 | 0 | 11.5 | 2025-10-27 | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Statewide ITS Spreadsheet | New |  |  | 13 | 0 | 13 |  | FALSE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Design Revisions, Cleanup, and Verification | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Review ITS Plan sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Detail Coordination | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Circuit Analysis | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Review Lighting Sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Review ITS Schedules | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Review Lighting Schedules | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Structure List & Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 3 | Address comments from PS&E Shared Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 4 | DOC StructList & Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 26 | 26 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Generate & populate construction notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Intermediate Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 16 | 16 | 0 |  | FALSE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 11 | Address Spec Comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 42 | 39 | 3 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Complete internal review of Intermediate Submittal | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 21 | 21 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 11 | Address Intermediate internal review comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 51.5 | 51.5 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Coordinate with TOTS for path analysis & request splice diagrams | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review & respond to NVE plans | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Update Plans/Specs with new controller writeup | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Submittals 3866; Caliente to Panaca, Group 4 Re-Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | JOB 3866 Submittals 623.2950 623.3030 Group 11 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3849 Submittal - 022.2 - Electrical Light Fixtures revised | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3824 - Ely CMAR - Electrical Submittal #88 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3863 Submittal Set #4 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3873 SUBMITTALS - 18 19 20 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract #3828 Submittals for WIM | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> |  | 70 | 70 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Update Schedules, SL, and Estimate | Done | Jordan James <jjames@dot.nv.gov> | 4 | 90.5 | 90.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3842 - Submittal Set 8 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3860 | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Submittal . 3866; Caliente to Panaca ¦ Group 3 Electrical Submittal | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Contract 3824 - Ely CMAR - Electrical Submittal #90 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Address comments from Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 6 | 67.5 | 67.5 | 0 |  | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Confirm QC comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 67.5 | 67.5 | 0 |  | FALSE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 12 | Field Site Visit | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 13 | Compile & Submit to Roadway | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 12 | Confirm QC comments on Intermediate Internal Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 55.5 | 54.5 | 1 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Linework - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 2 | 75.5 | 75.5 | 0 |  | FALSE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\2021 Sprint 12 | New SP Requests | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 116.5 | 60.5 | 56 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Address Spec Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 51.5 | 51.5 | 0 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 11 | Coordination with City of Fallon | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 11 | Compile and Submit for PS&E | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Create Block Diagrams for DMS Cabinet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS\2021 Sprint 12 | SLI Change Order | Done | Jordan James <jjames@dot.nv.gov> | 2 | 49 | 49 | 0 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 21 | Internal Review on QAQC Submittal | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 4 | 55.5 | 54.5 | 1 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 8 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 2 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Block Diagram | New |  | 4 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | PS&E Coordination Efforts | New |  | 1 | 7 | 0 | 7 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review | New |  | 2 | 7 | 0 | 7 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Update Schedules & Structure List & Estimate | New |  | 2 | 7 | 0 | 7 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 38 | 10 | 28 |  | TRUE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Field Visit w/City of Reno | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 19 | 9 | 10 | 2024-05-08 | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Update Estimate and Structure List | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Misc ITS Updates | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 0.5 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Radio Sites | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Radio Site Detail | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 71 | 59 | 12 |  | FALSE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Internal Review | New |  | 4 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Internal Review Comments | New |  | 2 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | DOC Submittal | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address Changes From Submittal | New |  | 2 | 3 | 0 | 3 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review Specifications | New |  | 2 | 7 | 0 | 7 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | DOC Submittal | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 1 | 3 | 0 | 3 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Cabinet Block Diagram | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 0.5 | 71 | 59 | 12 |  | FALSE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Create FHxx Sheets -1 | Committed | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 1 | 61 |  | TRUE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Bring to 90% Design | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Bring to 100% Design | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 29 | 10 | 19 | 2024-11-12 | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Directional Drilling Coordination | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Internal Review Comments | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2024 Material Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | FW: 3996 SUBMITTAL #43 R1 - POLES | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 0.5 | 44 | 44 | 0 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Project Build Out | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 26 | 1 | 25 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Accept/Reject Internal Review Comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 50 | 50 | 0 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | 30% design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Address internal review comments | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 50 | 50 | 0 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | IMD 2 Internal Review ITS Address Comments | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Field Visit Planning & Coordination | Committed | Fernando Torres <ftorres@dot.nv.gov> | 2 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Field Visit | New |  | 2 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Design Framework | New |  | 2 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 4 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Block Diagram | New |  | 2 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 2 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Internal Review | New |  | 2 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Internal Review Comments | New |  | 2 | 26 | 1 | 25 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | PS&E Coordination Efforts | New |  | 1 | 6 | 0 | 6 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review | New |  | 2 | 6 | 0 | 6 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Update Schedules & Structure List & Estimate | New |  | 1 | 6 | 0 | 6 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review Specifications | New |  | 2 | 6 | 0 | 6 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Doc Submittal | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address Changes From Submittal | New |  | 2 | 3 | 0 | 3 |  | FALSE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Doc Submittal | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 1 | 3 | 0 | 3 |  | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Update Fiber Trunk Design | Committed | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 26 | 5 | 21 | 2024-11-15 | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | RFI 36 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 27 | 27 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | 3-QUOTE- Compile and Submit | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 29 | 26 | 3 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | REV 7 Change Order | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 0.5 | 15.5 | 15.5 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Post-DOC | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | UPDATES TO REV 6 | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 4 | 29 | 29 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Field Visit and Plan Review | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 27 | 27 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Address CO comments | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 27 | 27 | 0 |  | FALSE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Modify Lighting Linework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 56.5 | 39 | 17.5 | 2024-09-17 | FALSE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS\2024 Sprint 12 | Professional Training for 1 Hour | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 5.5 | 5.5 | 0 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Initial Review of Site & Request Service Pedestal | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Framework | Committed | Fernando Torres <ftorres@dot.nv.gov> | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Create FHxx Sheets -1 | Committed | Fernando Torres <ftorres@dot.nv.gov> | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Framework | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Create FHxx Sheets -1 | Committed | Fernando Torres <ftorres@dot.nv.gov> | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Initial Review of Site & Request Service Pedestal | Done | Fernando Torres <ftorres@dot.nv.gov> | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Framework | Committed | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Create FHxx Sheets -1 | Committed | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Initial Review of Site & Request Service Pedestal | Committed | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 0 | 62 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 0 | 62 |  | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Update Schedules & Structure List | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | QA/QC Share review comments, Addressing share review comments and update design | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 7 | 7 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Additional Work | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 27 | 27 | 0 |  | FALSE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Framework | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Create FHxx Sheets -1 | Committed | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Initial Review of Site & Request Service Pedestal | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 2 | 60 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Framework | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Create FHxx Sheets -1 | Committed | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Initial Review of Site & Request Service Pedestal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 22 | Confirm QC comments on QAQC Internal Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 55.5 | 54.5 | 1 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Address Shared Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 51.5 | 51.5 | 0 |  | TRUE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 14 | Address Internal Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 2 | 42 | 39 | 3 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Lead designer review of Internal review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 35 | 35 | 0 |  | TRUE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Change Order 2 Pt. 2 | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 33.5 | 33.5 | 0 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Internal Review - QA/QC - 74204 | Done | Jordan James <jjames@dot.nv.gov> | 8 | 43 | 43 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Build Features & PBIs - Pete #4 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Build Features & PBIs - Austin #2 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Intermediate Submittal | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 12 | Internal Review- Address Lighting Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 12 | Field Site Visit 1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Create 3D Special Detail | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 51.5 | 51.5 | 0 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 12 | Confirm QC comments on QAQC Internal Review | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 76.5 | 67.5 | 9 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 12 | Update Conduit Schedule | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 67.5 | 67.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Framework Setup | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 4 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | UPRR @ Grade Xing/ ITS Special Details/ ITS General Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | ITS Design, Labeling, & Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Submit Service Pedestal Request (Lighting) | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0.5 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | ITS Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Sheet Layout, Cover sheet, Key Map, & Cut ITS sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Calculate Clearing & Grubbing/Seeding | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Lighting Design, Labels, & Construction Notes | Done | Jordan James <jjames@dot.nv.gov> | 8 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Sheet Layout, Cover sheet, & Cut LIGHTING sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Lighting Special Details/ Lighting General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Lighting Schedules | Done | Jordan James <jjames@dot.nv.gov> | 4 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Estimate & Submittal | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Comment on Intermediate Shared Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Address ITS Intermediate Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 19.5 | 19.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Address ITS Internal Review comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Update Framework Files from Roadway | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Address Lighting Internal Review comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 19.5 | 19.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Address Lighting Intermediate Review comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Comment on PS&E Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Address Lighting Internal QAQC Review comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Address Specs comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Address PS&E Review comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Address ITS Internal QAQC Review comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Structure List & Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Plot & Submit to Roadway | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Plot & Submit to Roadway | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Structure List & Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Confirm QC comments on Intermediate Internal Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Internal Review on Intermediate Submittal | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 4 | 43 | 43 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Confirm QC comments on QAQC Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 19.5 | 19.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Internal Review on QAQC Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 19.5 | 19.5 | 0 |  | FALSE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Framework Setup | New |  | 1 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Signal Design/ Signal Special Details/ Signal General Notes | New |  | 4 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Signal Design, Labeling, & Construction Notes | New |  | 2 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS\2021 Sprint 2 | Network Connection Analysis Request | New | Laura Vargo <lvargo@dot.nv.gov> | 0 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS\2021 Sprint 2 | Submit Service Pedestal Request (ITS & Lighting) | New | Laura Vargo <lvargo@dot.nv.gov> | 1 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Signal Schedules | New |  | 1 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Sheet Layout, Cover sheet, & Cut Signal sheets | New |  | 1 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Estimate & Submittal | New |  | 1 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Structure List | New |  | 1 | 17.5 | 0 | 17.5 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Submittal C3828 - 029 - 623.003 Pedestrian Push Button with Sign | Done |  |  | 70 | 70 | 0 |  | FALSE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | QAQC Design |  | Signals Lighting and ITS | Internal Review on Intermediate Submittal | New |  | 4 | 16.5 | 0 | 16.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | QAQC Design |  | Signals Lighting and ITS | Comment on Intermediate Review | New |  | 1 | 16.5 | 0 | 16.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | QAQC Design |  | Signals Lighting and ITS | Address Signal Intermediate Review Comments | New |  | 1 | 16.5 | 0 | 16.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | QAQC Design |  | Signals Lighting and ITS | Address Signal Internal Review comments | New |  | 4 | 16.5 | 0 | 16.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | QAQC Design |  | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 16.5 | 0 | 16.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | QAQC Design |  | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 16.5 | 0 | 16.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | DOC Design |  | Signals Lighting and ITS | Internal Review on QAQC Submittal | New |  | 2 | 9 | 0 | 9 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | DOC Design |  | Signals Lighting and ITS | Comment on PS&E Review | New |  | 1 | 9 | 0 | 9 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | DOC Design |  | Signals Lighting and ITS | Address Signal PS&E Review comments | New |  | 2 | 9 | 0 | 9 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | DOC Design |  | Signals Lighting and ITS | Address Signal Internal QAQC Review comments | New |  | 2 | 9 | 0 | 9 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | DOC Design |  | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 9 | 0 | 9 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | DOC Design |  | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 9 | 0 | 9 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Confirm QC comments on Intermediate Internal Review | New |  | 0.5 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | Intermediate Design |  | Signals Lighting and ITS | Internal Review on Intermediate Submittal | New |  | 4 | 17.5 | 0 | 17.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | QAQC Design |  | Signals Lighting and ITS | Confirm QC comments on QAQC Internal Review | New |  | 0.5 | 16.5 | 0 | 16.5 |  | TRUE
30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | On-Hold | QAQC Design |  | Signals Lighting and ITS | Internal Review on QAQC Submittal | New |  | 4 | 16.5 | 0 | 16.5 |  | TRUE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 14 | Check/Update Wildlife/Livestock flasher Details | Done | Jordan James <jjames@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract Q1-260-21-101 - Submittal 06 - Loop Detectors | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Submittal 3866; Caliente to Panaca ¦ Group 22 Electrical Submittal (Road and Weather Information System) 623.1115 | Done |  |  | 70 | 70 | 0 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Clearing and Grubbing/Seeding Calcs | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Shared Review Comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Accept/Reject Internal Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Update Linework | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 27.5 | 22.5 | 5 | 2024-11-27 | FALSE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Circuit Trace | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 67.5 | 67.5 | 0 |  | FALSE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 13 | Quantities for RRFB | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS | Preliminary Lighting Analysis | On-Hold | Jordan James <jjames@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS\2021 Sprint 12 | Asbuilt Creation | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0.5 | 36.5 | 35.5 | 1 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update ITS Structure List | New |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - ITS | New |  | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | SBX 3811 Submittal 008 - High Mast Pole | Done |  |  | 70 | 70 | 0 |  | FALSE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Lighting | New |  | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | LTP Comments Review - 75% | Done | Jordan James <jjames@dot.nv.gov> | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Signals | New |  | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Calculate Clearing & Grubbing/Seeding | Done | Jordan James <jjames@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | 75% Internal Review - Lighting | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide comments in NDOT shared review session | New |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address comments from NDOT shared review | New |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update ITS construction notes | New |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Signals Structure List | New |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Signals construction notes | New |  | 1 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Finish Signals linework | New |  | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | I80 Fiber Hut FAA Tower Application | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 51.5 | 51.5 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Intermediate Internal Review Accept/Reject Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 46 | 46 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | QAQC Internal Review Accept/Reject Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 28 | 28 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | QAQC Internal Review Address Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 28 | 28 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | QAQC Internal Review | Done | Brian Dodds <btdodds@dot.nv.gov> | 6 | 28 | 28 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | C 3842 Submittal: Radar Detector System | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Submittal #002 NDOT 3876 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Submittal #002 NDOT 3876 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | NDOT 3856 - 002 003 004 005 006 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | NDOT 3856 - 007 008 009 010 011 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | NDOT 3856 - 012 013 014 015 016 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | NDOT 3856 - 017 018 019 020 021 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | 3866 Group-6 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Compile and Submit Again | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | NDOT 3856 - 022 023 024 025 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Framework - 74373 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 15 | 15 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Preliminary design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 15 | 15 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Cut sheets & send to project team | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Complete OSC Forms | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 17 | 17 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Lighting construction notes | New |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Lighting Structure List | New |  | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review | New |  | 12 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTP Comments Review - QAQC | New |  | 1 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS comments from NDOT shared review | New |  | 1 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - ITS | New |  | 2 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Signals | New |  | 2 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Signals comments from NDOT shared review | New |  | 1 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Lighting | New |  | 2 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting comments from NDOT shared review | New |  | 1 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide comments in NDOT shared review session | New |  | 2 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Print PDF and Submit | New |  | 1 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 2 | 17 | 0 | 17 | 2022-07-18 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address comments from NDOT shared review | New |  | 2 | 17 | 0 | 17 | 2022-07-18 | TRUE
10994 | Done | Potential | C3833 - EA 73518 - Consultant Design - US-95 3D |  | Signals Lighting and ITS | Collect SLI Change Order info | Done | Jordan James <jjames@dot.nv.gov> | 1 | 49 | 49 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Update Fiber Design$ | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 90.5 | 90.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | FH31 Sheet updates | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | FH23 Sheet updates | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | FH30 Sheet Updates | Done | Jordan James <jjames@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | FH34 Sheet Updates$ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | FH36 Sheet Updates | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Update Existing ROW for ITS Design* | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Review Shared Review Set* - DID NOT GET WORKED ON | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Review special provisions | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | FALSE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 13 | Coordination with City of Fallon -3 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 13 | Internal- Compile Plan Set | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 14 | Decorative Lighting- Acorn Luminaire Selection | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 13 | Address Pending Comments from Internal Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 13 | Update QAQC Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 13 | Solar & Battery Calcs$ | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS | Estimate for Future RRFB | New |  | 2 | 76.5 | 67.5 | 9 |  | TRUE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Finalize CO#2 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Build Features & PBIs - Laura4 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Complete internal review of QAQC Submittal | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Address QAQC2 internal review comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 51.5 | 51.5 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Build Features & PBIs - Brenda2 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | 30% Design(Preliminary) |  | Signals Lighting and ITS\2021 Sprint 13 | Project Scoping | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 2 | 1 | 1 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS\2021 Sprint 13 | Transition to Rick | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 116.5 | 60.5 | 56 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Build Features & PBIs - Victoria4 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Comment on Standard Plans Shared Review - Jordan | Done | Jordan James <jjames@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Comment on Standard Plans Shared Review - Pete | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Comment on Standard Plans Shared Review - Victoria | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Comment on Standard Plans Shared Review - Laura | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Comment on Standard Plans Shared Review - Brenda | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Comment on Standard Plans Shared Review - Gurpreet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Comment on Standard Plans Shared Review - Austin | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | More changes to Conceptual Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | FH35 Sheet Update | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Voltage Drop Calcs | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 28 | 28 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Adjust lighting design - solar design & new geometry | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 6 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Update ITS design for new geometry | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Update General Notes for both sections | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Lighting Cutting Sheets | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Finish Intermediate Template | Done |  |  | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Finish QA/QC Feature of Template | Done |  |  | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Finish DOC Feature of Template | Done |  |  | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Finish Scoping Feature of Template | Done |  |  | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Finish Review Feature of Template - Victoria | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Finish Review Feature of Template - Laura | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Finish Review Feature of Template - Jordan | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Finish Review Feature of Template - Gurpreet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Finish Review Feature of Template - Brenda | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Finish Review Feature of Template - Austin | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Calculate seeding area | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 43 | 43 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Approve Internal Review Comments - QAQC2 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 51.5 | 51.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Updates to Special Provisions | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Update Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | ITS Design Coordination | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 28 | 28 | 0 |  | TRUE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Address Utility Conflicts - Check for aquisition or relocation needs | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 17 | 17 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Internal Review - Intermediate Signals | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Address ITS Internal Review Comments - Intermediate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Provide Comments in Intermediate Shared Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Update Schedules and Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Update Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | QCR Comments Approval - Intermediate | Done | Jordan James <jjames@dot.nv.gov> | 2 | 75.5 | 75.5 | 0 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Cut sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 15 | Framework | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 2 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address QAQC Shared Review Comments | New |  | 1 | 7.5 | 0 | 7.5 | 2026-12-21 | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Update Schedules and Structure List | New |  | 1 | 7.5 | 0 | 7.5 | 2026-12-21 | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 7.5 | 0 | 7.5 | 2026-12-21 | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 2 | 7.5 | 0 | 7.5 | 2026-12-21 | FALSE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | 74151 Address Review Comments | New |  | 2 | 8 | 0 | 8 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | 74151 Internal Review | New |  | 4 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 0.5 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule | New |  | 2 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & labels | New |  | 2 | 29 | 0 | 29 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Initial Review of Site & Request Service Pedestal | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Create FHxx Sheets -1 | Committed | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Framework | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 1 | 61 |  | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clean up schedules | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 2 | 34 | 2024-09-23 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 21 | 42 | 2 | 40 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Bring to 100% Design | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 29.5 | 17.5 | 12 |  | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Bring to 100% Design | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 31 | 12.5 | 18.5 | 2025-09-15 | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Updates based on Field Investigations - Conduit | Committed | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Updates based on Field Investigations - Pull Boxes | Done | Connie Ullas <cullas@dot.nv.gov> | 1 | 71 | 59 | 12 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Meeting with BLW | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 27 | 27 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Meeting with Jonna and Sean | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 27 | 27 | 0 |  | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Lighting Construction Notes | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 38 | 10 | 28 |  | TRUE
66927 | EA xxxxx / xxxxx - District 1 DMS and TTS panel replacements | Potential | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 38 | 10 | 28 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit 6/10 - 6/13 | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit 6/10 - 6/13 | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit 6/10 - 6/13 | Done | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit 6/10 - 6/13 | Done | Connie Ullas <cullas@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit 6/10 - 6/13 | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit 6/10 - 6/13 | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit 6/10 - 6/13 | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | 3-Quote--Internal Review | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | ITS Linework Updates | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Confirm QC Comments | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 29 | 26 | 3 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Additional SLI Changes | Done | Brittany Brickman <bbrickman@dot.nv.gov> | 4 | 27 | 27 | 0 |  | FALSE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Doc3 plot & Submit | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 2 | 2 | 0 |  | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Electrical Service Requests | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 57 | 33 | 24 | 2025-03-01 | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit 6/10 - 6/13 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Field Visit 6/10 - 6/13 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Historical Documentation Search | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 146 | 133 | 13 |  | FALSE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | Electrical Service Justification Letter | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Ph. 2 Signal IMD Design | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 42 | 2 | 40 |  | FALSE
52656 | Staff Training | Potential | 2024 Professional Training |  | Signals Lighting and ITS\2024 Sprint 14 | Professional Training for 1 Hour | Done | Connie Ullas <cullas@dot.nv.gov> | 0.5 | 5.5 | 5.5 | 0 |  | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | ITS Keymap | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 14 | ITS Cut Sheets | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Change Order #1 | Committed | Pete Rosenberg <PRosenberg@dot.nv.gov> | 3 | 9.5 | 6.5 | 3 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Collapsible RWIS Tower Detail | New |  | 2 | 37.5 | 0 | 37.5 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Service Pedestal and Communication Cabinet Historical Doc Search at Jean Interchange | Committed | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Ph2 Temp Signal - PBI 1 | Committed | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 11 | 1 | 10 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Ph2 Temp Signal - PBI 2 | Committed | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 11 | 1 | 10 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Ph2 Temp Signal - PBI 3 | Committed | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 11 | 1 | 10 |  | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | ITS SCHEDULES UPDATE | Committed | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | 3 Quote IMD Internal Review Accept/Reject Comments | Committed | Alex Traeger <atraeger.ctr@dot.nv.gov> | 1 | 29 | 26 | 3 |  | FALSE
39835 | Miscellaneous Items | Actively Working | 3-quotes 2023 | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | 3 Quote- IMD Internal Review Address Comments | Committed | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 29 | 26 | 3 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | IMD 3 Internal Review - ITS | Committed | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | IMD 3 Internal Reivew Accept/Reject Comments | Committed | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | IMD 3 Internal Review - ITS Address Comments | Committed | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | IMD 3 Internal Review Signals & Lighting Address Comments | Committed | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | 95% Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | IMD 3 Internal Reivew - Signals and Lighting | Committed | Alex Traeger <atraeger.ctr@dot.nv.gov> | 2 | 71 | 59 | 12 |  | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Update signal linework and keymap and cut sheets | Committed | Shaza Elshazli <selshazli@dot.nv.gov> | 4 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Update & send SP request | New |  | 1 | 57 | 33 | 24 | 2025-03-01 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 15 | Lighting schedules and Structure list | Committed | Shaza Elshazli <selshazli@dot.nv.gov> | 2 | 78.5 | 56 | 22.5 | 2025-01-13 | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 1 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 1 | 29 | 0 | 29 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Address Internal Review Comments | On-Hold |  | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Address Internal Review Comments | On-Hold |  | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Address Internal Review Comments | On-Hold |  | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Address Internal Review Comments | On-Hold |  | 4 | 116.5 | 60.5 | 56 |  | TRUE
10994 | Done | Potential | EA 74272 Pyramid Highway Widening Project |  | Signals Lighting and ITS | Address Internal Review Comments | On-Hold |  | 4 | 116.5 | 60.5 | 56 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | ITS Construction Notes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | ITS General Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Address Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 5 | 5 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | ITS Schedule | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | ITS Cleanup | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | ITS Cover/Key Map | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | ITS Special Details | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | IR Lead review comments - QA/QC | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Signal Coversheet | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | General Notes | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Signal Design | New |  | 2 | 35 | 0 | 35 |  | TRUE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | QA/QC - Internal Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 13 | 13 | 0 |  | FALSE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Framework | New |  | 2 | 35 | 0 | 35 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | 30% Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | PDFS Report | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | QA/QC - Address Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Estimate | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Structure List | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Compile and Submit | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Signal Plan | New |  | 2 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Schedules | New |  | 2 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Special Details | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Construction Notes | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Address Internal review Comments | New |  | 2 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Review special provisions | New |  | 1 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Address Intermediate shared review comments | New |  | 2 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Check schedules and structure list | New |  |  | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Update estimate | New |  | 1 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Compile and submit | New |  | 1 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | 30% Design(Preliminary) |  | Signals Lighting and ITS | Project Scoping _New Signalosed Intersection | New |  | 1 | 2 | 1 | 1 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | DOC Design |  | Signals Lighting and ITS | Review shared set plans | New |  | 2 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | DOC Design |  | Signals Lighting and ITS | Review special provisions | New |  | 1 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | DOC Design |  | Signals Lighting and ITS | Address Intermediate shared review comments | New |  | 2 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | DOC Design |  | Signals Lighting and ITS | Update estimate | New |  | 1 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | DOC Design |  | Signals Lighting and ITS | Compile and submit | New |  | 1 | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | DOC Design |  | Signals Lighting and ITS | Check schedules and structure list | New |  |  | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Plans | New |  | 2 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | General Notes | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Special Details | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Design | New |  | 2 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | ITS Coversheet | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Schedules | New |  | 2 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Construction Notes | New |  | 1 | 35 | 0 | 35 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | QCR Comments Approval - Intermediate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Internal Review - Intermediate ITS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Provide Comments in Shared Review - Intermediate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Framework - 74361 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Lighting Cutting Sheets | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Lighting Cover/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Lighting Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Lighting Linework/Labels | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 4 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Lighting General Notes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 0.5 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Lighting Construction Notes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 46.5 | 45.5 | 1 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Submittal. 3866; Caliente to Panaca ¦ RFI007, SBMT 080, & SBMT 081 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | FW: 3866 Group 6 Submittals | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Service Pedestal Research | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 43 | 43 | 0 |  | FALSE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  | 4 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate - Address Review Comments | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC - Internal Review | New |  | 2 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intl approval QA/QC - Lead designer review of comments | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Scope Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address comments from Intermediate reviews | New |  | 2 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Complete Schedule population | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List - 74361 | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate - 74361 | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Specs Revisions | New |  | 2 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit - 74361 | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List - 74360 | New |  | 1 | 12 | 0 | 12 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate - 74360 | New |  | 1 | 12 | 0 | 12 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review Specifications | New |  | 2 | 12 | 0 | 12 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit - 74360 | New |  | 2 | 12 | 0 | 12 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 14 | Lighting Design Updates at US50/ Sherman | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Structure List & Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 46.5 | 45.5 | 1 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Framework - 74151 | Approved |  | 4 | 29 | 0 | 29 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 14 | Schedules- Update | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate - 74204 | New |  | 1 | 8 | 0 | 8 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit - 74204 | New |  | 1 | 8 | 0 | 8 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Update General Notes for both sections | New |  | 1 | 8 | 0 | 8 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Check need for seeding | New |  | 1 | 8 | 0 | 8 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address comments from PS&E review | New |  | 2 | 8 | 0 | 8 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit - 74204 | New |  | 1 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List - 74204 | New |  | 1 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate - 74204 | New |  | 1 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | PS&E Review & Comments | New |  | 2 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Internal Review - QA/QC - 74204 | New |  | 6 | 29 | 0 | 29 |  | TRUE
7452 | EA 74151 - I-80 & Mote Road (3R) | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New |  | 1 | 29 | 0 | 29 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 14 | Structure List & Estimate Update | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 14 | Coordination with City of Fallon -4 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 76.5 | 67.5 | 9 |  | TRUE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | 30% Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | SP Search | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 16 | Review Special Provisions | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 76.5 | 67.5 | 9 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Trench Detail Updates | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 81 | 81 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Assess SP Requirements | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Revise design - only Beatty DMS work to remain | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 35 | 1 |  | FALSE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Compile & submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 36 | 35 | 1 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Address minor GENERAL comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Address minor SIGNALS comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Address minor LIGHTING comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Address minor ITS comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
10994 | Done | Potential | EA 74164 - US-95/Amargosa Valley |  | Signals Lighting and ITS\2021 Sprint 14 | Calculate Seeding | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 42 | 39 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Intermediate Design Conflict Efforts | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | Provide Comments QA/QC Internal Review | Done | Connie Ullas <cullas@dot.nv.gov> | 2 | 17 | 14 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 0 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 17 | 14 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Confirm QC Comments on Intermediate Internal Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Confirm QC Comments on QA/QC Internal Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 17 | 14 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | Address Internal Review Comments | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 17 | 14 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Lighting Linework & Labels | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Intermediate Review Utility and UPRR Conflicts | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 0.5 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 21 | QA/QC Compile and Submit | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 17 | 14 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Intermediate Estimate | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Intermediate Structure List | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | Intermediate Compile and Submit | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 25.5 | 25.5 | 0 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\2021 Sprint 22 | Address PS&E Shared Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\2021 Sprint 22 | DOC Structure List | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\2021 Sprint 22 | DOC Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\2021 Sprint 23 | DOC Compile and Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 45.5 | 44.5 | 1 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | PDFS Report | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Scoping KMZ | On-Hold |  | 4 | 43.5 | 6 | 37.5 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Lighting Intermediate Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 6 | 25 | 25 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Confirm QC comments on Intermediate Internal Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 25 | 25 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | PS&E Shared Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 25 | 25 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | QA/QC Conflict Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 25 | 25 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Create Block Diagram | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 9.5 | 9.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Lighting Voltage Drop | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Lighting Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Lighting Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Lighting Construction Notes | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Lighting General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Lighting Linework & Labels | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 4 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Cutting Lighting Sheets | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | ITS Construction Notes | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | ITS General Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | ITS Schedule | Done | Jordan James <jjames@dot.nv.gov> | 2 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | ITS Cover/Key Map | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | ITS Special Details | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Cutting ITS Sheets | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | ITS Linework & Labels | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Intermediate Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Intermediate Structure List | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Intermediate Compile and Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 31.5 | 31.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Lighting Address Internal Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 25 | 25 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | ITS Address Internal Review Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 25 | 25 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | QA/QC Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 25 | 25 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | QA/QC Structure List $ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 25 | 25 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | QA/QC Compile and Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 25 | 25 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Address Shared Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 9.5 | 9.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | DOC Structure List | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 9.5 | 9.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | ITS Devices Added to Spreadsheet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 9.5 | 9.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | DOC Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 9.5 | 9.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | DOC Compile and Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 9.5 | 9.5 | 0 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 15 | Luminaires at Tedford Ln | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 4 | 76.5 | 67.5 | 9 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | NDOT 3833 623N-084 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | NDOT 3843 Submittal Nos. 148 through 160 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | NDOT 3876 Submittal #3 Valmont Poles | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3856 - 002,003,004,005 Resubmittals | Done |  | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Submittal 013 NDOT 3860 Pull Boxes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
42439 | C 3881 - EA 74276/60935 - Logandale to Mesquite | DOCed | C3881/EA 74276/60935 - Logandale to Mesquite | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | C3881 BRAT Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 31 | 31 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | General Notes Master Sheet | New |  |  | 146 | 133 | 13 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 15 | Foundation Special Detail | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 32 | 32 | 0 |  | FALSE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 15 | Luminaire Selection for AGI32 Analysis$ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 76.5 | 67.5 | 9 |  | TRUE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 15 | Update Sheet Numbers | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 32 | 32 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 15 | DOC Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0.5 | 32 | 32 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Address minor SIGNALS comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Address minor ITS comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Address minor GENERAL comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Address minor LIGHTING comments | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | General Notes & Details - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 14.5 | 14.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Schedules - Lighting Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 14.5 | 14.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Construction Notes - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 14.5 | 14.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Linework & Cut Sheets - Lighting Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 14.5 | 14.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Lighting Coversheet/Key Map | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 14.5 | 14.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Framework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 14.5 | 14.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Address Intermediate Shared Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 14.5 | 14.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Compile and Submit | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 14.5 | 14.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Update Estimate & Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 14.5 | 14.5 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | DOC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Provide PS&E Shared Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 2 | 3.5 | 3.5 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Provide Intermediate-2 Shared Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 28 | 28 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Confirm QC comments on QAQC-2 Internal Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0.5 | 10.5 | 10.5 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | QAQC-2 Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 10.5 | 10.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | 30% Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | PDFS Report | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Structure List, Estimate, Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | NDOT 3866 Group 6 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Standard Plan Coordination | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Standard Plan Coordination | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 81 | 81 | 0 |  | FALSE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Intermediate Internal Review Address Lighting Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 28 | 28 | 0 |  | TRUE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Design Coordination | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 14.5 | 14.5 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Review New Details & Provide Markups | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | New Detail Revisions | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 81 | 81 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Update IPD estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Address QAQC2 shared review comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 6 | 51.5 | 51.5 | 0 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Update Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | Update ITS Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 66.5 | 65.5 | 1 |  | FALSE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Build Features & PBIs | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 9 | 9 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Confirm QC Comments on PS&E Shared Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 17 | 14 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Confirm QC Comments on Intermediate Shared Review | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | Clearing and Grubbing/Seeding | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 25.5 | 25.5 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Pothole Locations | Done | Jordan James <jjames@dot.nv.gov> | 6 | 75.5 | 75.5 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | NEW DETAIL - AC Driver Feedback Sign | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | NEW DETAIL - Solar Driver Feedback Sign | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Address comments from review w/ Rod | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Review and update ITS Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Lighting Sheet cleanup | Done | Jordan James <jjames@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 15 | MODIFIED - SLI Conduit Trench Detail | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | New Service request | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Confirm QC comments on Intermediate Internal Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0.5 | 66.5 | 65.5 | 1 |  | FALSE
10994 | Done | Potential | EA 74267 - EA 74030 - I-515 & Charleston Interchange |  | Signals Lighting and ITS | QA/QC review | On-Hold |  | 8 | 11 | 3 | 8 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Add 2 speed feedback signs for Topaz - 74239 | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Add crosswalk lighting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | NDOT 3843 Submittal 169-180 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | NDOT 3843 Submittal 181-195 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | NDOT 3843 Submittals 196-203 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | NDOT 3876 Group 8 Submittal 005 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | NDOT 3876 Submittal 004 Group 3 Pull Boxes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | 30% Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Field Visit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
10994 | Done | Potential | EA 74350 - SR 613 Summerlin Parkway, Las Vegas Nevada, 3R project |  | Signals Lighting and ITS\2021 Sprint 16 | Compare Preservation report with SLI scope | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 3 | 3 | 0 |  | TRUE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Contract Search for RR crossing @ SR-160 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Add more general notes for lighting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 18.5 | 18.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Voltage drop calcs and panel schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 43 | 43 | 0 |  | FALSE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Service Pedestal Request | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 3 | 3 | 0 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Develop Scope | Done | Jordan James <jjames@dot.nv.gov> | 1 | 3 | 3 | 0 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | PDFS Report | Done | Jordan James <jjames@dot.nv.gov> | 1 | 3 | 3 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Compile & Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Structure List & Estimate | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Review VE Report | Done | Jordan James <jjames@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | ITS Cover Sheet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | TRUE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Update Plot set | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Create FHxx Sheets - 2 | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | TRUE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | UPRR Responses | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 28 | 28 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | MODIFIED- Ped Push Button Extension Detail | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 81 | 81 | 0 |  | FALSE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Plan sheet and Detail Sheet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Clearing and Grubbing/Seeding Calculations | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | QAQC Internal Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 6 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | QAQC Internal Review Accept/Reject Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | TRUE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Address QAQC Internal Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 7 | 7 | 0 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC2 set for internal review | On-Hold |  |  | 36 | 35 | 1 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Intermediate ITS Internal Review | Done | Jordan James <jjames@dot.nv.gov> | 6 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Provide Intermediate Shared Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Confirm QC Comments on IMD IR | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 74 | 74 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | QAQC2 Internal Review | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 8 | 51.5 | 51.5 | 0 |  | TRUE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Intermediate Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 16 | Lighting Plan Sheets - Intermediate - 74341 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 16 | 16 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | DOC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Update NVE service entrance design to the new and existing service pedestals | Done | Jordan James <jjames@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Service Requests | New |  |  | 40 | 38 | 2 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Structure List Plotting Troubleshooting | New |  | 1 | 146 | 133 | 13 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Integrate ITS Topo on SR-431 | Approved | Laura Vargo <lvargo@dot.nv.gov> | 4 | 15 | 7 | 8 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | 3792 Submittal No. 0398 Gator Patch | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Add 4th Leg to Intersection | Done | Jordan James <jjames@dot.nv.gov> | 2 | 25.5 | 25.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | FW: NDOT 3863 Submittal set #7 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | NDOT 3843 Submittal 207 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | NDOT 3856 S. No. - 35, 36, 37 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | 3866 Submittal - No. 10 THW Wire | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | Split Project | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 121 | 25 | 96 | 2022-04-25 | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 17 | As-built search for Lighting at Bowers Interchange | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 17 | 17 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Lighting Sheet Cutting | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 74 | 74 | 0 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\2021 Sprint 17 | Address Spec's Comments on Intermediate Submittal | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 22 | Confirm QC Comments on QA/QC Shared Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 22 | Provide PS&E Shared Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\2021 Sprint 21 | Address Spec Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | ITS Linework/Labels | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | ITS Schedules | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | ITS Special Details | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | ITS General Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | ITS Cover/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | ITS Cutting Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | ITS Construction Notes | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Service Pedestal Request | Done | Jordan James <jjames@dot.nv.gov> | 2 | 43.5 | 6 | 37.5 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Atkins response to NDOT comments | Done | Eric Macgill <emacgill@dot.nv.gov> |  | 17 | 17 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Move SP location at Apex Interchange | Done |  | 2 | 90.5 | 90.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Lighting Voltage Drop$ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 74 | 74 | 0 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Special Details | Approved |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Signal Linework/Labels | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Signal Schedules | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Signal Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Signal General Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Signal Cutting Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Signal Cover/Key Map | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Intermediate Plan Review - 1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 17 | 17 | 0 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Intermediate Plan Review - 2 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 17 | 17 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & labels | Done |  | 4 | 21 | 21 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | ITS Sheet Creation | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 21 | 21 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Lighting Linework and Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Lighting Sheet Creation | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Print and submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 21 | 21 | 0 |  | TRUE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Coordinate with Signs & Traffic Analysis | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Framework | New |  | 4 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Initial Project research | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Respond to Request for project support | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Intermediate Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Lead designer review internal review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 16 | 16 | 0 |  | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Build Features & PBIs | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Internal Review - Intermediate Lighting | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 46.5 | 45.5 | 1 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS cleanup | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address comments from PS&E review | New |  | 1 | 12 | 0 | 12 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address comments from Intermediate review | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal cleanup | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Complete Schedule population | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address comments from PS&E review | New |  | 1 | 12 | 0 | 12 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address comments from PS&E review | New |  | 1 | 12 | 0 | 12 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS cleanup | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Address comments that have not already been completed in the original shared review | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Update Trench Detail in DOC Plans | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 25.5 | 25.5 | 0 |  | FALSE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | 30% Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Upload SP Photos to AMP | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 1 | 8 | 8 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | AGI32 Lighting Analysis - Setup | Done | Jordan James <jjames@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Adjust trunkline based on new information | Done | Jordan James <jjames@dot.nv.gov> | 4 | 41 | 41 | 0 |  | TRUE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\2021 Sprint 19 | Comment on PS&E Shared Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | 3860 Submittal 021 - Sent to TOTS | Done |  |  | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | 3860 Submittal 022 | Done |  | 0.5 | 70 | 70 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | ITS Coversheet/Key Map | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Cut sheets - ITS Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Construction Notes - ITS Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Structure List - ITS Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Estimate- ITS Design | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 18 | Linework - ITS Design | Done | Jordan James <jjames@dot.nv.gov> | 4 | 75.5 | 75.5 | 0 |  | FALSE
10994 | Done | Potential | EA 74350 - SR 613 Summerlin Parkway, Las Vegas Nevada, 3R project |  | Signals Lighting and ITS\2021 Sprint 19 | Bid Item List | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 3 | 3 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Priority 8, 15 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Priority 3-5 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Priority 1-2 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Priority 11, 17 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Priority 5-7 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Priority 1-4 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Priority 8-10 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Priority 6, 8 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Priority 1, 7 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Priority 12, 18 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Priority 11, 14 | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Priority 12-13 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Priority 9 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Address UPRR comments | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Program Project | New |  | 0 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | 74302 Send Details to UPRR | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Email R/W Util. for UPRR | New |  | 1 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Bridge Conduit Detail | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Intermediate Schedules | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Intermediate Design | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Compile and Submit | New |  | 1 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Address Intermediate Internal Review Comments | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Traffic Control Design | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Compile and Submit | New |  | 1 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Update Estimate | New |  | 1 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Confirm QC comments on Intermediate Internal Review | New |  | 0.5 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Confirm QC comments on QAQC Internal Review | New |  | 0.5 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Intermediate Internal Review | New |  | 4 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | QAQC Internal Review | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Address QAQC Internal Review Comments | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Address Shared Review Comments | New |  | 2 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Compile and Submit | New |  | 1 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Update Estimate | New |  | 1 | 34 | 0 | 34 |  | FALSE
10990 | On Hold | Potential | EA xxxxx - I-15 UPRR Crossing (make project level when needed) |  | Signals Lighting and ITS | Update Estimate | New |  | 1 | 34 | 0 | 34 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Pull Box Submittal Jensen | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lead designer review of comments - Intermediate | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Cut Sheets - Signals | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Cut Sheets - Lighting | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Cut Sheets - ITS | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Service Pedestals | New |  |  | 7.5 | 7.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Develop Scope & PDFS Report | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 7.5 | 7.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Quantify Scope Items and Add Pricing | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 7.5 | 7.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Confirm QC Comments on PS&E Shared Review (need A/C review) | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 12 | 12 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Provide PS&E Shared Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Provide Comments IMD IR ITS | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Provide IMD SR Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Confirm QC Comments on IMD IR | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Update LMA Callouts | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | CO #3 Design Changes (PBI 3.1/5) | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 33.5 | 33.5 | 0 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Submit to plans to specifications | Done | Eric Macgill <emacgill@dot.nv.gov> |  | 28 | 28 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Plot updated Planset | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 81 | 81 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | NDOT 3843 Submittal No. 220 Pedestrian Signal Mount Pole Top | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Update Underdeck design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 72.75 | 72.75 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Update Project Number | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | Review Pothole Locations | Done | Jordan James <jjames@dot.nv.gov> | 1 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | 75% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Update Signals Structure List | Done | Jordan James <jjames@dot.nv.gov> | 2 | 3 | 3 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Scoping Effort Check | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | EA 73932/60750 - US-50 Down Town Fallon Improvements |  | Signals Lighting and ITS\2021 Sprint 20 | BRAT Review | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 2 | 76.5 | 67.5 | 9 |  | TRUE
45236 | C 3886/EA 74250 - US-50 Roadway Horse Lighting | DOCed | C3886/EA 74250 - US-50 Roadway Horse Lighting | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 19 | BRAT Report Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 67.5 | 67.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Adjust high mast pull box detail | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.25 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Adjust Lighting Linework and Labels | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Coordinate with other Design Sections | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 51.5 | 51.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | NDOT 3863 Submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 70 | 70 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Fix conduit schedules | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 90.5 | 90.5 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 20 | Cut Sheets2 - ITS | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Internal Review - Intermediate Lighting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 6 | 75.5 | 75.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | Intermediate Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Internal Review - Intermediate ITS | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 75.5 | 75.5 | 0 |  | FALSE
56363 | C 3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) | DOCed | C3889 - EA 74243 - EA 61005 - US-95 3R (HU MM 31 - 74) |  | Signals Lighting and ITS\2021 Sprint 20 | Complete SLI Supplemental #1 | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 0.5 | 32 | 32 | 0 |  | FALSE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Create Scoping Template | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Priority 6-7 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Priority 9, 13 | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Priority 10, 16 | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Priority 2-3 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Priority 4-5 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Address QAQC Shared Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Priority 14 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 22 | Adjust Signal SP per NVE LEA | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Update quantities based on revised limits. | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 8 | 8 | 0 |  | TRUE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels | New |  | 6 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedules | New |  | 6 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 4 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Service request - replace overhead power | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Gather existing Service Pedestal Info | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Solar Site Design (evaluate possible A/C?) | Done | Jordan James <jjames@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Voltage Drop Calcs | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Complete ITS Schedules | Done | Jordan James <jjames@dot.nv.gov> | 6 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Block Diagrams and Special Details | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Create Power One-Line Diagrams | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 101.5 | 101.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Submittal Review Request for NDOT Contract 3833 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | NDOT 3860 Submittal 0027 | Done | Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General Notes | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedule & Structure List | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Cutting Sheets | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Special Details | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  | 8 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 0.25 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 6 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels (check PMP) | New |  | 6 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Voltage Drop | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedule & Structure List | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cutting Sheets | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & Labels | New |  | 6 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit (review A/C) | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 12 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 0.5 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team Coordination Meeting | New |  | 0.5 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 1 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | TOTs Coordination | New |  | 0.5 | 85.25 | 0 | 85.25 | 2022-11-14 | TRUE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Lighting Sheet Cutting | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Provide comments intermediate internal review | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Confirm QC Comments on Intermediate Internal Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 20.5 | 20.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Address comment | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 20.5 | 20.5 | 0 |  | FALSE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Field Visit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 17 | 17 | 0 |  | TRUE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | Intermediate Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 5 | 57 | 2023-01-30 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | DOC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate - 74385 | New |  | 2 | 16 | 0 | 16 | 2023-10-23 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | DOC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit - 74385 | New |  | 2 | 16 | 0 | 16 | 2023-10-23 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | DOC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Structure List - DOC - 74385 | New |  | 2 | 16 | 0 | 16 | 2023-10-23 | FALSE
33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | On-Hold | DOC Design | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Doc Specs Revisions | New |  | 2 | 16 | 0 | 16 | 2023-10-23 | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Internal Review - Intermediate Signals | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 72.75 | 72.75 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Internal Review - Intermediate Lighting | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 6 | 72.75 | 72.75 | 0 |  | FALSE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 21 | Review Bid Items | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 90.5 | 90.5 | 0 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | QAQC Plan Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 81 | 81 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Review 2022 Standard Plans Shared Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 81 | 81 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | SUE conflict search | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 35 | 35 | 0 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 2 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 1 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 14 | 0 | 14 | 2023-05-06 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 14 | 0 | 14 | 2023-05-06 | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team Coordination Meeting | New |  | 0.5 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 12 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lead Designer Accept/Reject Comments - IR Intermediate | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General Notes | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Cutting Sheets | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels | New |  | 6 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedule & Structure List | New |  | 6 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Special Details | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 0.25 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  | 8 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels (check PMP) | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cutting Sheets | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | TOTs Coordination | New |  | 0.5 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Voltage Drop | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & Labels | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedule & Structure List | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit (review A/C) | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 2 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 14 | 0 | 14 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Move SP and Add 20Ft Gate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\2021 Sprint 22 | Provide comments on PS&E Shared Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\2021 Sprint 22 | Lighting Address PS&E Shared Review Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\2021 Sprint 22 | DOC Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\2021 Sprint 22 | DOC Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 54.5 | 54.5 | 0 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\2021 Sprint 22 | DOC Compile and Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 54.5 | 54.5 | 0 |  | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New | Jordan James <jjames@dot.nv.gov> | 1 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | 75% Internal Review - Signals | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 121 | 25 | 96 | 2022-04-25 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | 75% Internal Review - ITS | Done | Laura Vargo <lvargo@dot.nv.gov> | 6 | 121 | 25 | 96 | 2022-04-25 | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RRFB removal from plans | New |  | 1 | 26.5 | 0 | 26.5 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Labels & linework | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Detail Sheets | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plan sheets | New |  | 4 | 16 | 0 | 16 | 2030-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plans & Schedules | New |  | 4 | 16 | 0 | 16 | 2030-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Circuit Analysis | New |  | 2 | 16 | 0 | 16 | 2030-01-01 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Comments from Intermediate reviews | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Internal Review - QA/QC set | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address comments from PS&E & Internal Reviews | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Placeholder PBI | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC StructList & Estimate | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New |  | 2 | 16 | 0 | 16 | 2030-01-01 | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | NDOT 3843 Submittal #187-1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Submittal review request NDOT Contract 3833 623N-92-1 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
16329 | DOC'ed | Potential | Fiber Hut US-50 East of SR-439 |  | Signals Lighting and ITS | Update Service Panel Schedule load calcs | New |  | 1 | 36.5 | 35.5 | 1 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | 3881 6230000 Electrical Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | 3881 6230000 Electrical Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | ITS One-line Diagrams | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
50278 | C 3892 - EA 74215 & 74162 / 60992 & 60993 - I-15 N. Ph3 (Speedway to Garnet) | DOCed | Design for I-15 N. Ph3 (Speedway to Garnet) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 22 | Supp 2 Revisions | Done | Jordan James <jjames@dot.nv.gov> | 8 | 90.5 | 90.5 | 0 |  | TRUE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | 30% Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Send SP Request | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | FALSE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Update Intermediate Plans | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 13.5 | 13.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Update Intermediate Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 13.5 | 13.5 | 0 |  | TRUE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Redesign trunkline based on new conduit standards & SUE work | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 56 | 56 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | NDOT 3843 Submittal 187-2 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 14 | Submittal 00623-044 & 45 - NDOT 3856 | Done |  | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | RE: 3881 6230000 Electrical Submittal (1 of 2) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Intermediate Lighting Internal Review | Done | Jordan James <jjames@dot.nv.gov> | 6 | 74 | 74 | 0 |  | TRUE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | DOC Internal Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 66.5 | 65.5 | 1 |  | FALSE
44587 | C 3907 - EA 74349 - I-80, Humboldt County Nevada, 3R project | DOCed | IMD/QAQC/DOC Design Submittals | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Address DOC Internal Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 66.5 | 65.5 | 1 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Address Intermediate Shared Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | DOC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 23 | Update DOC design | Done | Jordan James <jjames@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Integrate ITS Topo on SR-28 | New |  | 4 | 15 | 7 | 8 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Adjust design based on SUE | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | QAQC Comments Addressed | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 81 | 81 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | NDOT 3843 Submittal 207 Vehicle Detection Loop | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | NDOT 3843 Submittal 241 IISNS Strain Relief | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | 30% Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | 30% Design in KMZ file | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | 30% Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Send Service Pedestal Request | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 21 | 21 | 0 |  | TRUE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Provide PS&E Shared Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Confirm QC Comments on QA/QC Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Provide Comments QA/QC Internal Review | Done | Jordan James <jjames@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Lighting Voltage Drop$ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Lighting Cover/Key Map | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Lighting Schedule & Structure List | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Lighting Construction Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Lighting General Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Lighting Linework & Labels | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Lighting Cutting Sheets | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | ITS Construction Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | ITS General Notes | Done | Jordan James <jjames@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | ITS Schedule & Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | ITS Cover/Key Map | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | ITS Special Details | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | ITS Cutting Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | ITS Linework & Labels | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | QA/QC Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | QA/QC Check Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | QA/QC Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | ITS Address Review Internal Comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 8 | 8 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Lighting Address Shared Review & Specs Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 8 | 8 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Lighting Address Internal Review Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 8 | 8 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | ITS Address Shared Review & Specs Comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 8 | 8 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | DOC Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 8 | 8 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | ITS Devices Added to Spreadsheet | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 8 | 8 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | DOC Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 8 | 8 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | DOC Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 8 | 8 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Framework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 35.5 | 35.5 | 0 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts - needs a/c | New |  | 0 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 0 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review Utility and UPRR Conflicts | New |  | 0 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Lighting Voltage Drop | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Cover/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | Special Details | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Schedule & Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Construction Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 23 | General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | Lighting Linework & Labels (check PMP) | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 1 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 16 | RWIS Linework & Labels (check PMP) | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 29.5 | 17.5 | 12 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Review Intermediate Specs Comments | Done | Jordan James <jjames@dot.nv.gov> | 1 | 72.75 | 72.75 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Lighting Spots & Dots | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 7.5 | 7.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Signal Spots & Dots | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 7.5 | 7.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | ITS Spots & Dots | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 7.5 | 7.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | 30% Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Design Framework | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 7.5 | 7.5 | 0 |  | FALSE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | QA/QC Submittal | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 24 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Provide PS&E Shared Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | QAQC Internal Review | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 13 | 13 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | IMD Lead respond to comments on Shared Review | Done |  | 1 | 23 | 23 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | IR Lead review comments - QA/QC | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 13 | 13 | 0 |  | FALSE
58530 | Scoping - Biennial District Scoping Process | Actively Working | Scoping - Biennial District Scoping Process 2021 | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Priority 15 (Added Scope) | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 66 | 66 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Address Specs Comments on ITS section of Intermediate Submittal | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Address Specs Comments on Lighting section of Intermediate Submittal | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | TRUE
16329 | DOC'ed | Potential | EA 73650 - Ely CMAR Road Reconstruction Project |  | Signals Lighting and ITS | Change Order #? | New |  |  | 94 | 94 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal | New |  | 0 | 25.5 | 25.5 | 0 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 17 | 14 | 3 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Supplemental #1 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 35 | 1 |  | FALSE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Compile and Submit QAQC2 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 10.5 | 10.5 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Compile and Submit | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 51.5 | 51.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Jensen Pull Boxes Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | 30% Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | 74374_Framework Setup $ | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | Post-DOC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Supplemental 1 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 4 | 4 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 25 | Review of current specs to see if updated specs are needed $ | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 51.5 | 51.5 | 0 |  | TRUE
27391 | C 3988 - EA 74352- EA 69962 - US-395 fm Cold Springs to State Line, Mill and Overlay | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Comment on Intermediate Shared Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 46 | 46 | 0 |  | TRUE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Doc Submittal - 74341 | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Intl. QA/QC approval - Lead designer response to QA/QC internal review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 9 | 9 | 0 |  | FALSE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Battery Backup system. | New |  | 2 | 26.5 | 0 | 26.5 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | SP Design Review from NVE | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 29.5 | 29.5 | 0 |  | TRUE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | QA/QC address review comments | Done | Brian Dodds <btdodds@dot.nv.gov> | 2 | 14 | 14 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | DOC Lighting Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Address IMD review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 17 | 17 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Intl. QA/QC approval - Lead designer respond to QA/QC internal review comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15.5 | 15.5 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Intl QA/QC Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 24 | ITS cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | ITS Schedules - Migration & update $ | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 27 | 27 | 0 |  | TRUE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | Lighting Schedules - Verification/Cleanup | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 27 | 27 | 0 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2021 Sprint 25 | Supplemental | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 55.5 | 54.5 | 1 |  | TRUE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Intl. IMD Review - Intermediate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 17 | 17 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Intl IMD approval - Lead designer respond to comments - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 17 | 17 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Cover/Key Map | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 23 | 23 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Lighting Construction Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 23 | 23 | 0 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | 30% Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | KMZ to Cultural | Done | Jordan James <jjames@dot.nv.gov> | 2 | 2 | 2 | 0 |  | FALSE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | ITS Design Changes | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 31.5 | 31.5 | 0 |  | TRUE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Search DGN files to find relevant mapping | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 36 | 36 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Create Schedules - Signals | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 6 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Update Structure List - Signals | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Update Estimate- Signals | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Finish Linework and Labels - Signals | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Update Schedules - Lighting | Done | Jordan James <jjames@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Update Estimate - Lighting | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Update Construction Notes - Lighting | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | General Notes - Lighting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Update Structure List - Lighting | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Update Lighting Coversheet/Key Map | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Update Linework and Labels - Lighting | Done | Jordan James <jjames@dot.nv.gov> | 6 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Update Signals Coversheet/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Complete General Notes - Signals | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Cut sheets - ITS Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | General Notes - ITS | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Update ITS Coversheet/Key Map | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Update Structure List - ITS | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Schedules - ITS | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Linework and labels - ITS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 8 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Update Estimate- ITS | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Update Construction Notes - ITS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | Address any final review comments and DOC | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 81 | 81 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Address Lighting Internal Review Comments - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 6 | 99.5 | 99.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | NDOT 3876 Submittal 007 Underground Electric Service | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | AGI32 Lighting Analysis - Optimization | Done | Jordan James <jjames@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | AGI32 Lighting Analysis - Lighting Layout | Done | Jordan James <jjames@dot.nv.gov> | 2 | 99.5 | 99.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | Material Submittals Old | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 26 | 3876 Submittal 008 $ | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 70 | 70 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | UPRR Underdeck Lighting Analysis | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 50.5 | 50.5 | 0 |  | TRUE
10994 | Done | Potential | C3860 - EA 73976 - Railroad Active Advance Warning System (AAWS) |  | Signals Lighting and ITS\2022 Sprint 1 | Cabinet Locations to TOTS | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 29.5 | 29.5 | 0 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Basic Linework | New |  | 4 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Basic Linework | New |  | 4 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Basic Linework | New |  | 4 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals - Cut Sheets | New |  | 1 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting - Cut Sheets | New |  | 2 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS - Cut Sheets | New |  | 2 | 43.5 | 6 | 37.5 |  | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Conduct a PDFS Google Drive for project limits | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 6.5 | 6 | 0.5 | 2023-01-17 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New |  | 2 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 2 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | New |  | 2 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Structure List | New |  | 1 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Structure List | New |  | 1 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Structure List | New |  | 1 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Framework | New |  | 2 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 43.5 | 6 | 37.5 |  | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 2 | 43.5 | 6 | 37.5 |  | TRUE
8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | On-Hold | 30% Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Comment on PS&E Shared Review | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 6.5 | 6.5 | 0 |  | FALSE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Address PS&E Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 11 | 11 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | Underdeck lighting coordination w/ Structures | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Address Lighting Design changes from Structures | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | TRUE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 1 | ITS Cleanup | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 31.5 | 31.5 | 0 |  | TRUE
26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | On-Hold | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Internal Review - Intermediate Signals | Approved | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 46.5 | 45.5 | 1 |  | TRUE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Lighting Cover/Key Map | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Lighting Schedule & Structure List | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Lighting General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Lighting Linework/Labels/Construction Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 6 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Lighting Cutting Sheets | Done | Jordan James <jjames@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Signal General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Signal Linework & Labels | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 6 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Signal Schedule & Structure List | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 4 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Signals Cutting Sheets | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Signal Cover/Key Map | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | ITS General Notes | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | ITS Schedule & Structure List | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | ITS Cover/Key Map | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | ITS Cutting Sheets | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | ITS Linework/Labels/Construction Notes | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Intermediate Estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Intermediate Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Intermediate Compile and Submit (review A/C) | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Lighting Address Internal Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 21.5 | 21.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | ITS Address Review Shared Comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 21.5 | 21.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Lighting Address Shared Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 21.5 | 21.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Signal Address Shared Review Comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 21.5 | 21.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Signal Address Internal Review Comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 4 | 21.5 | 21.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | ITS Address Review Internal Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 21.5 | 21.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | QA/QC Estimate | Done | Brian Dodds <btdodds@dot.nv.gov> | 1 | 21.5 | 21.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | QA/QC Structure List | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 21.5 | 21.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | QA/QC Compile and Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 21.5 | 21.5 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Lighting Address Shared Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | ITS Address Review Shared Comments | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Signal Address Shared Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | DOC Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | ITS Devices Added to Spreadsheet | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 12 | 12 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | DOC Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 12 | 12 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | DOC Compile and Submit | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 12 | 12 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | C3973 BRAT Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 2.5 | 2.5 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Review Traffic-rated Heavy lid detail | New |  |  | 146 | 133 | 13 |  | FALSE
10994 | Done | Potential | C3904/EA 74376 - Advanced Signal Warning System (ASWS) Modification/Removal Designs |  | Signals Lighting and ITS\2022 Sprint 1 | BRAT Review | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 45.5 | 44.5 | 1 |  | TRUE
10994 | Done | Potential | C3901/EA 74368 - SR-445/Egyptian/Sunset Springs Ln Signal system |  | Signals Lighting and ITS\2022 Sprint 1 | BRAT Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 55.5 | 54.5 | 1 |  | TRUE
10994 | Done | Potential | C3899/EA 74234 - Caliente Multi-Use Path |  | Signals Lighting and ITS\2022 Sprint 1 | BRAT Review | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 54.5 | 54.5 | 0 |  | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 2 | 15 | 0 | 15 | 2025-10-20 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 15 | 0 | 15 | 2025-10-20 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 15 | 0 | 15 | 2025-10-20 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 15 | 0 | 15 | 2025-10-20 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 15 | 0 | 15 | 2025-10-20 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 1 | 15 | 0 | 15 | 2025-10-20 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 15 | 0 | 15 | 2025-10-20 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 4 | 15 | 0 | 15 | 2025-10-20 | FALSE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 11 | Review NVE Plans/721A forms | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review (need A/C review) | New |  | 1 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 5 | 74346 - Fallon Ph2 - IMD Internal Review | Done | Alex Traeger <atraeger.ctr@dot.nv.gov> | 8 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 2 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 6 | Accept/Reject Comments on Intermediate Internal Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject Comments on QA/QC Internal Review | New |  | 2 | 36 | 2 | 34 | 2024-09-23 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Internal Review | New |  | 6 | 36 | 2 | 34 | 2024-09-23 | FALSE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 17 | 14 | 3 |  | TRUE
45240 | EA 74358 (No 60K#) SR 766 Newmont Mine Rd | Actively Working | Doc Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts | New |  | 1 | 7 | 6 | 1 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Transition one project from Epic to Project - Laura | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Transition one project from Epic to Project - Jordan | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Enter Comments for RFQ - Q0-239-21-813 | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 146 | 133 | 13 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | ITS Linework and Labels | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | ITS Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | ITS Schedules | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | ITS Coversheet | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Cut Plan Sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Special Details | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | ITS General Notes | Done | Jordan James <jjames@dot.nv.gov> | 1 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Structure List | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Estimate | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Compile and Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | QAQC Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Confirm QC comments on Intermediate Internal Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | Doc Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Address Internal Review Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 8 | 8 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Upload SP Photos to AMP | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 19.5 | 19.5 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Intermediate 3 Structure List | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Intermediate 3 Estimate | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 5 | Intermediate 3 Compile and Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 57 | 57 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Contract 3886 - Submittals - Poles and Structures, Roadway Lighting, and AC Power Dist. Equip | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Contract 3886 - Submittals - Geotextile, Poles/Structures, and Roadway Lighting | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design (Only 30% ITS & LTG Plans & Rough Estimate) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | SP Request for updating Existing 100AMP SP | Done |  | 1 | 16 | 16 | 0 |  | TRUE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Framework | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 22.5 | 22.5 | 0 |  | FALSE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | ITS Intermediate Internal Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 25 | 25 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Convert Fiber Hut DC drawings | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 11 | 11 | 0 |  | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | Build Features & PBIs | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 6.5 | 6 | 0.5 | 2023-01-17 13:30 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 2 | PDFS Report | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 6.5 | 6 | 0.5 | 2023-01-17 13:30 | FALSE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Confirm QC Comments on QA/QC Internal Review | Done | Jordan James <jjames@dot.nv.gov> | 1 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Provide PS&E Shared Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 1 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Internal Review - QA/QC - Signals | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Confirm QC Comments on PS&E Shared Review (need A/C review) | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Framework | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Schedules - Signal Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Linework - Signal Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Estimate- Signal Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Structure List - Signal Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Signals Coversheet/Key Map | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Construction Notes - Signal Design | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | General Notes - Signal Design | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Cut sheets - Signal Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Cut sheets - Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Linework - Lighting Design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 6 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | General Notes - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Estimate - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 1 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Lighting Coversheet/Key Map | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Structure List - Lighting Design | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Schedules - Lighting Design | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 4 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Construction Notes - Lighting Design | Done | Jordan James <jjames@dot.nv.gov> | 2 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Review special provisions | Done | Jordan James <jjames@dot.nv.gov> | 1 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 2 | 61.5 | 61.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | DOC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Address Shared Review Comments | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11.5 | 11.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | DOC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Compile and Submit | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11.5 | 11.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | DOC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Address Internal Review Comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 6 | 11.5 | 11.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | DOC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Check Bid Items + Quantities | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11.5 | 11.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | DOC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Final estimate | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11.5 | 11.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | DOC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | Done |  | 0.5 | 11.5 | 11.5 | 0 |  | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team Intermediate Coordination Meeting | New |  | 0.5 | 28 | 0 | 28 | 2024-08-07 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Intermediate Coordination Efforts | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 4 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 2 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 2 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 8 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 2 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels 1/2 | New |  | 8 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 4 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General Notes | New |  | 1 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels 1/2 | New |  | 8 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New |  | 2 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedule & Structure List | New |  | 6 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Cutting Sheets | New |  | 6 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 2 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Special Details | New |  | 2 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  | 0.5 | 28 | 0 | 28 | 2024-08-07 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New |  | 0.5 | 28 | 0 | 28 | 2024-08-07 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts - needs custom criteria when importing | New |  |  | 28 | 0 | 28 | 2024-08-07 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | IMD Estimate | New |  | 1 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | IMD Structure List | New |  | 2 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | IMD Compile and Submit (Review A/C) | New |  | 4 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Signal Internal Review | New |  | 4 | 28 | 0 | 28 | 2024-08-07 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 2 | 28 | 0 | 28 | 2024-08-07 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 28 | 0 | 28 | 2024-08-07 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 28 | 0 | 28 | 2024-08-07 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 28 | 0 | 28 | 2024-08-07 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts - needs custom criteria when importing | New |  |  | 16 | 0 | 16 | 2024-04-11 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address IR Comments | New |  | 4 | 16 | 0 | 16 | 2024-04-11 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address SR Comments | New |  | 2 | 16 | 0 | 16 | 2024-04-11 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address IR Comments | New |  | 4 | 16 | 0 | 16 | 2024-04-11 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address SR Comments | New |  | 2 | 16 | 0 | 16 | 2024-04-11 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 16 | 0 | 16 | 2024-04-11 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 16 | 0 | 16 | 2024-04-11 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 16 | 0 | 16 | 2024-04-11 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Post Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  |  |  | 0 |  | 2024-04-11 | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Internal Review (QAQC) - Signals | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Lead Designer Approval/Rejection - QAQC | Done | Jordan James <jjames@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Provide Comments in PS&E Shared Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Address Internal Review Comments - QAQC (Signals) | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 28.5 | 28.5 | 0 |  | FALSE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | BRAT Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal | New |  | 1 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  |  | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  |  | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  |  | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  |  |  | 0 |  | 2025-02-24 | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | QA/QC Estimate | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 5 | 5 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | QA/QC Structure List | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 5 | 5 | 0 |  | TRUE
31553 | EA 74373 - EA 61007 - Cutting St to Slime Wash - Tonopah RCB | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | QA/QC Compile and Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 5 | 5 | 0 |  | TRUE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | DOC Structure List & Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
27148 | C 4501 - EA 74360 / 74373 - EA 61007 - US6, Tonopah, Millers to Slime Wash 3R and ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 6 | DOC Compile and Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Confirm QC Comments on Intermediate Internal Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Provide Comments IMD IR | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 17.5 | 17.5 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Provide Comments QA/QC Internal Review | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 10 | 10 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 25 | Confirm QC Comments on QA/QC Internal Review | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 10 | 10 | 0 |  | TRUE
23967 | EA 74323 / 69961 - FR WA51 (Matley Ln) Safety Improvements | DOCed | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 10 | Plot & Submit | Done | Shaza Elshazli <selshazli@dot.nv.gov> | 1 | 2 | 2 | 0 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  | 0.5 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts - needs custom criteria when importing | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Design Conflict Efforts - needs a/c | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Coordination - District pull box type preferences | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Intermediate Review Utility and UPRR Conflicts | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Lighting Voltage Drop | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Lighting Cover/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Lighting Schedule & Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Lighting Construction Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Lighting General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Lighting Linework & Labels (check PMP) | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | Lighting Cutting Sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 8 | ITS Request TOTS Pathway Analysis | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | ITS Construction Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | ITS General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | ITS Voltage Drop | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | ITS Schedule & Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | ITS Cover/Key Map | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | ITS Special Details | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 12 | ITS Cutting Sheets | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | ITS Linework & Labels | Done | Jordan James <jjames@dot.nv.gov> | 2 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Clearing and Grubbing/Seeding | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Estimate | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | Intermediate Structure List | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Intermediate Compile and Submit | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal | New |  | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 1 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 18 | Internal Review - Intermediate | Done | Fernando Torres <ftorres@dot.nv.gov> | 4 | 44 | 41 | 3 |  | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  | 0.5 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New |  | 0.5 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 9 | Lighting Address Internal Review Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 4 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 7 | ITS Address Review Internal Comments | Done | Alesha Jackson <ajackson@dot.nv.gov> | 4 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 1 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 6 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 1 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 29 | 10 | 19 | 2024-11-12 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 9.5 | 0 | 9.5 | 2025-10-02 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 9.5 | 0 | 9.5 | 2025-10-02 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 9.5 | 0 | 9.5 | 2025-10-02 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 | FALSE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | On-Hold | Post-DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-10-02 | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Lead Designer Accept/Reject Comments - QAQC | Done | Jordan James <jjames@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Review special provisions - QAQC | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Internal Review - QAQC Signals | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 25 | Provide Comments in Shared Review - PS&E | Done | Jordan James <jjames@dot.nv.gov> | 1 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Address internal review - Signals | Done | Alesha Jackson <ajackson@dot.nv.gov> | 2 | 39.5 | 39.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Address internal review - Lighting | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 6 | 39.5 | 39.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 2 | Address internal review - ITS | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 39.5 | 39.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 19 | Address shared review - Intermediate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Address shared review - PS&E | Done | Jordan James <jjames@dot.nv.gov> | 2 | 39.5 | 39.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Internal Review - QAQC Lighting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 24 | Internal Review - QAQC ITS | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | Post-DOC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 17 | BRAT Review | Done | Fernando Torres <ftorres@dot.nv.gov> | 0.5 | 27 | 27 | 0 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 12 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 35.5 | 0 | 35.5 | 2023-03-20 | TRUE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lead Designer Accept/Reject Comments - QAQC | New |  | 1 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Internal Review - QAQC | New |  | 6 | 29.5 | 17.5 | 12 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address Internal Review Comments - QAQC | New |  | 2 | 7.5 | 0 | 7.5 | 2026-12-21 | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments in QAQC Shared Review | New |  | 1 | 29.5 | 17.5 | 12 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | Doc Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Compile and Submit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 8 | 8 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | Doc Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Update Structure List and Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 8 | 8 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | BRAT Review | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 28.5 | 28.5 | 0 |  | FALSE
38980 | EA 74178 - SR-207 (Kingsbury grade) 3R | On-Hold | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 7.5 | 0 | 7.5 | 2026-12-21 | FALSE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 12 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 2 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 34.5 | 0 | 34.5 |  | TRUE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Internal Review - QAQC | Done | Laura Vargo <lvargo@dot.nv.gov> | 6 | 14 | 14 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments in Shared Review - QAQC | Done |  | 1 | 14 | 14 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Address Internal Review Comments - QAQC | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 11 | 11 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Lead Designer Accept/Reject Comments - QAQC | Done | Jordan James <jjames@dot.nv.gov> | 1 | 14 | 14 | 0 |  | FALSE
39013 | C 3992 - EA 74175 - SR-359 - Hawthorne ADA | DOCed | Post-DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | BRAT Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 3.5 | 3.5 | 0 |  | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 10 | Address Intermediate Internal Review Comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 18 | 18 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 11 | Internal Review QAQC | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 6 | 18 | 18 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 13 | Accept/Reject Internal Review Comments QAQC | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 18 | 18 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Address Shared Review comments | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | TRUE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review | New |  | 0 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | Intermediate Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject Shared Review Comments | New |  | 0 | 36 | 36 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review | New |  | 0 | 0 | 0 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | QAQC Shared Review | New |  | 0 | 0 | 0 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject QAQC Shared Review comments | New |  | 0 | 0 | 0 | 0 |  | FALSE
19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | On-Hold | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject QAQC Internal Review comments | New |  | 0 | 0 | 0 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | QAQC Internal Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 6.5 | 6.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Accept/Reject QAQC Internal Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 6.5 | 6.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | PS&E Shared Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 6.5 | 6.5 | 0 |  | FALSE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC Plan review | Done |  | 6 | 10.5 | 10.5 | 0 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Perform Internal Review | New |  | 4 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Accept/Reject Internal Review comments | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Perform Shared Review | New |  | 4 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | Intermediate Design |  | Signals Lighting and ITS | Accept/Reject Shared Review comments | New |  | 1 | 35 | 0 | 35 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Perform Shared Review | New |  |  | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Accept/Reject Internal Review comments | New |  |  | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Accept/Reject Shared Review comments | New |  |  | 7 | 0 | 7 |  | TRUE
31065 | EA xxxxx - US-95A/50A at Cottonwood (Fernley) | Potential | QAQC Design |  | Signals Lighting and ITS | Perform Internal Review | New |  |  | 7 | 0 | 7 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | IPD Estimate | Done | Jordan James <jjames@dot.nv.gov> | 4 | 10.5 | 10.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Provide Intermediate Shared Review Comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 13.5 | 13.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Signal Schedules & Structure List | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 10.5 | 10.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Signal General Notes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Signal Linework/labels/construction notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 10.5 | 10.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Cover | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 10.5 | 10.5 | 0 |  | TRUE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Structure List & Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15.5 | 15.5 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 13 | Compile & Submit | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Structure List & Estimate | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 8 | Address Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15.5 | 15.5 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 12 | Address Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 6 | 6 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Provide Comments IMD IR Lighting | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 50 | 50 | 0 |  | FALSE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | Intermediate Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Provide Comments IMD IR Signals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 4 | 50 | 50 | 0 |  | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Additional Estimated EP (BUFFER) | New |  |  | 16 | 0 | 16 | 2024-04-11 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review Comments | New |  | 0 | 11.5 | 0 | 11.5 | 2025-01-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review Comments | New |  | 0 | 11.5 | 0 | 11.5 | 2025-01-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Devices added to Spreadsheet | New |  | 0.5 | 11.5 | 0 | 11.5 | 2025-01-27 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 11.5 | 0 | 11.5 | 2025-01-27 | FALSE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Submit rough plot set to RD | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | Removal/Relocation of Sign with Flashers | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 22.5 | 22.5 | 0 |  | FALSE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Estimate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 7 | 7 | 0 |  | TRUE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | CO #3 Design Changes (PBI 2/5) | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 6 | 33.5 | 33.5 | 0 |  | FALSE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | CO#3 Memo (PBI 5/5) | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 33.5 | 33.5 | 0 |  | FALSE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | CO#3 Structure List (PBI 4/5) | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | FALSE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 3 | CO #3 Coordination (PBI 1/5) | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 33.5 | 33.5 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Update Golden Valley SP to reflect DAA | Done | Alesha Jackson <ajackson@dot.nv.gov> | 0.5 | 50.5 | 50.5 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 14 | Estimate | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 15.5 | 15.5 | 0 |  | TRUE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Review NVE SP Plans | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 35.5 | 35.5 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Hydraulics Conflict Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | 3899 - Submittal - 623.0575 - Steel Pole, Type 7 (with safety base) | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3899 - Submittals - 6231795, 6231820, 6230226, 6230236. | Done |  | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | 3899 - Submittals - 6231980, 6231985, 6231620. | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | 3899 - Submittal - 6230267 - Luminaire, Type A | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Address ITS IMD IR comments - Sheets | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Address ITS IMD IR comments - Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 6 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Address LTG IMD IR comments - LT010-LT15 | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 50.5 | 50.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | LTG One-line Diagrams | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 37.5 | 37.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Address LTG IMD SR Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 50.5 | 50.5 | 0 |  | TRUE
23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | QAQC Estimate | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 10.5 | 10.5 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Address TOTs Comments | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS IMD IR comments | New |  | 4 | 12 | 0 | 12 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS IMD SR comments | New |  | 1 | 12 | 0 | 12 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Design Framework | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 2 | 37 | 2 | 35 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 4 | Add lighting Power Sources | Done | Jordan James <jjames@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | Update ITS based on sound wall design | Done | Jordan James <jjames@dot.nv.gov> | 8 | 101.5 | 101.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | PS&E Shared Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 22.5 | 22.5 | 0 |  | FALSE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | Doc Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Address Shared Review Comments & Sign Location Change | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 8 | 8 | 0 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Beowawe Solar - Schedules | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 43 | 43 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Beowawe Solar - Solar Power design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 6 | 43 | 43 | 0 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cutting Sheets | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedule & Structure List | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | Approved |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Request TOTS Pathway Analysis - need A/C | New |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | Approved |  | 1 | 37 | 2 | 35 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | Approved |  | 4 | 37 | 2 | 35 |  | FALSE
7451 | C 4521 - EA 74249 - EA 60959 - US-50 in East Lake Tahoe Ph1 | DOCed | Intermediate #2 Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | Redo Signal design based on SUE results & coordination | Done | Jordan James <jjames@dot.nv.gov> | 6 | 56 | 56 | 0 |  | TRUE
8157 | C 3987 - EA 74302 - 8-00250 - D2 Rural ITS Pkg 2 (USA Pkwy ITS conduit connection over UPRR) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Address QAQC Shared Review Comments | Done | Victoria Jeffery <vjeffery@dot.nv.gov> | 1 | 10.5 | 10.5 | 0 |  | FALSE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Address Changes from Specs and Compile & Submit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 14.5 | 14.5 | 0 |  | FALSE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 5 | Bid Items and Quantities | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 61.5 | 61.5 | 0 |  | TRUE
24311 | C 3943 - EA 74341 - I-11 Hoover Dam 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 11 | 11 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Add Breaker Panel to SP06 | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 99.5 | 99.5 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Service Pedestal (for post replacements) request | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 17 | 17 | 0 |  | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | Submit RRFB locations to T.O. Analysis group | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 17 | 17 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | 3892 Pull Boxes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | 3892 029- No 500 Conductor, 046-47 & 051-053 1 1/2" & 3" Conduits | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 6 | 3892 Submittal 048- Dura-Line 4 Inch Conduit & 054- 4 Inch Conduit Alternative | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Intermediate Internal Review A/R Comments | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 29.5 | 29.5 | 0 |  | TRUE
7457 | C 3900 - EA 74208 - EA 60942 - US-95 South of Goldfield 3R | DOCed | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Brat Report | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Address QAQC Internal Review Comments at UPRR Crossing | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | 3892 Submittals 017-018 Shorting Caps & 019- Luminaire | Done | Jordan James <jjames@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | NDOT 3893 electrical submittals | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3893 Submittal - 010 - 30' ITS Pole | Done |  | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | 3892 Submittals 031- Ground Rods, 032- Service Wire #4 Conductor | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | 3892 Submittals 036- Transformer Pad & 037- Transformer Pad Alternate | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | 3892 Submittals 039- #10 Conductor, 041-042- Ground Plate & Clamp, 043- Stranded Conductor #4 | Done | Jordan James <jjames@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | 3892 Submittal 061- 4-Inch Multi-duct Conduit | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Submittal: 3898 ITS Group 1 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Submittal: 3898 ITS Group 3, 4,10,11,16 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | 3892 Submittal 062- Luminaire Type B | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3891 Fallon - Pull Boxes Submittal 09 , Conductor & Cables Submittal 10 | Done |  | 1 | 89 | 89 | 0 |  | FALSE
41179 | C 3911 - EA 74194 / 61023 - US-50/Warrior Way New Signal | Actively Working | Post-DOC | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Change Order 1 | Done | Jordan James <jjames@dot.nv.gov> | 4 | 13 | 13 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Update Push Buttons | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Internal Review (QAQC) - Lighting | On-Hold | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Internal Review (QAQC) - ITS | On-Hold | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0 | 99.5 | 99.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Update SP Enclosure Special Detail | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Panel Schedules | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 28.5 | 28.5 | 0 |  | FALSE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | Post DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | SP Location Change in plan sheet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 3 | 3 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Update ITS SP Info | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Update Structure List | Done | Jordan James <jjames@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Coordination and Plans Changes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Ramp Meter Design | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 61.5 | 61.5 | 0 |  | TRUE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | US-95/SR-163 Additional Lighting Discussion | Done |  |  | 57 | 57 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Bridge rail expansion joint conduit detail | Approved |  | 4 | 146 | 133 | 13 |  | FALSE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 7 | Replace pull boxes | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 61.5 | 61.5 | 0 |  | TRUE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | ITS Splice Diagrams | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 50.5 | 50.5 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | QA/QC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Add Existing Linework for Tropicana | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 99.5 | 99.5 | 0 |  | FALSE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Pole Assessment & Scoping | Approved | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 21.5 | 14.5 | 7 | 2022-11-30 13:30 | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design (Only 30% ITS & LTG Plans & Rough Estimate) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Utility conflict with Trunkline | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 16 | 16 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design (Only 30% ITS & LTG Plans & Rough Estimate) | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Solar Design for Lighting | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 16 | 16 | 0 |  | TRUE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | DOC Plans Preparation | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 2 | 2 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Make additional minor changes to 2022 standard plan sheets | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3901 - Conduit Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3901 - Pull Box Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3901 - Conductor Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3901 - Signal Cable Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3901 - Ped Button Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3899 - Alternate pullbox 2017 version | Done | Eric Macgill <emacgill@dot.nv.gov> | 0 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3893 Submittals 17, 18, 19 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Contract 3898 Group 12 Dynamic Message Sign and Communication Cabinet | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Contract 3889 - Electrical Submittal #10.1 | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3838R Wadsworth - Submittal 002 (Poles) | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3838R Wadsworth - Submittal 001 (Conductor) | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3838R Wadsworth - Submittal 003 (Conduit) | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3838R Wadsworth - Submittal 004 Pull Boxes | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3838R Wadsworth - Submittal 005 RRFB | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3838R Wadsworth - Submittal 006 (Traffic Radar Sign) | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3838R Wadsworth - Submittal 007 Electrical Service | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3838R Wadsworth - Submittal 008 Type A Luminaire | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3838R Wadsworth - Submittal 009 Type B Luminaire | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Submittal NDOT 3899 - SBMT 004.R1 - ITS Group 4, Conductor, Concrete, Meter Pedestal | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3893 - Submittal 015.1 Pull Boxes | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Contract 3886 - Submittals - Roadway Lighting | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3890 - 040 - Luminaire A Combined | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3890 - 041 - Pole 7 Combined | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | 3890 - 042 - Pole 14 Combined | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
29406 | C 4527 - EA 74367 - EA 61011 Ely Midtown Project | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | Provide Intermediate Shared Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | QA/QC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Internal Review - QA/QC - Lighting | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 4 | 61.5 | 61.5 | 0 |  | TRUE
33940 | C 3973 - EA 74371 - EA 69975 - I-580 South Reno 3R | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 17 | LTG - Headframe Assemblies | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 21.5 | 21.5 | 0 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | QA/QC #3 Submittal | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 8 | BRAT review of C3917 - EA 74324 - EA 61021 - SR-225/Terminal Way Elko RRFB | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Printing Issues | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 8 | 8 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Make changes to the C3860 UPRR oneline diagram for wiring connections to UPRR. | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 18.5 | 18.5 | 0 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Create Solar light pole foundation detail(s) | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Phasing Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 36 | 34 | 2 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3890-022 - 3.5 Pull Box | Done |  | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Contract 3889 - Electrical Submittal 10.1- Pull Boxes | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Contract 3889 - Electrical Submittals 17, 18, 19, and 20 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | 3901 Submittal Traffic Actuated Controller | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | CONTRACT 3890 SUBMITTAL 047 1.5 Inch Conduit | Done |  | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | CONTRACT 3890 SUBMITTAL 048 3 Inch Conduit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | NDOT 3892 Submittal #105 - Modify Electrical Service | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | NDOT 3892 Submittal #106 - 7.5 KVA Transformer | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
22213 | Fiber Hut at Border Inn (near Baker, NV and Utah border) | DOCed | Post DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Changes on ITS and FH sheets based on I-80 Planset | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 3 | 3 | 0 |  | TRUE
19922 | Fiber Hut I-80 West of SR-439 | DOCed | Post DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | New changes to ITS and FH Sheets | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 7 | 7 | 0 |  | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | 2022-05-10 - Right of Way acquisition review to RW | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 6.5 | 6 | 0.5 | 2023-01-17 13:30 | FALSE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Intermediate "progress" set | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 17 | 17 | 0 |  | FALSE
42012 | C 3898 - EA 60978 - D2 DMS Betterment Project | DOCed | Post-DOC Design | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Change Order 1 | Done | Jordan James <jjames@dot.nv.gov> | 2 | 4 | 4 | 0 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | ITS Plan Phasing | Done | Jordan James <jjames@dot.nv.gov> | 2 | 48.5 | 48.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Q0-239-21-813 Material Submittal 3 No. 5 H20 Certs | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | 3906 Submittals 012-013-014 Pull Box, 3inch Conduit and Loop | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | 3890 SUBMITTAL 051 Meter Pedestal | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | ITS Design - Linework/Labels/Construction Notes | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | ITS Design - Schedules/Structure List | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 19.5 | 19.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | ITS Design - Special Details/General Notes | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 19.5 | 19.5 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | ITS Design - Cover/Key Map | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 19.5 | 19.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3838R Wadsworth - Re-Submittal 002R / 11 (Poles) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Cont. 3901 Submittal Request ITS Meter Service | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Cont. 3901 Submittal Request | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 9 | Add Kingslane RRFB to ITS Schedules | Done | Jordan James <jjames@dot.nv.gov> | 2 | 48.5 | 48.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | NDOT 3911 - Submittal 02 & 03 | Done |  | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3838R Wadsworth - Submittal 10 (Geotextile for Conduit Trenches) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Cont. #3901 - Pull Box Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Q1-492-21-101 Preformed Loop Detector Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3838R Wadsworth - Submittal 009-R Type B Luminaire | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Submittal #109 - No. 9 Pull Box, Modified | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | CONTRACT 3890 SUBMITTAL 2.5 PVC Conduit | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | ITS Design - Coordination | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 1 | 19.5 | 19.5 | 0 |  | TRUE
37939 | C 3922 - EA 74397 - I-15@Primm Widening and Ramp Meter | DOCed | Post DOC changes | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Changes to Sign Detail | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 10 | Update ITS Block Diagram/Compile | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | QA/QC ITS IR | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 4 | 48.5 | 48.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Confirm QC Comments on QA/QC Internal Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 48.5 | 48.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 23 | Provide PS&E Shared Review Comments $ | Done | Jordan James <jjames@dot.nv.gov> | 2 | 15.5 | 15.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Provide Intermediate Shared Review Comments | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 34 | 2 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3838R Wadsworth - Submittal 008 Type A Luminaire Resubmittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3901 Submittal Gridsmart Video Image Detection System | Done |  | 0.5 | 89 | 89 | 0 |  | FALSE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | ITS Block Diagrams | Done | Laura Vargo <lvargo@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3901 SUBMITTAL LUMINAIRE TYPE A | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | 3892 Re-Submittal No. 062-01 - Luminaire Type B | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Contract 3889 - Electrical Submittal #10.2 - Pull Boxes | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Submittal No. 131 - Weigh in Motion System - NDOT 3892 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | CO #3 Design Changes (PBI 3.2/5) | Done | Laura Vargo <lvargo@dot.nv.gov> | 4 | 33.5 | 33.5 | 0 |  | FALSE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | CO #3 Design Changes (PBI 3.3/5) | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Lighting Design Changes | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 18.5 | 18.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | 3892 Re-Submittal No. 0019-01 Luminaire | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Contract 3901 ILLUMINATED STREET NAME SIGN SUBMITTAL | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | FW: NDOT 3911 Submittals 7-10 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels 2/2 | New |  | 8 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels 2/2 | New |  | 8 | 84 | 1 | 83 | 2023-08-14 | FALSE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Lighting Internal Review | New |  | 4 | 28 | 0 | 28 | 2024-08-07 | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Signal Plan Phasing | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 48.5 | 48.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | Lighting Plan Phasing | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 48.5 | 48.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Address Signal PS&E Shared Review comments | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 7.5 | 7.5 | 0 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Respond & Comment - PS&E #3 Shared Review | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Framework | New |  | 2 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 2 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Lighting Linework & Labels & Construction Notes | New |  | 2 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Signal General Notes | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Signal Linework & Labels & Construction Notes | New |  | 4 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Signal Schedule & Structure List | New |  | 2 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Signals Cutting Sheets | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | ITS Schedule & Structure List | New |  | 2 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | ITS Cutting Sheets | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | ITS Linework & Labels & Construction Notes | New |  | 4 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Intermediate Compile and Submit (review A/C) | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Confirm Specs review comments - IMD Submittal | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Confirm QC Comments on IMD IR | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Confirm QC Comments on IMD SR | New |  | 1 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Provide IMD SR Comments | New |  | 2 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Provide Comments IMD IR Review Lighting | New |  | 2 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | QA/QC Coordination Efforts - needs custom criteria when importing | New |  | 0.5 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | QAQC Submittal |  | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25.5 | 0 | 25.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | Doc Coordination Efforts - needs custom criteria when importing | New |  | 0.5 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 2 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 1 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 1 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Doc Submittal |  | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 12.5 | 0 | 12.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Post-Doc |  | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Provide Comments IMD IR Review Signals | New |  | 2 | 43 | 0 | 43 |  | TRUE
42799 | EA 74435, I-580, Peckham to Mill - SLI Moved to Ph2 | Potential | Intermediate Submittal |  | Signals Lighting and ITS | Provide Comments IMD IR ITS | New |  | 2 | 43 | 0 | 43 |  | TRUE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Adjust poles based on meeting | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 43 | 43 | 0 |  | TRUE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Create KMZ with RoW footprint for all SLI work including solar | Done | Jordan James <jjames@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | 3891 Submittal 21 - Ornamental Lights R1 | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 11 | 3891 Submittal 17 - Luminaire Type A | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Move Lighting Design | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Update Lighting Schedules | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Re-cut Lighting & ITS Plan Sheets | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Update Lighting Coversheet/Key Map | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Update Ref Files & Move ITS Design | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Update ITS Coversheet/Key Map | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Update ITS Schedules | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 15 | 15 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Contract 3900 - SBMT 006 - 623 Group 1 Electrical (ITS Pole) | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Contract 3900 - SBMT - 623 Group 6 Electrical (Loop Detector) | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Contract 3900 - SBMT - 623 Group 4 Electrical (Conductors) | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Contract 3900 - SBMT - 623 Group 3 Electrical (Pull Box and Conduits) | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | NDOT 3911 - Submittal 13 -Electrical Poles & Misc. | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | NDOT 3911 - Submittal 14 - Controller Cabinets & Traffic Controller | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
26196 | EA 74346 - EA 69993 - US 50, Fallon, 3R - PH1 | DOCed | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Preliminary design | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 8 | 8 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | SUBMITTAL: REVISED Contract 3898 Group 12 Dynamic Message Sign and Communication Cabinet | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Check Schedules - Lighting/ITS | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 28.5 | 28.5 | 0 |  | FALSE
25027 | C 3951 EA 74339 EA 61051 - SR-376 Carver's Roadside Rest Park | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Check Schedules | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 11 | 11 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | NDOT 3911 - Submittal 15 - Signals | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | NDOT 3911 - Electrical Submittal | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | NDOT 3911 - Electrical Submittals 21-24 | Done | Jordan James <jjames@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | RWIS site coordination | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2026 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Bridge Rail Expansion Joint Detail | New |  | 2 | 4 | 2 | 2 |  | FALSE
38131 | C 3940 - EA 74338 - EA 61033 - I 15 Bonanza to Craig 3R | DOCed | DOC Submittal | Jordan James <jjames@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Battery Backup System | Done | Jordan James <jjames@dot.nv.gov> | 1 | 11.5 | 11.5 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 22 | Update Bid Items and Quantities | Done | Jordan James <jjames@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | Update Estimate and send to Roadway | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 101.5 | 101.5 | 0 |  | FALSE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | QA/QC LTG IR | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 48.5 | 48.5 | 0 |  | TRUE
7211 | C 3981 - EA 74108 - EA 60831 - Ph1 - US-395 from Waterloo Ln. to 1st St. | DOCed | Ph. 1 QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 20 | QA/QC SIG IR | Done | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 2 | 48.5 | 48.5 | 0 |  | TRUE
13108 | C 3952 - EA 74301 - SR-431 - Mt. Rose Hwy @ Callahan Ranch Rd. & Edmonton Dr. | DOCed | Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 12 | Address SPEC comments | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 7.5 | 7.5 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | 3892 Submittal No. 169 - Underground Service Enclosure | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2021 Sprint 13 | PS&E Submittal | Done | Jordan James <jjames@dot.nv.gov> | 2 | 28.5 | 28.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | 3892 Re-Submittal No. 105-1 Modify Electrical Service | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Submittal 3900 - SBMT 017 - Dynamic Message Sign | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | FW: 3838R Wadsworth - Submittal 16 (Signs) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | FW: NDOT 3858 - Electrical Submittals 78-84 | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | Cont. 3901 Submittal Signal Head | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Update Schedules - Circuit Info | Done | Jordan James <jjames@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 13 | RWIS Details - QAQC- 74239 | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 41 | 41 | 0 |  | TRUE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Finish SP Scope | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 28.5 | 28.5 | 0 |  | FALSE
7601 | C 3936 - EA 74204 - I-80 @ Beowawe Interch. truck climbing lane | DOCed | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Revise foundation details based on responses | Done | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 6 | 6 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Move conduits to run alongside sound walls | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 101.5 | 101.5 | 0 |  | FALSE
24504 | C 3944 - EA 74337 - EA 61034 - I-80 Ch 3R (Nightingale) | DOCed | DOC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Add Conduits and Power Outlet | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 7 | 7 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | 3838 Wadsworth - Submittal 17 (Beacon Controller) | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7083 | C 3983 - EA 74107 / 61052 - US-395 North Valleys Ph1B (All Other Roadwork - McCarran to Golden Valley) | DOCed | QAQC Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Structures Lighting Coordination | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 50.5 | 50.5 | 0 |  | TRUE
30871 | C 3929 - EA 74205 - Battle Mountain Stand Alone L&A | DOCed | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | BRAT Report Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 0.5 | 0.5 | 0 |  | FALSE
29218 | C 3956 - EA 74177 - EA 69991 - US-95 Fm Trinity Intg to US-50 - Ch 3R fr US-50 to I-80 | DOCed | Post DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | BRAT Report Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 1 | 1 | 0 |  | FALSE
35766 | C3939 - EA 74370 - EA 61015 - I-80, E. of Carlin - Pavement Rehab | DOCed | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | BRAT Report Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 3.5 | 3.5 | 0 |  | FALSE
28673 | C 3955 - EA 74365 - EA 61004 - I-80 East of Battle Mt. (Rosny Creek) LA 15.889 - EU 2.877 | DOCed | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | BRAT Report Review | Done | Austin Hoekstra <ahoekstra@dot.nv.gov> | 0.5 | 2.5 | 2.5 | 0 |  | TRUE
7305 | C 3858 - EA 74079 - SR-28 fm Incline to NV/CA line | DOCed | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Address comments from Eric's Review | Done | Laura Vargo <lvargo@dot.nv.gov> | 2 | 33.5 | 33.5 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | NDOT # 3917, Group 1 - Poles | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | submittal 3900 - SBMT 010 - 623 Group 15 Electrical | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Add Existing ITS to Design | Done | Adji Witjaksono <awitjaksono@dot.nv.gov> | 4 | 101.5 | 101.5 | 0 |  | FALSE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Sound Wall Shared Review | Done | Jordan James <jjames@dot.nv.gov> | 0.5 | 101.5 | 101.5 | 0 |  | FALSE
38430 | C 3954 - EA 74356 - EA 61008 - I-515, Henderson Bowl to Wyoming Ave, 3R and ADA | DOCed | DOC Submittal | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Update SP Locations | Done | Jordan James <jjames@dot.nv.gov> | 1 | 28.5 | 28.5 | 0 |  | FALSE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | C3821 - Pole-mounted Cabinet & Switch | Done | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 146 | 133 | 13 |  | FALSE
43326 | Standard Plans Updates | Actively Working | 9106 - 2022 Standard Plans update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Comment on Final Shared Review | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 81 | 81 | 0 |  | FALSE
31381 | C 3974 - EA 74374 - I-80 (Elko) West of Pilot Peak to NV/UT Line | DOCed | QAQC Design | Gurpreet Singh Rai <grai@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 15 | Calculate Clearing and Grubbing Quantities | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 25 | 25 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 21 | Buffer PBI for power to new Communication Cabinets | Done | Jordan James <jjames@dot.nv.gov> | 2 | 101.5 | 101.5 | 0 |  | FALSE
7708 | C 4500 - EA 74239 - US-395 from CA/NV Line to Leviathan Mine Rd. | DOCed | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 16 | Update RWIS Details & add quantities to structure list | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
8089 | Material Submittal/RFI Reviews | Actively Working | 2022 Material Submittal | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 14 | Submittal Contract 3900 - SBMT 007.1 - 623 Group 3 Electrical | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 0.5 | 89 | 89 | 0 |  | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Estimate | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 7 | Compile and Submit | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | Add callouts to linework | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
38915 | C 3982 - EA 74308 / 61003 - I-15 South Phase 2 | DOCed | QA/QC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2022 Sprint 18 | Power to new Communication Cabinets | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 6 | 101.5 | 101.5 | 0 |  | FALSE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | ITS Schedules | Done | Kaur, Navneet <nkaur@dot.nv.gov> | 4 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 3 | ITS Construction Notes | Done | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 41 | 41 | 0 |  | TRUE
7665 | C 3996 - EA 74217 / 69954 - US-50 Lake Lahontan 3R | DOCed | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 4 | ITS General Notes | Done | Alesha Jackson <ajackson@dot.nv.gov> | 1 | 41 | 41 | 0 |  | TRUE

## Upcoming sprint Data
Project_ID | Project_title | Project_state | Epic_Title | Project_Assigned_To | Iteration Path | PBI_Title | PBI_State | PBI_Assigned_To | PBI_Efforts | Epic_TotalEfforts | Epic_Completed_Efforts | Epic_Pending_Efforts | Due_Date
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plan Sheets | New | NULL | 4 | 12 | 0 | 12 | 2023-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New | NULL | 2 | 12 | 0 | 12 | 2023-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plan sheets | New | NULL | 4 | 12 | 0 | 12 | 2023-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Special Provisions, Structure List, & Estimate | New | NULL | 2 | 12 | 0 | 12 | 2023-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plan Sheets | New | NULL | 6 | 18 | 0 | 18 | 2023-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New | NULL | 2 | 18 | 0 | 18 | 2023-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plans | New | NULL | 4 | 18 | 0 | 18 | 2023-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Special Provisions, Structure List, & Estimate | New | NULL | 2 | 18 | 0 | 18 | 2023-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Circuit Analysis | New | NULL | 4 | 18 | 0 | 18 | 2023-01-01
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Cut Lighting Sheets | New | NULL | 2 | 21.5 | 14.5 | 7 | 2022-11-30 13:30
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Sheets | New | NULL | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List | New | NULL | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate & Submittal | New | NULL | 1 | 21.5 | 14.5 | 7 | 2022-11-30 13:30
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | 12 EP to be created into "Address Comments" PBI's | New | NULL | 13 | 28 | 0 | 28 | 2024-08-07
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Shared Review | New | NULL | 2 | 15 | 7 | 8 | 2024-10-21
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E SR comments | New | NULL | 1 | 15 | 7 | 8 | 2024-10-21
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Signals PS&E SR comments | New | NULL | 1 | 15 | 7 | 8 | 2024-10-21
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E SR comments | New | NULL | 0 | 15 | 7 | 8 | 2024-10-21
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Post-DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 0.5 | 0 | 0.5 | 2024-10-21
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New | NULL | 2 | 15 | 7 | 8 | 2024-10-21
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New | NULL | 1 | 15 | 7 | 8 | 2024-10-21
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review R/W Setting Documents | New | NULL | 0.5 | 6.5 | 6 | 0.5 | 2023-01-17 13:30
46165 | Fiber Hut - Trinity Rest Area | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address QAQC IR comments | New | NULL | 4 | 7 | 0 | 7 | 2023-06-16
46165 | Fiber Hut - Trinity Rest Area | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate | New | NULL | 1 | 7 | 0 | 7 | 2023-06-16
46165 | Fiber Hut - Trinity Rest Area | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New | NULL | 2 | 7 | 0 | 7 | 2023-06-16
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New | NULL | 1 | 15 | 7 | 8 | 2024-10-21
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Post-DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 0.5 | 0 | 0.5 | 2024-10-28
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E SR comments | New | NULL | 1 | 16 | 15 | 1 | 2024-07-29
47998 | EA 74478 / 61087 - IR80 Jessup and Trinity Preservation Project | Actively Working | Post-DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 0.5 | 0 | 0.5 | 2024-07-29
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New | NULL | 2 | 17 | 0 | 17 | 2025-07-21
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 17 | 0 | 17 | 2025-07-21
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 17 | 0 | 17 | 2025-07-21
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E SR Comments | New | NULL | 2 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E SR (need A/C review) | New | NULL | 0.5 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC IR | New | NULL | 0 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC IR | New | NULL | 0 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New | NULL | 1 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New | NULL | 0 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New | NULL | 0 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New | NULL | 1 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | 1 | 17 | 0 | 17 | 2025-07-21
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Coordination Efforts | New | NULL | 0 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | NULL | 1 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | NULL | 1 | 9 | 0 | 9 | 2025-10-20
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 9 | 0 | 9 | 2025-10-20
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Signal Internal Review Comments | New | NULL | 2 | 13 | 0 | 13 | 2027-01-02
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR ITS Comments | New | NULL | 2 | 13 | 0 | 13 | 2027-01-02
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review comments | New | NULL | 1 | 13 | 0 | 13 | 2027-01-02
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR Signal Comments | New | NULL | 2 | 13 | 0 | 13 | 2027-01-02
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | NULL | 2 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | NULL | 2 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | NULL | 2 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | NULL | 2 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | NULL | 2 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 2 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 2 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | NULL | 1 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | NULL | 4 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 1 | 25 | 0 | 25 | 2026-04-13
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 25 | 0 | 25 | 2026-04-13
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New | NULL | 4 | 17 | 0 | 17 | 2025-07-21
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New | NULL | 2 | 17 | 0 | 17 | 2025-07-21
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New | NULL | 4 | 17 | 0 | 17 | 2025-07-21
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New | NULL | 2 | 17 | 0 | 17 | 2025-07-21
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | NULL | 0 | 17 | 0 | 17 | 2025-07-21
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New | NULL | 2 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New | NULL | 4 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | 1 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New | NULL | 2 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New | NULL | 4 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New | NULL | 2 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New | NULL | NULL | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | NULL | 0 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS QAQC IR | New | NULL | 2 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG QAQC IR | New | NULL | 2 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | NULL | 0.5 | 24 | 0 | 24 | 2025-03-03
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Post Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New | NULL | 0.5 | 0.5 | 0 | 0.5 | 2025-10-27
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 26 | 5 | 21 | 2024-11-15
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 2 | 26 | 5 | 21 | 2024-11-15
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | NULL | 2 | 26 | 5 | 21 | 2024-11-15
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | NULL | 6 | 26 | 5 | 21 | 2024-11-15
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 26 | 5 | 21 | 2024-11-15
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 1 | 26 | 5 | 21 | 2024-11-15
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 26 | 5 | 21 | 2024-11-15
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR ITS Comments | New | NULL | 2 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 2 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 1 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | NULL | 2 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | NULL | 2 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR Lighting Comments | New | NULL | 1 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit1 | New | NULL | 2 | 17.5 | 0 | 17.5 | 2025-10-20
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 0.5 | 0 | 0.5 | 2025-10-20
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Internal Review | New | NULL | 2 | 11.5 | 0 | 11.5 | 2025-01-27
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Internal Review Comments | New | NULL | 2 | 11.5 | 0 | 11.5 | 2025-01-27
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | NULL | 0.5 | 48.5 | 44 | 4.5 | 2024-07-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New | NULL | 1 | 48.5 | 44 | 4.5 | 2024-07-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | NULL | 2 | 48.5 | 44 | 4.5 | 2024-07-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 2 | 31 | 12.5 | 18.5 | 2025-09-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Shared Review Comments | New | NULL | 2 | 31 | 12.5 | 18.5 | 2025-09-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 1 | 31 | 12.5 | 18.5 | 2025-09-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 31 | 12.5 | 18.5 | 2025-09-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QAQC Internal Review | New | NULL | 0.5 | 31 | 12.5 | 18.5 | 2025-09-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 4 | 31 | 12.5 | 18.5 | 2025-09-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 2 | 31 | 12.5 | 18.5 | 2025-09-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 31 | 12.5 | 18.5 | 2025-09-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 31 | 12.5 | 18.5 | 2025-09-15
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | NULL | NULL | 5.5 | 0 | 5.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 5.5 | 0 | 5.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | NULL | 1 | 5.5 | 0 | 5.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | NULL | 2 | 5.5 | 0 | 5.5 | 2025-11-18
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | NULL | 2 | 5.5 | 0 | 5.5 | 2025-11-18
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | NULL | 2 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | NULL | 2 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | NULL | 2 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | NULL | 1 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 1 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | 1 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 1 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 1 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New | NULL | NULL | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | NULL | 0.5 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New | NULL | 0.5 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | NULL | 1 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | NULL | 1 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New | NULL | 1 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New | NULL | 10 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | NULL | 2 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | NULL | 0.5 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New | NULL | 1 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | NULL | 1 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | NULL | 1 | 57 | 33 | 24 | 2025-03-01
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 5.5 | 0 | 5.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | NULL | NULL | 5.5 | 0 | 5.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | NULL | 2 | 5.5 | 0 | 5.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | NULL | 1 | 5.5 | 0 | 5.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | NULL | 2 | 5.5 | 0 | 5.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | NULL | 4 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | NULL | 2 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | NULL | 2 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 1 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | NULL | 2 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 1 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | NULL | 1 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | NULL | 10 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 2 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 40.5 | 0 | 40.5 | 2025-08-20
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts | New | NULL | 0.5 | 8.5 | 2 | 6.5 | 2024-09-27
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | NULL | 1 | 8.5 | 2 | 6.5 | 2024-09-27
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | NULL | 1 | 8.5 | 2 | 6.5 | 2024-09-27
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 8.5 | 2 | 6.5 | 2024-09-27
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Post DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New | NULL | 1 | 1 | 0 | 1 | 2024-09-27
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | NULL | 13 | 9 | 4 | 2024-05-08
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 13 | 9 | 4 | 2024-05-08
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit (Review A/C) | New | NULL | 2 | 13 | 9 | 4 | 2024-05-08
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 0.5 | 0 | 0.5 | 2025-10-20
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 15 | 2 | 13 | 2025-10-20
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Comments | New | NULL | 4 | 15 | 2 | 13 | 2025-10-20
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 15 | 2 | 13 | 2025-10-20
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 15 | 2 | 13 | 2025-10-20
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 15 | 2 | 13 | 2025-10-20
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 15 | 2 | 13 | 2025-10-20
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 15 | 2 | 13 | 2025-10-20
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 15 | 2 | 13 | 2025-10-20
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 0.5 | 0 | 0.5 | 2024-01-08
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 11 | 0 | 11 | 2024-01-08
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address Internal Review Comments | New | NULL | 1 | 11 | 0 | 11 | 2024-01-08
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 11 | 0 | 11 | 2024-01-08
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Comments | New | NULL | 1 | 11 | 0 | 11 | 2024-01-08
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 11 | 0 | 11 | 2024-01-08
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 11 | 0 | 11 | 2024-01-08
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 11 | 0 | 11 | 2024-01-08
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 11 | 0 | 11 | 2024-01-08
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 11 | 0 | 11 | 2024-01-08
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | NULL | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | NULL | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New | NULL | 1 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New | NULL | NULL | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | NULL | 0.5 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New | NULL | 0.5 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team Intermediate Coordination Meeting | New | NULL | NULL | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | NULL | 1 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | NULL | 1 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New | NULL | 1 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New | NULL | 1 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | NULL | 2 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signals Special Details | New | NULL | 1 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | Approved | William Renter <wrenter@dot.nv.gov> | 1 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | Approved | NULL | 1 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | Approved | NULL | 1 | 78.5 | 56 | 22.5 | 2025-01-13
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 5.5 | 0 | 5.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | NULL | NULL | 5.5 | 0 | 5.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | NULL | 2 | 5.5 | 0 | 5.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | NULL | 1 | 5.5 | 0 | 5.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | NULL | 2 | 5.5 | 0 | 5.5 | 2025-10-27
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | NULL | 4 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | NULL | 2 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | NULL | 4 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 2 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New | NULL | NULL | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | NULL | 4 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | NULL | 2 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | NULL | 0 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New | NULL | NULL | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | NULL | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | NULL | NULL | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | NULL | NULL | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 2 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 25 | 0 | 25 | 2025-07-28
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 25 | 0 | 25 | 2025-07-28
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting and Signal Address Shared Review Comments | New | NULL | 2 | 60.5 | 50.5 | 10 | 2026-03-08
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 60.5 | 50.5 | 10 | 2026-03-08
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 60.5 | 50.5 | 10 | 2026-03-08
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | NULL | 0.5 | 60.5 | 50.5 | 10 | 2026-03-08
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 60.5 | 50.5 | 10 | 2026-03-08
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | NULL | 2 | 60.5 | 50.5 | 10 | 2026-03-08
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | NULL | 2 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New | NULL | 2 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | NULL | 1 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | NULL | 2 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | 1 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 20.5 | 0 | 20.5 | 2026-12-21
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS Details | New | NULL | 2 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New | NULL | 4 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | 2 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New | NULL | 4 | 26.5 | 0 | 26.5 | 2025-10-25
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cleanup | New | NULL | 2 | 40.5 | 0 | 40.5 | 2025-08-20
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New | NULL | 2 | 26.5 | 0 | 26.5 | 2025-10-25
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | NULL | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | NULL | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 1 | 7.5 | 1 | 6.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 7.5 | 1 | 6.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 7.5 | 1 | 6.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 1 | 7.5 | 1 | 6.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | NULL | 1 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | NULL | 1 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 0.5 | 0 | 0.5 | 2025-08-12
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | NULL | 1 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 0.5 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | NULL | 0.5 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 0.5 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 1 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 15 | 5 | 10 | 2025-08-27
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 15 | 5 | 10 | 2025-08-27
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Pull Box Theft Mitigation | New | NULL | NULL | 57 | 33 | 24 | 2025-03-01
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New | NULL | 4 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New | NULL | 4 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New | NULL | 2 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New | NULL | NULL | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New | NULL | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | NULL | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | NULL | 2 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | NULL | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | NULL | 4 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | NULL | 2 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 2 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | NULL | 2 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | NULL | 4 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | NULL | 4 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New | NULL | NULL | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New | NULL | NULL | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | NULL | 0 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | NULL | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | NULL | NULL | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | NULL | NULL | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 2 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 24 | 0 | 24 | 2025-07-21
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | NULL | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | NULL | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | NULL | NULL | 5.5 | 0 | 5.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 5.5 | 0 | 5.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | NULL | 1 | 5.5 | 0 | 5.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | NULL | 2 | 5.5 | 0 | 5.5 | 2025-09-29
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | NULL | 2 | 5.5 | 0 | 5.5 | 2025-09-29
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Coordination items | New | NULL | 4 | 16 | 0 | 16 | 2030-01-01
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | K2-1 updates | New | NULL | 2 | 27.5 | 22.5 | 5 | 2024-11-27
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS labels | Approved | NULL | 4 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS schedules | Approved | NULL | 6 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General notes | Approved | NULL | 1 | 121 | 25 | 96 | 2022-04-25
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | NULL | 2 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | NULL | 2 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | NULL | 2 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Respond to QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 2 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 20 | 0 | 20 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | NULL | 1 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | NULL | 2 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 2 | 8 | 0 | 8 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | NULL | 2 | 8 | 0 | 8 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | NULL | 2 | 8 | 0 | 8 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | NULL | 2 | 8 | 0 | 8 | 2027-12-01
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | NULL | 2 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 2 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | NULL | 2 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | NULL | 4 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Respond to QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 2 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 2 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 46.5 | 21.5 | 25 | 2026-01-11
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 46.5 | 21.5 | 25 | 2026-01-11
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New | NULL | 2 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Schedule & Structure List | New | NULL | 6 | 39.5 | 5 | 34.5 | 2024-12-13
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Special Details | New | NULL | 1 | 39.5 | 5 | 34.5 | 2024-12-13
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal labels | Approved | NULL | 2 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting labels | Approved | NULL | 4 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal schedules | Approved | NULL | 4 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting schedules | Approved | NULL | 6 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General notes | Approved | NULL | 1 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General notes | Approved | NULL | 1 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | Approved | NULL | 4 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Add Underdeck Lighting | Approved | NULL | 2 | 121 | 25 | 96 | 2022-04-25
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New | NULL | NULL | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New | NULL | NULL | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | NULL | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | NULL | 1 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New | NULL | 1 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | NULL | 4 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New | NULL | 6 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | NULL | 1 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | NULL | 1 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New | NULL | 1 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | NULL | 1 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | NULL | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New | NULL | 0.5 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New | NULL | 2 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | NULL | 2 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New | NULL | 2 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | NULL | 2 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject IR comments | New | NULL | 1 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | NULL | 56.5 | 39 | 17.5 | 2024-09-17
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 0.5 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | NULL | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | NULL | 0.5 | 6 | 0 | 6 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 6 | 0 | 6 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | NULL | 1 | 6 | 0 | 6 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | NULL | 2 | 6 | 0 | 6 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | NULL | 2 | 6 | 0 | 6 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments PS&E Internal Review | New | NULL | 6 | 26 | 0 | 26 | 2026-07-27
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Verify Network Connection Evaluation | New | NULL | 0 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Verify Network Analysis Info | New | NULL | 0 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Redesign southern interchange at I-80/McCarran | New | NULL | 1 | 121 | 25 | 96 | 2022-04-25
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Post-DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | NULL | 0.5 | 0.5 | 0 | 0.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Post-DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | NULL | NULL | 0.5 | 0 | 0.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | NULL | 1 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 1 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | NULL | 2 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | NULL | 1 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New | NULL | 2 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | NULL | 2 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New | NULL | 4 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | NULL | 1 | 23.5 | 0 | 23.5 | 2026-12-28
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | NULL | 1 | 23.5 | 0 | 23.5 | 2026-12-28
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Finish Lighting linework | New | NULL | 6 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Finish ITS linework | New | NULL | 6 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Print PDF and Submit | New | NULL | 1 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New | NULL | 2 | 121 | 25 | 96 | 2022-04-25
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | NULL | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | NULL | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | NULL | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | NULL | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lead Designer Response to IMD IR comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review Comments & Responses | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Specs Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 5.5 | 0 | 5.5 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | NULL | 5.5 | 0 | 5.5 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 5.5 | 0 | 5.5 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 5.5 | 0 | 5.5 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 5.5 | 0 | 5.5 | 2026-02-16
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Design - Coversheet/Key Map | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Design - General Notes | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0 | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review Comments & Responses | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | NULL | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Internal Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review and PS&E Shared Review - Comment Revisions | New | NULL | 4 | 31 | 12.5 | 18.5 | 2025-09-15
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm PS&E Internal Review Comments | New | NULL | 0.5 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | NULL | NULL | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | NULL | NULL | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | NULL | 4 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 2 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | NULL | 4 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | NULL | 2 | 26 | 0 | 26 | 2026-07-27
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LGT IR Comments | New | NULL | 2 | 16.5 | 0 | 16.5 | 2026-05-10
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New | NULL | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New | NULL | 2 | 21 | 0 | 21 | 2025-02-24
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E Review comments | New | NULL | 2 | 21 | 0 | 21 | 2025-02-24
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New | NULL | 1 | 21 | 0 | 21 | 2025-02-24
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 21 | 0 | 21 | 2025-02-24
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 1 | 21 | 0 | 21 | 2025-02-24
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Additional Doc items needed for SLI Standalone project | New | NULL | 8 | 21 | 0 | 21 | 2025-02-24
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Internal Review of QAQC Submittal | New | NULL | 2 | 21 | 0 | 21 | 2025-02-24
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address QAQC Internal Review comments | New | NULL | 4 | 21 | 0 | 21 | 2025-02-24
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Field Visit | New | NULL | 2 | 36 | 2 | 34 | 2024-09-23
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject PS&E Shared Review comments | New | NULL | 1 | 16.5 | 0 | 16.5 | 2026-05-10
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review Comments | New | NULL | 2 | 13 | 0 | 13 | 2027-01-02
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Shared Review Comments | New | NULL | 1 | 13 | 0 | 13 | 2027-01-02
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New | NULL | 2 | 13 | 0 | 13 | 2027-01-02
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 1 | 13 | 0 | 13 | 2027-01-02
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS design | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 57 | 33 | 24 | 2025-03-01
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New | NULL | 2 | 11.5 | 0 | 11.5 | 2025-10-27
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New | NULL | 1 | 11.5 | 0 | 11.5 | 2025-10-27
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS QAQC IR comments | New | NULL | 2 | 11.5 | 0 | 11.5 | 2025-10-27
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address LTG QAQC IR comments | New | NULL | 2 | 11.5 | 0 | 11.5 | 2025-10-27
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E Review comments | New | NULL | 2 | 11.5 | 0 | 11.5 | 2025-10-27
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 11.5 | 0 | 11.5 | 2025-10-27
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 1 | 11.5 | 0 | 11.5 | 2025-10-27
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Statewide ITS Spreadsheet | New | NULL | 0.5 | 11.5 | 0 | 11.5 | 2025-10-27
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Update Schedules & Structure List | New | NULL | 2 | 46.5 | 21.5 | 25 | 2026-01-11
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Shared Review Comments | New | NULL | 2 | 11.5 | 0 | 11.5 | 2025-01-27
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | NULL | 2 | 27.5 | 22.5 | 5 | 2024-11-27
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 1 | 27.5 | 22.5 | 5 | 2024-11-27
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | NULL | 2 | 11.5 | 0 | 11.5 | 2025-01-27
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | NULL | 2 | 11.5 | 0 | 11.5 | 2025-01-27
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update ITS Structure List | New | NULL | 2 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - ITS | New | NULL | 4 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Lighting | New | NULL | 4 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Signals | New | NULL | 4 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide comments in NDOT shared review session | New | NULL | 2 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address comments from NDOT shared review | New | NULL | 2 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update ITS construction notes | New | NULL | 2 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Signals Structure List | New | NULL | 2 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Signals construction notes | New | NULL | 1 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Finish Signals linework | New | NULL | 4 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Lighting construction notes | New | NULL | 2 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Lighting Structure List | New | NULL | 2 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review | New | NULL | 12 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTP Comments Review - QAQC | New | NULL | 1 | 121 | 25 | 96 | 2022-04-25
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS comments from NDOT shared review | New | NULL | 1 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - ITS | New | NULL | 2 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Signals | New | NULL | 2 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Signals comments from NDOT shared review | New | NULL | 1 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Lighting | New | NULL | 2 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting comments from NDOT shared review | New | NULL | 1 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide comments in NDOT shared review session | New | NULL | 2 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New | NULL | 1 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Print PDF and Submit | New | NULL | 1 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New | NULL | 2 | 17 | 0 | 17 | 2022-07-18
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address comments from NDOT shared review | New | NULL | 2 | 17 | 0 | 17 | 2022-07-18
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clean up schedules | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 2 | 34 | 2024-09-23
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Update & send SP request | New | NULL | 1 | 57 | 33 | 24 | 2025-03-01
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General Notes | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels | New | NULL | 4 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New | NULL | 2 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedule & Structure List | New | NULL | 4 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Cutting Sheets | New | NULL | 2 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Special Details | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New | NULL | 8 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New | NULL | 0.25 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New | NULL | 6 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New | NULL | 2 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels (check PMP) | New | NULL | 6 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New | NULL | 4 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | New | NULL | 2 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Voltage Drop | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedule & Structure List | New | NULL | 4 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New | NULL | 2 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cutting Sheets | New | NULL | 4 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & Labels | New | NULL | 6 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | NULL | 2 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit (review A/C) | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New | NULL | 12 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | NULL | 1 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | NULL | 0.5 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | TOTs Coordination | New | NULL | 0.5 | 85.25 | 0 | 85.25 | 2022-11-14
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | NULL | 4 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | NULL | 2 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 2 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | NULL | 2 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | NULL | 4 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | NULL | 4 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 1 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | NULL | 2 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | NULL | 2 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 1 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | NULL | 2 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | NULL | 1 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | NULL | 1 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | NULL | 1 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 0.5 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | NULL | 1 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 14 | 0 | 14 | 2023-05-06
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New | NULL | 0.5 | 14 | 0 | 14 | 2023-05-06
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New | Jordan James <jjames@dot.nv.gov> | 1 | 121 | 25 | 96 | 2022-04-25
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plan sheets | New | NULL | 4 | 16 | 0 | 16 | 2030-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plans & Schedules | New | NULL | 4 | 16 | 0 | 16 | 2030-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Circuit Analysis | New | NULL | 2 | 16 | 0 | 16 | 2030-01-01
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New | NULL | 2 | 16 | 0 | 16 | 2030-01-01
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | NULL | 4 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 2 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | NULL | 2 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | NULL | 4 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | NULL | 1 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | NULL | 1 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | NULL | 2 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | NULL | 2 | 15 | 0 | 15 | 2025-10-20
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | NULL | 2 | 15 | 0 | 15 | 2025-10-20
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | NULL | 2 | 15 | 0 | 15 | 2025-10-20
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | NULL | 2 | 15 | 0 | 15 | 2025-10-20
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | NULL | 1 | 15 | 0 | 15 | 2025-10-20
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | NULL | 1 | 15 | 0 | 15 | 2025-10-20
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | NULL | 1 | 15 | 0 | 15 | 2025-10-20
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 4 | 15 | 0 | 15 | 2025-10-20
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review (need A/C review) | New | NULL | 1 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | NULL | 2 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject Comments on QA/QC Internal Review | New | NULL | 2 | 36 | 2 | 34 | 2024-09-23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Internal Review | New | NULL | 6 | 36 | 2 | 34 | 2024-09-23
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team Intermediate Coordination Meeting | New | NULL | 0.5 | 28 | 0 | 28 | 2024-08-07
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New | NULL | 4 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New | NULL | 2 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New | NULL | 2 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New | NULL | 8 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New | NULL | 2 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New | NULL | 1 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels 1/2 | New | NULL | 8 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New | NULL | 4 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General Notes | New | NULL | 1 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels 1/2 | New | NULL | 8 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New | NULL | 2 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedule & Structure List | New | NULL | 6 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Cutting Sheets | New | NULL | 6 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New | NULL | 2 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Special Details | New | NULL | 2 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | NULL | 2 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New | NULL | 0.5 | 28 | 0 | 28 | 2024-08-07
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New | NULL | 0.5 | 28 | 0 | 28 | 2024-08-07
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts - needs custom criteria when importing | New | NULL | NULL | 28 | 0 | 28 | 2024-08-07
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | IMD Estimate | New | NULL | 1 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | IMD Structure List | New | NULL | 2 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | IMD Compile and Submit (Review A/C) | New | NULL | 4 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Signal Internal Review | New | NULL | 4 | 28 | 0 | 28 | 2024-08-07
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | NULL | 2 | 28 | 0 | 28 | 2024-08-07
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 2 | 28 | 0 | 28 | 2024-08-07
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 28 | 0 | 28 | 2024-08-07
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | NULL | 1 | 28 | 0 | 28 | 2024-08-07
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts - needs custom criteria when importing | New | NULL | NULL | 16 | 0 | 16 | 2024-04-11
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address IR Comments | New | NULL | 4 | 16 | 0 | 16 | 2024-04-11
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address SR Comments | New | NULL | 2 | 16 | 0 | 16 | 2024-04-11
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address IR Comments | New | NULL | 4 | 16 | 0 | 16 | 2024-04-11
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address SR Comments | New | NULL | 2 | 16 | 0 | 16 | 2024-04-11
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | NULL | 1 | 16 | 0 | 16 | 2024-04-11
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | NULL | 1 | 16 | 0 | 16 | 2024-04-11
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | NULL | 2 | 16 | 0 | 16 | 2024-04-11
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Post Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New | NULL | NULL | NULL | 0 | NULL | 2024-04-11
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New | NULL | NULL | NULL | 0 | NULL | 2025-02-24
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | NULL | 1 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | NULL | 1 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | NULL | 12 | 35.5 | 0 | 35.5 | 2023-03-20
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | NULL | 0.5 | 35.5 | 0 | 35.5 | 2023-03-20
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Additional Estimated EP (BUFFER) | New | NULL | NULL | 16 | 0 | 16 | 2024-04-11
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review Comments | New | NULL | 0 | 11.5 | 0 | 11.5 | 2025-01-27
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review Comments | New | NULL | 0 | 11.5 | 0 | 11.5 | 2025-01-27
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Devices added to Spreadsheet | New | NULL | 0.5 | 11.5 | 0 | 11.5 | 2025-01-27
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | NULL | 1 | 11.5 | 0 | 11.5 | 2025-01-27
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Pole Assessment & Scoping | Approved | Adji Witjaksono <awitjaksono@dot.nv.gov> | 2 | 21.5 | 14.5 | 7 | 2022-11-30 13:30
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels 2/2 | New | NULL | 8 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels 2/2 | New | NULL | 8 | 84 | 1 | 83 | 2023-08-14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Lighting Internal Review | New | NULL | 4 | 28 | 0 | 28 | 2024-08-07

## Resource_Leaves
Resource | Active | Sprint 1 (2020) | Sprint 2 (2020) | Sprint 3 (2020) | Sprint 4 (2020) | Sprint 5 (2020) | Sprint 6 (2020) | Sprint 7 (2020) | Sprint 8 (2020) | Sprint 9 (2020) | Sprint 10 (2020) | Sprint 11 (2020) | Sprint 1 (2021) | Sprint 2 (2021) | Sprint 3 (2021) | Sprint 4 (2021) | Sprint 5 (2021) | Sprint 6 (2021) | Sprint 7 (2021) | Sprint 8 (2021) | Sprint 9 (2021) | Sprint 10 (2021) | Sprint 11 (2021) | Sprint 12 (2021) | Sprint 13 (2021) | Sprint 14 (2021) | Sprint 15 (2021) | Sprint 16 (2021) | Sprint 17 (2021) | Sprint 18 (2021) | Sprint 19 (2021) | Sprint 20 (2021) | Sprint 21 (2021) | Sprint 22 (2021) | Sprint 23 (2021) | Sprint 24 (2021) | Sprint 25 (2021) | Sprint 26 (2021) | Sprint 1 (2022) | Sprint 2 (2022) | Sprint 3 (2022) | Sprint 4 (2022) | Sprint 5 (2022) | Sprint 6 (2022) | Sprint 7 (2022) | Sprint 8 (2022) | Sprint 9 (2022) | Sprint 10 (2022) | Sprint 11 (2022) | Sprint 12 (2022) | Sprint 13 (2022) | Sprint 14 (2022) | Sprint 15 (2022) | Sprint 16 (2022) | Sprint 17 (2022) | Sprint 18 (2022) | Sprint 19 (2022) | Sprint 20 (2022) | Sprint 21 (2022) | Sprint 22 (2022) | Sprint 23 (2022) | Sprint 24 (2022) | Sprint 25 (2022) | Sprint 26 (2022) | Sprint 27 (2022) | Sprint 1 (2023) | Sprint 2 (2023) | Sprint 3 (2023) | Sprint 4 (2023) | Sprint 5 (2023) | Sprint 6 (2023) | Sprint 7 (2023) | Sprint 8 (2023) | Sprint 9 (2023) | Sprint 10 (2023) | Sprint 11 (2023) | Sprint 12 (2023) | Sprint 13 (2023) | Sprint 14 (2023) | Sprint 15 (2023) | Sprint 16 (2023) | Sprint 17 (2023) | Sprint 18 (2023) | Sprint 19 (2023) | Sprint 20 (2023) | Sprint 21 (2023) | Sprint 22 (2023) | Sprint 23 (2023) | Sprint 24 (2023) | Sprint 25 (2023) | Sprint 26 (2023) | Sprint 1 (2024) | Sprint 2 (2024) | Sprint 3 (2024) | Sprint 4 (2024) | Sprint 5 (2024) | Sprint 6 (2024) | Sprint 7 (2024) | Sprint 8 (2024) | Sprint 9 (2024) | Sprint 10 (2024) | Sprint 11 (2024) | Sprint 12 (2024) | Sprint 13 (2024) | Sprint 14 (2024) | Sprint 15 (2024) | Sprint 16 (2024) | Sprint 17 (2024) | Sprint 18 (2024) | Sprint 19 (2024) | Sprint 20 (2024) | Sprint 21 (2024) | Sprint 22 (2024) | Sprint 23 (2024) | Sprint 24 (2024) | Sprint 25 (2024) | Sprint 26 (2024) | Sprint 1 (2025) | Sprint 2 (2025) | Sprint 3 (2025) | Sprint 4 (2025) | Sprint 5 (2025) | Sprint 6 (2025) | Sprint 7 (2025) | Sprint 8 (2025) | Sprint 9 (2025) | Sprint 10 (2025) | Sprint 11 (2025) | Sprint 12 (2025) | Sprint 13 (2025) | Sprint 14 (2025) | Sprint 15 (2025) | Sprint 16 (2025) | Sprint 17 (2025) | Sprint 18 (2025) | Sprint 19 (2025) | Sprint 20 (2025) | Sprint 21 (2025) | Sprint 22 (2025) | Sprint 23 (2025) | Sprint 24 (2025) | Sprint 25 (2025) | Sprint 26 (2025)
Jordan James <jjames@dot.nv.gov> |  | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 2 | 0 | 1 | 2 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 0 | 2 | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 1 | 0 | 0
Kaur, Navneet <nkaur@dot.nv.gov> |  | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 0 | 2 | 0 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 1 | 0 | 2 | 2 | 2 | 0 | 2 | 0 | 2 | 1 | 1 | 2 | 1 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 1 | 2 | 0 | 1 | 2 | 2 | 1 | 0 | 1 | 1 | 1 | 2 | 0 | 2 | 0 | 1 | 2 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 1 | 1 | 0 | 2 | 0 | 2 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 1 | 2 | 1 | 2 | 0 | 2 | 2 | 0 | 2 | 1 | 1 | 1 | 2 | 0 | 2 | 2 | 1 | 0 | 2 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 2
Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> |  | 2 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 2 | 0 | 2 | 2 | 1 | 2 | 0 | 1 | 2 | 0 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 1
Gurpreet Singh Rai <grai@dot.nv.gov> |  | 2 | 2 | 0 | 1 | 0 | 2 | 2 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 0 | 1 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 1 | 0 | 2 | 1 | 1 | 2 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0
Austin Hoekstra <ahoekstra@dot.nv.gov> |  | 0 | 2 | 1 | 1 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 1 | 2 | 1 | 0 | 2 | 0 | 1 | 2 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 2 | 2 | 2 | 1 | 0 | 2 | 2 | 0 | 0 | 1 | 2 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 2 | 0 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 2 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 2 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0
Laura Vargo <lvargo@dot.nv.gov> |  | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 1 | 2 | 0 | 2 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 0 | 1 | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 2 | 1 | 2 | 0 | 1 | 1 | 1 | 2 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 1 | 1 | 2 | 1 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 2
Brian Dodds <btdodds@dot.nv.gov> |  | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 2 | 2 | 1 | 0 | 2 | 2 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 0 | 2 | 0 | 2 | 1 | 2 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 2 | 2 | 1 | 2 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 1 | 0 | 2
Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 2 | 2 | 2 | 0 | 2 | 0 | 2 | 2 | 1 | 0 | 1 | 0 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 2 | 1 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 1 | 0 | 2 | 1 | 1 | 1 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 2 | 1
Alesha Jackson <ajackson@dot.nv.gov> |  | 2 | 1 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 0 | 2 | 0 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 2 | 0 | 2 | 1 | 1 | 2 | 1 | 2 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 1 | 2 | 0 | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 0 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 0 | 0 | 2 | 2 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 1 | 1 | 2 | 0 | 0
Connie Ullas <cullas@dot.nv.gov> |  | 2 | 2 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 2 | 1 | 1 | 2 | 0 | 2 | 1 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 1 | 2 | 2 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 2 | 1 | 2
William Renter <wrenter@dot.nv.gov> |  | 2 | 1 | 2 | 0 | 2 | 0 | 2 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 2 | 0 | 1 | 2 | 0 | 1 | 2 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 1 | 1 | 1 | 2 | 1 | 0 | 2 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 1 | 2 | 0 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 2 | 2 | 0 | 1 | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 2 | 0 | 1
Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> |  | 0 | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | 1 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 2 | 2 | 0 | 2 | 1 | 2 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 2 | 2 | 1 | 2 | 0 | 1 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 1 | 1 | 0 | 2 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 2 | 1 | 2 | 0 | 0 | 2 | 0 | 1 | 2 | 2 | 0 | 1 | 0 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 1
Alex Traeger <atraeger.ctr@dot.nv.gov> |  | 2 | 2 | 0 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 2 | 0 | 1 | 2 | 1 | 2 | 0 | 0 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 2 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 2 | 1 | 1 | 0 | 2 | 1 | 2 | 2 | 0 | 0 | 1 | 1 | 2 | 1 | 2 | 2 | 0 | 2 | 1 | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 2 | 1 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 1 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 2 | 0 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1
Brittany Brickman <bbrickman@dot.nv.gov> |  | 1 | 0 | 1 | 2 | 2 | 2 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 1 | 2 | 1 | 0 | 2 | 0 | 2 | 2 | 1 | 0 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 0 | 0 | 1 | 1 | 2 | 0 | 2 | 2 | 1 | 1 | 0 | 2 | 1 | 2 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 1 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 2 | 2 | 0 | 2 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 2 | 2 | 2 | 1 | 2 | 1 | 0 | 1 | 2 | 0 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2
Frederick Tydeman <FTydeman@dot.nv.gov> |  | 0 | 2 | 1 | 0 | 1 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 2 | 1 | 1 | 2 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 2 | 2 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 1 | 2 | 1 | 0 | 2 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 2 | 1 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 2 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 2 | 2 | 0 | 1 | 1 | 2
Shaza Elshazli <selshazli@dot.nv.gov> |  | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 2 | 0 | 1 | 0 | 2 | 2 | 1 | 0 | 2 | 2 | 1 | 2 | 0 | 1 | 1 | 0 | 2 | 0 | 2 | 0 | 1 | 1 | 2 | 2 | 1 | 0 | 1 | 2 | 0 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 2 | 1 | 2 | 1 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 2 | 1 | 0 | 2 | 2 | 1 | 0 | 0 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 0 | 1 | 0 | 1 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 0 | 1 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 2 | 0 | 1 | 2 | 2 | 0 | 2 | 1 | 0 | 2 | 1 | 0
Fernando Torres <ftorres@dot.nv.gov> |  | 1 | 2 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 0 | 2 | 1 | 2 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 0 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 0 | 2 | 2 | 0 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 2 | 2 | 0 | 2 | 2 | 1 | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 0 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 0
Eric Macgill <emacgill@dot.nv.gov> |  | 1 | 2 | 1 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 0 | 1 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 2 | 2 | 0 | 1 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 2 | 2 | 1 | 0 | 2 | 2 | 2 | 0 | 2 | 2 | 0 | 2 | 0 | 1 | 0 | 2 | 2 | 0 | 1 | 2 | 2 | 2 | 1 | 2 | 2
Victoria Jeffery <vjeffery@dot.nv.gov> |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 2 | 2 | 1 | 2 | 2 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 2 | 0 | 2 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 2 | 0 | 1 | 0 | 2 | 2 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 1 | 1 | 0 | 1 | 0 | 1
Elias-Zarate, Brenda <beliaszarate@dot.nv.gov> |  | 0 | 0 | 1 | 0 | 0 | 2 | 1 | 1 | 2 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 2 | 0 | 0 | 2 | 2 | 1 | 0 | 2 | 2 | 2 | 2 | 0 | 2 | 1 | 1 | 2 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | 2 | 1 | 2 | 2 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 2 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 2 | 0 | 2 | 2 | 1 | 2 | 2 | 0 | 2 | 1
Brenda.eliaszarate <Brenda.eliaszarate@hdrinc.com> |  | 0 | 2 | 0 | 2 | 2 | 2 | 0 | 2 | 0 | 1 | 1 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 1 | 2 | 1 | 2 | 2 | 2 | 1 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 1 | 2 | 2 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 2 | 0 | 1 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 2 | 1 | 1 | 2 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 1 | 1
Austin.hoekstra <Austin.hoekstra@atkinsglobal.com> |  | 1 | 1 | 2 | 0 | 2 | 1 | 1 | 0 | 1 | 2 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 2 | 0 | 2 | 2 | 0 | 1 | 1 | 0 | 2 | 1 | 0 | 2 | 1 | 1 | 2 | 0 | 2 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 2 | 1 | 0 | 2 | 1 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 1 | 0 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 2 | 0 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 1 | 2 | 2 | 1 | 0 | 2 | 0 | 0 | 0
Adji Witjaksono <awitjaksono@dot.nv.gov> |  | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 2 | 2 | 1 | 2 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 2 | 2 | 0 | 2 | 1 | 1 | 1 | 2 | 0 | 2 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 2 | 1 | 2 | 0 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 0 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 0 | 1 | 2 | 2 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 2 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 2 | 1 | 0 | 1 | 1

## Holidays_in_sprint
Sprint | Holidays
Sprint 1 (2020) | 0
Sprint 2 (2020) | 0
Sprint 3 (2020) | 1
Sprint 4 (2020) | 0
Sprint 5 (2020) | 0
Sprint 6 (2020) | 1
Sprint 7 (2020) | 0
Sprint 8 (2020) | 1
Sprint 9 (2020) | 1
Sprint 10 (2020) | 0
Sprint 11 (2020) | 1
Sprint 1 (2021) | 0
Sprint 2 (2021) | 1
Sprint 3 (2021) | 0
Sprint 4 (2021) | 1
Sprint 5 (2021) | 0
Sprint 6 (2021) | 0
Sprint 7 (2021) | 0
Sprint 8 (2021) | 0
Sprint 9 (2021) | 0
Sprint 10 (2021) | 0
Sprint 11 (2021) | 1
Sprint 12 (2021) | 0
Sprint 13 (2021) | 0
Sprint 14 (2021) | 1
Sprint 15 (2021) | 0
Sprint 16 (2021) | 0
Sprint 17 (2021) | 0
Sprint 18 (2021) | 1
Sprint 19 (2021) | 0
Sprint 20 (2021) | 0
Sprint 21 (2021) | 1
Sprint 22 (2021) | 0
Sprint 23 (2021) | 1
Sprint 24 (2021) | 1
Sprint 25 (2021) | 0
Sprint 26 (2021) | 1
Sprint 1 (2022) | 1
Sprint 2 (2022) | 1
Sprint 3 (2022) | 0
Sprint 4 (2022) | 1
Sprint 5 (2022) | 0
Sprint 6 (2022) | 0
Sprint 7 (2022) | 0
Sprint 8 (2022) | 0
Sprint 9 (2022) | 0
Sprint 10 (2022) | 0
Sprint 11 (2022) | 1
Sprint 12 (2022) | 0
Sprint 13 (2022) | 0
Sprint 14 (2022) | 1
Sprint 15 (2022) | 0
Sprint 16 (2022) | 0
Sprint 17 (2022) | 0
Sprint 18 (2022) | 1
Sprint 19 (2022) | 0
Sprint 20 (2022) | 0
Sprint 21 (2022) | 1
Sprint 22 (2022) | 0
Sprint 23 (2022) | 1
Sprint 24 (2022) | 1
Sprint 25 (2022) | 0
Sprint 26 (2022) | 1
Sprint 27 (2022) | 0
Sprint 1 (2023) | 1
Sprint 2 (2023) | 0
Sprint 3 (2023) | 1
Sprint 4 (2023) | 0
Sprint 5 (2023) | 0
Sprint 6 (2023) | 0
Sprint 7 (2023) | 0
Sprint 8 (2023) | 0
Sprint 9 (2023) | 0
Sprint 10 (2023) | 1
Sprint 11 (2023) | 0
Sprint 12 (2023) | 0
Sprint 13 (2023) | 1
Sprint 14 (2023) | 0
Sprint 15 (2023) | 0
Sprint 16 (2023) | 0
Sprint 17 (2023) | 1
Sprint 18 (2023) | 0
Sprint 19 (2023) | 0
Sprint 20 (2023) | 1
Sprint 21 (2023) | 0
Sprint 22 (2023) | 1
Sprint 23 (2023) | 1
Sprint 24 (2023) | 0
Sprint 25 (2023) | 1
Sprint 26 (2023) | 0
Sprint 1 (2024) | 1
Sprint 2 (2024) | 0
Sprint 3 (2024) | 1
Sprint 4 (2024) | 0
Sprint 5 (2024) | 0
Sprint 6 (2024) | 0
Sprint 7 (2024) | 0
Sprint 8 (2024) | 0
Sprint 9 (2024) | 0
Sprint 10 (2024) | 1
Sprint 11 (2024) | 0
Sprint 12 (2024) | 0
Sprint 13 (2024) | 1
Sprint 14 (2024) | 0
Sprint 15 (2024) | 0
Sprint 16 (2024) | 0
Sprint 17 (2024) | 1
Sprint 18 (2024) | 0
Sprint 19 (2024) | 0
Sprint 20 (2024) | 1
Sprint 21 (2024) | 0
Sprint 22 (2024) | 1
Sprint 23 (2024) | 1
Sprint 24 (2024) | 0
Sprint 25 (2024) | 1
Sprint 26 (2024) | 0
Sprint 1 (2025) | 1
Sprint 2 (2025) | 0
Sprint 3 (2025) | 1
Sprint 4 (2025) | 0
Sprint 5 (2025) | 0
Sprint 6 (2025) | 0
Sprint 7 (2025) | 0
Sprint 8 (2025) | 0
Sprint 9 (2025) | 0
Sprint 10 (2025) | 1
Sprint 11 (2025) | 0
Sprint 12 (2025) | 0
Sprint 13 (2025) | 1
Sprint 14 (2025) | 0
Sprint 15 (2025) | 0
Sprint 16 (2025) | 0
Sprint 17 (2025) | 1
Sprint 18 (2025) | 0
Sprint 19 (2025) | 0
Sprint 20 (2025) | 1
Sprint 21 (2025) | 0
Sprint 22 (2025) | 1
Sprint 23 (2025) | 1
Sprint 24 (2025) | 0
Sprint 25 (2025) | 1
Sprint 26 (2025) | 0