## Sheet1
Project_ID | Project_title | Project_state | Epic_Title | Project_Assigned_To | Iteration Path | PBI_Title | PBI_State | PBI_Assigned_To | PBI_Efforts | Epic_TotalEfforts | Epic_Completed_Efforts | Epic_Pending_Efforts | Due_Date | Anchor Project
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Review Traffic-rated Heavy lid detail | New |  |  | 146 | 136 | 10 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | General Notes Master Sheet | New |  |  | 146 | 136 | 10 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Structure List Plotting Troubleshooting | New |  | 1 | 146 | 136 | 10 |  | TRUE
39835 | Miscellaneous Items | Actively Working | Miscellaneous Items | Eric Macgill <emacgill@dot.nv.gov> | Signals Lighting and ITS | Add 14 PBIs - 7 for adding notes for DG and 7 for adding notes for standard plans | New |  |  | 146 | 136 | 10 |  | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review R/W Setting Documents | New |  | 0.5 | 6.5 | 6 | 0.5 |  | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 4 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 2 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 2 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 8 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 2 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels 1/2 | New |  | 8 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 4 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General Notes | New |  | 1 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels 1/2 | New |  | 8 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New |  | 2 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedule & Structure List | New |  | 6 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Cutting Sheets | New |  | 6 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 2 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Special Details | New |  | 2 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | IMD Estimate | New |  | 1 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | IMD Structure List | New |  | 2 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | IMD Compile and Submit (Review A/C) | New |  | 4 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels 2/2 | New |  | 8 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels 2/2 | New |  | 8 | 84 | 1 | 83 | 2023-08-14 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Lighting Internal Review | New |  | 4 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team Intermediate Coordination Meeting | New |  | 0.5 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Signal Internal Review | New |  | 4 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 2 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  | 0.5 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New |  | 0.5 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts - needs custom criteria when importing | New |  |  | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | 12 EP to be created into "Address Comments" PBI's | New |  | 13 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts - needs custom criteria when importing | New |  |  | 16 | 0 | 16 | 2024-04-11 13:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address IR Comments | New |  | 4 | 16 | 0 | 16 | 2024-04-11 13:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address SR Comments | New |  | 2 | 16 | 0 | 16 | 2024-04-11 13:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address IR Comments | New |  | 4 | 16 | 0 | 16 | 2024-04-11 13:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address SR Comments | New |  | 2 | 16 | 0 | 16 | 2024-04-11 13:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 16 | 0 | 16 | 2024-04-11 13:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 16 | 0 | 16 | 2024-04-11 13:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 16 | 0 | 16 | 2024-04-11 13:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Additional Estimated EP (BUFFER) | New |  |  | 16 | 0 | 16 | 2024-04-11 13:30 | TRUE
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | Post Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  |  |  | 0 |  | 2024-04-11 13:30 | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clean up schedules | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review (need A/C review) | New |  | 1 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject Comments on QA/QC Internal Review | New |  | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Internal Review | New |  | 6 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Field Visit | New |  | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 2 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 1 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 4 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 27.5 | 22.5 | 5 | 2024-11-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 27.5 | 22.5 | 5 | 2024-11-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | K2-1 updates | New |  | 2 | 27.5 | 22.5 | 5 | 2024-11-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Internal Review | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Internal Review Comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review Comments | New |  | 0 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review Comments | New |  | 0 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Devices added to Spreadsheet | New |  | 0.5 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Shared Review Comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Scope Summary and Survey to D2 | New |  |  | 8 | 2 | 6 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Cut Lighting Sheets | New |  | 2 | 21.5 | 14.5 | 7 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Sheets | New |  | 1 | 21.5 | 14.5 | 7 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 21.5 | 14.5 | 7 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate & Submittal | New |  | 1 | 21.5 | 14.5 | 7 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Spots & Dots | New |  | 1 | 11.5 | 0 | 11.5 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Key Map & Cutting Sheets | New |  | 0.5 | 11.5 | 0 | 11.5 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Spots & Dots | New |  | 0.5 | 11.5 | 0 | 11.5 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Key Map & Cutting Sheets | New |  | 0.5 | 11.5 | 0 | 11.5 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Spots & Dots | New |  | 2 | 11.5 | 0 | 11.5 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Key Map & Sheets | New |  | 2 | 11.5 | 0 | 11.5 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Design Framework | New |  | 2 | 11.5 | 0 | 11.5 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Develop Scope & PDFS Report | New |  | 1 | 11.5 | 0 | 11.5 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  | 1 | 11.5 | 0 | 11.5 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Service Pedestals | New |  | 1 | 11.5 | 0 | 11.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/labels/construction notes | New |  | 8 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules | New |  | 4 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details & General Notes | New |  | 1 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedules | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/labels/construction notes | New |  | 4 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details & General Notes | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Coordinate Intermediate Review w/ Specifications | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Fiber Optic Sensing | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal | New |  | 1 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  |  | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  |  | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  |  | 41 | 4 | 37 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | 74316 Incorporate information from C3673 | New |  | 2 | 41 | 4 | 37 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cutting Sheets | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedule & Structure List | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Request TOTS Pathway Analysis - need A/C | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedules & Structure List | New |  | 2 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | General Notes & Special Details | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Cover/Keymap | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Sheets | New |  | 2 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate & Submittal | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Cover/Keymap | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | General Notes & Special Details | New |  | 1 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedules & Structure List | New |  | 2 | 37 | 2 | 35 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Sheets | New |  | 1 | 37 | 2 | 35 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 1 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 2 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS IMD Design/Labels/Construction Notes | New |  | 1 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Coversheet/Key Map | New |  | 1 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Schedules - ITS Design | New |  | 0.5 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 2 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on IMD SR | New |  | 0.5 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on IMD IR | New |  | 0.5 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS IMD IR | New |  | 1 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Comment on IMD SR | New |  | 2 | 19 | 0 | 19 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG IMD IR | New |  | 2 | 19 | 0 | 19 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Internal Review of Intermediate Submittal | New |  | 4 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review comments | New |  | 4 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS Intermediate Review Comments | New |  | 2 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Comment on Intermediate Review | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Intermediate Review comments | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review comments | New |  | 4 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Coordinate PS&E Review w/ Specifications | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  | 0.5 | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts - needs custom criteria when importing | New |  |  | 21.5 | 0 | 21.5 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS IMD IR comments | New |  | 4 | 12 | 0 | 12 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS IMD SR comments | New |  | 1 | 12 | 0 | 12 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address LTG IMD SR comments | New |  | 4 | 12 | 0 | 12 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address LTG IMD IR comments | New |  | 1 | 12 | 0 | 12 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 12 | 0 | 12 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 12 | 0 | 12 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New |  | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 4 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New |  | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 4 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  |  | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS QAQC IR | New |  | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG QAQC IR | New |  | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 0.5 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New |  | 2 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E Review comments | New |  | 2 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New |  | 1 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Additional Doc items needed for SLI Standalone project | New |  | 8 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Internal Review of QAQC Submittal | New |  | 2 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address QAQC Internal Review comments | New |  | 4 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Signal PS&E Review comments | New |  | 2 | 13 | 0 | 13 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal QAQC Review comments | New |  | 2 | 13 | 0 | 13 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Signal Internal QAQC Review comments | New |  | 2 | 13 | 0 | 13 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New |  | 2 | 13 | 0 | 13 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New |  | 1 | 13 | 0 | 13 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Internal Review on QAQC Submittal | New |  | 2 | 13 | 0 | 13 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 13 | 0 | 13 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 13 | 0 | 13 |  | TRUE
8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Statewide ITS Spreadsheet | New |  |  | 13 | 0 | 13 |  | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New |  | 1 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS QAQC IR comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address LTG QAQC IR comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E Review comments | New |  | 2 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Statewide ITS Spreadsheet | New |  | 0.5 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Post Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-10-27 12:30 | TRUE
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  |  |  | 0 |  | 2025-02-24 13:30 | TRUE
7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | Actively Working | Post Doc Design | Laura Vargo <lvargo@dot.nv.gov> | Signals Lighting and ITS | Integrate ITS Topo on SR-28 | New |  | 4 | 15 | 7 | 8 |  | FALSE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plan Sheets | New |  | 6 | 18 | 0 | 18 | 2023-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New |  | 2 | 18 | 0 | 18 | 2023-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plans | New |  | 4 | 18 | 0 | 18 | 2023-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Special Provisions, Structure List, & Estimate | New |  | 2 | 18 | 0 | 18 | 2023-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Circuit Analysis | New |  | 4 | 18 | 0 | 18 | 2023-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plan Sheets | New |  | 4 | 12 | 0 | 12 | 2023-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New |  | 2 | 12 | 0 | 12 | 2023-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plan sheets | New |  | 4 | 12 | 0 | 12 | 2023-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Special Provisions, Structure List, & Estimate | New |  | 2 | 12 | 0 | 12 | 2023-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Coordination items | New |  | 4 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plan sheets | New |  | 4 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plans & Schedules | New |  | 4 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Circuit Analysis | New |  | 2 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New |  | 2 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal | New |  | 1 | 44 | 41 | 3 |  | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 44 | 41 | 3 |  | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 1 | 44 | 41 | 3 |  | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  | 0.5 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New |  | 0.5 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 4 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 6 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | Post-DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-10-02 13:30 | TRUE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team Coordination Meeting | New |  | 0.5 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 1 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Basic Linework | New |  | 4 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Basic Linework | New |  | 4 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Basic Linework | New |  | 4 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals - Cut Sheets | New |  | 1 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting - Cut Sheets | New |  | 2 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS - Cut Sheets | New |  | 2 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New |  | 2 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 2 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | New |  | 2 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Structure List | New |  | 1 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Structure List | New |  | 1 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Structure List | New |  | 1 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Framework | New |  | 2 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 2 | 43.5 | 6 | 37.5 |  | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | TOTs Coordination | New |  | 0.5 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General Notes | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedule & Structure List | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Cutting Sheets | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Special Details | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  | 8 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 0.25 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 6 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels (check PMP) | New |  | 6 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Voltage Drop | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedule & Structure List | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cutting Sheets | New |  | 4 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & Labels | New |  | 6 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 2 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit (review A/C) | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 12 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 0.5 | 85.25 | 0 | 85.25 | 2022-11-14 13:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 12 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 35.5 | 0 | 35.5 | 2023-03-20 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 2 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 1 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38953 | EA 74375 - US 395 Carson Valley Phase 1 | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 14 | 0 | 14 | 2023-05-06 12:30 | FALSE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New | Jordan James <jjames@dot.nv.gov> | 1 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update ITS Structure List | New |  | 2 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - ITS | New |  | 4 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Lighting | New |  | 4 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Signals | New |  | 4 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide comments in NDOT shared review session | New |  | 2 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address comments from NDOT shared review | New |  | 2 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update ITS construction notes | New |  | 2 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Signals Structure List | New |  | 2 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Signals construction notes | New |  | 1 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Finish Signals linework | New |  | 4 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Lighting construction notes | New |  | 2 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Lighting Structure List | New |  | 2 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review | New |  | 12 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTP Comments Review - QAQC | New |  | 1 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Verify Network Connection Evaluation | New |  | 0 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Verify Network Analysis Info | New |  | 0 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Redesign southern interchange at I-80/McCarran | New |  | 1 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Finish Lighting linework | New |  | 6 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Finish ITS linework | New |  | 6 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Print PDF and Submit | New |  | 1 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 2 | 121 | 25 | 96 | 2022-04-25 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS comments from NDOT shared review | New |  | 1 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - ITS | New |  | 2 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Signals | New |  | 2 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Signals comments from NDOT shared review | New |  | 1 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address internal review - Lighting | New |  | 2 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting comments from NDOT shared review | New |  | 1 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide comments in NDOT shared review session | New |  | 2 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Print PDF and Submit | New |  | 1 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 2 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address comments from NDOT shared review | New |  | 2 | 17 | 0 | 17 | 2022-07-18 12:30 | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team Coordination Meeting | New |  | 0.5 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 12 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lead Designer Accept/Reject Comments - IR Intermediate | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal General Notes | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signals Cutting Sheets | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Linework & Labels | New |  | 6 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Schedule & Structure List | New |  | 6 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Special Details | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 0.25 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  | 8 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Construction Notes | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework & Labels (check PMP) | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Cutting Sheets | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cutting Sheets | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 2 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | TOTs Coordination | New |  | 0.5 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Voltage Drop | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Construction Notes | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & Labels | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedule & Structure List | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 4 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit (review A/C) | New |  | 1 | 85.25 | 0 | 85.25 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 12 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 2 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 1 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | QA/QC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 34.5 | 0 | 34.5 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 2 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 14 | 0 | 14 |  | TRUE
38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 14 | 0 | 14 |  | TRUE
7202 | EA 74225 / 61174 - Winnemucca RRFBs | Actively Working | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | TRUE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | 74108 - Confirm Waterloo SP Panel | New |  | 2 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG IMD Schedules | New |  | 2 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG IMD Design/Labels/Construction Notes | New |  | 4 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Schedules - ITS Design | New |  | 0.5 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS IMD Design/Labels/Construction Notes | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 2 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 2 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Coversheet/Key Map | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS IMD IR | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG IMD IR | New |  | 2 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Comment on IMD SR | New |  | 2 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG IMD IR | New |  | 2 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG General Notes | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | IMD Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on IMD IR | New |  | 0.5 | 29.5 | 0 | 29.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG QAQC IR | New |  | 2 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG QAQC IR | New |  | 2 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS QAQC IR | New |  | 2 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 4 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New |  | 2 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 4 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG Address SR Comments | New |  | 2 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG Address IR Comments | New |  | 4 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New |  | 2 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 0.5 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  |  | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New | Laura Vargo <lvargo@dot.nv.gov> | 2 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | Gurpreet Singh Rai <grai@dot.nv.gov> | 1 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | Brian Dodds <btdodds@dot.nv.gov> | 1 | 32 | 0 | 32 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | Laura Vargo <lvargo@dot.nv.gov> | 1 | 32 | 0 | 32 |  | FALSE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Adjust quantities based on redrawing of county line | New |  | 1 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Labels & linework | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Detail Sheets | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Comments from Intermediate reviews | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Internal Review - QA/QC set | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address comments from PS&E & Internal Reviews | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Placeholder PBI | New |  | 4 | 39 | 0 | 39 |  | TRUE
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Archive - Internal design (void) | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | DOC StructList & Estimate | New |  | 2 | 39 | 0 | 39 |  | TRUE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Address Intermediate Shared Review Comments | New |  | 0 | 12 | 12 | 0 |  | TRUE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | QAQC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Address Changes from Specs | New |  | 0 | 12 | 12 | 0 |  | TRUE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Address Changes from Specs | New |  | 0 | 2 | 2 | 0 |  | TRUE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Comments | New |  | 0 | 2 | 2 | 0 |  | TRUE
45019 | EA 74206 / 74244 - I-80 Elko, L&A and Erosion Control PE | Actively Working | Post-DOC Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Add Key Map to Sheets | New |  | 0 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting 30% SR comments | New |  | 2 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Signals 30% SR comments | New |  | 2 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS 30% SR comments | New |  | 1 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  | 1 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Coversheet/Key Map | New |  | 1 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Linework & Cut Sheets - ITS Design | New |  | 2 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | General Notes - ITS Design | New |  | 1 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Lighting Coversheet/Key Map | New |  | 1 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Linework - Lighting Design | New |  | 4 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Schedules - Lighting Design | New |  | 4 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Labels - Lighting Design | New |  | 4 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Cut sheets - Lighting Design | New |  | 6 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Construction Notes - Lighting Design | New |  | 4 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes - ITS Design | New |  | 2 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | General Notes - Signal Design | New |  | 1 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Schedules - Signal Design | New |  | 6 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Construction Notes - Signal Design | New |  | 4 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | General Notes & Trench Detail - Lighting Design | New |  | 1 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Schedules - ITS Design | New |  | 2 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Intermediate Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Comment on 30% Shared Review | New |  | 2 | 60 | 9 | 51 |  | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Shared Review | New |  | 2 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E SR comments | New |  | 1 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Signals PS&E SR comments | New |  | 1 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E SR comments | New |  | 0 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New |  | 2 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Post-DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2024-10-21 12:30 | TRUE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 40 | 38 | 2 |  | FALSE
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Service Requests | New |  |  | 40 | 38 | 2 |  | FALSE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting and Signal Address Shared Review Comments | New |  | 2 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 0.5 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 2 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | Post-DOC Work | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Brat Report Review | New |  | 1 | 1 | 0 | 1 |  | TRUE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Cover Sheet | New |  | 1 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Linework Labels and Construction Notes | New |  | 4 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding calculations | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Cut sheets | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Create One-line Diagram | New |  | 1 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -1 | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets - 2 | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 2 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Intermediate IR | New |  | 6 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Accept/reject comments | New |  | 1 | 32 | 0 | 32 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Intermediate IR Comments | New |  | 4 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Include design changes, if any | New |  | 2 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 2 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC IR | New |  | 4 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Accept/reject comments | New |  | 1 | 14 | 0 | 14 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address QAQC IR comments | New |  | 4 | 7 | 0 | 7 | 2023-06-16 12:30 | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 7 | 0 | 7 | 2023-06-16 12:30 | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | DOC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 2 | 7 | 0 | 7 | 2023-06-16 12:30 | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | FAA Tower Coordination | New |  | 1 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Consolidate the Specs based on emails & 2 projects | New |  |  | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | FH Conceptual Design | New |  | 2 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Coordination emails | New |  | 1 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SP request email | New |  | 1 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Roadway Coordination | New |  | 2 | 11 | 2 | 9 |  | FALSE
46165 | Fiber Hut - Trinity Rest Area | Actively Working | 30% Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Framework | New |  | 2 | 11 | 2 | 9 |  | FALSE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Linework & Schedules Updates: REMOVED | New |  | 0 | 20 | 20 | 0 |  | TRUE
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Post-DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2024-10-28 12:30 | TRUE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide IMD SR Comments | New |  | 2 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments IMD IR ITS | New |  | 0 | 34.5 | 32.5 | 2 |  | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 4 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New |  | 2 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 4 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New |  | 2 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Coordination Efforts | New |  | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E SR Comments | New |  | 2 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E SR (need A/C review) | New |  | 0.5 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC IR | New |  | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC IR | New |  | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New |  | 1 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New |  | 1 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | Post-DOC | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Coordination Efforts - needs acceptance criteria | New |  | 0 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | Laura Vargo <lvargo@dot.nv.gov> | 0.5 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | Laura Vargo <lvargo@dot.nv.gov> | 1 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | Laura Vargo <lvargo@dot.nv.gov> | 1 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | Laura Vargo <lvargo@dot.nv.gov> | 2 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address PS&E SR Comments | New | Jordan James <jjames@dot.nv.gov> | 1 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New |  | 2 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New |  | 2 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SIG Address IR Comments | New |  | 2 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address PS&E SR Comments | New | Gurpreet Singh Rai <grai@dot.nv.gov> | 2 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address PS&E SR Comments | New | Shofiq Ahmed <shofiq.ahmed@dot.nv.gov> | 1 | 14.5 | 0 | 14.5 |  | FALSE
48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | Actively Working | Post-DOC | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 0.5 | 0.5 | 0 | 0.5 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | IMD Coordination Efforts | New |  | 2 | 38 | 2 | 36 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 15 | 38 | 2 | 36 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Ph. 2 Signal IMD Design | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 38 | 2 | 36 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Schedules | New |  | 2 | 38 | 2 | 36 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedules | New |  | 2 | 38 | 2 | 36 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules | New |  | 2 | 38 | 2 | 36 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 38 | 2 | 36 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Intermediate | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 38 | 2 | 36 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 4 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Signal Internal Review Comments | New |  | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR ITS Comments | New |  | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review comments | New |  | 1 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR Signal Comments | New |  | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review Comments | New |  | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Shared Review Comments | New |  | 1 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 2 | 2 | 0 | 2 |  | FALSE
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | Post-DOC | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 2 | 0 | 2 |  | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 42.5 | 41.5 | 1 |  | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 2 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 6 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR ITS Comments | New |  | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR Lighting Comments | New |  | 1 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit1 | New |  | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 0.5 | 50 | 44 | 6 | 2024-07-10 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 50 | 44 | 6 | 2024-07-10 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 50 | 44 | 6 | 2024-07-10 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Shared Review Comments | New |  | 2 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QAQC Internal Review | New |  | 0.5 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 4 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 0.5 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review and PS&E Shared Review - Comment Revisions | New |  | 4 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE
53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | Actively Working | Intermediate Design | Austin Hoekstra <ahoekstra@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review Comments | New |  | 0 | 50.5 | 50.5 | 0 |  | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2024 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | 2020-ITS25A (HAR Solar Site): the solar pole location needs to be moved to match that of ITS-22 (behind cabinet, away from road). | New |  |  | 18 | 18 | 0 |  | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 0 | 35.5 | 35.5 | 0 |  | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New |  | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New |  | 4 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Pull Box Theft Mitigation | New |  |  | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 10 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS design | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Update & send SP request | New |  | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 10 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  |  | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cleanup | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS Details | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New |  | 4 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 13 | 9 | 4 | 2025-03-03 13:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 13 | 9 | 4 | 2025-03-03 13:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit (Review A/C) | New |  | 2 | 13 | 9 | 4 | 2025-03-03 13:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Comments | New |  | 4 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-06-30 12:30 | TRUE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 35 | 33 | 2 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Intermediate Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 35 | 33 | 2 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  |  | 42.5 | 38 | 4.5 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0.5 | 42.5 | 38 | 4.5 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 42.5 | 38 | 4.5 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New |  | 1 | 42.5 | 38 | 4.5 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | QAQC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 42.5 | 38 | 4.5 |  | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts | New |  | 0.5 | 8.5 | 2 | 6.5 | 2024-09-27 12:30 | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New |  | 1 | 8.5 | 2 | 6.5 | 2024-09-27 12:30 | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New |  | 1 | 8.5 | 2 | 6.5 | 2024-09-27 12:30 | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 8.5 | 2 | 6.5 | 2024-09-27 12:30 | FALSE
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Post DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New |  | 1 | 1 | 0 | 1 | 2024-09-27 12:30 | FALSE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 0 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Intermediate Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | Kaur, Navneet <nkaur@dot.nv.gov> | 0 | 18.5 | 18.5 | 0 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | QAQC Submittal | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Accept/reject Internal PS&E Review Comments | New |  | 0.5 | 8.5 | 8 | 0.5 |  | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | DOC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 4.5 | 0 | 4.5 | 2024-01-08 12:30 | TRUE
53396 | EA 74480 / 61088 - US-95 CL, South of I-11 Interchange | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2024-01-08 12:30 | TRUE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team Intermediate Coordination Meeting | New |  |  | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New |  |  | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 1 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2025-08-12 13:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 0.5 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0.5 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 0.5 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Service Pedestals | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Review As-Built Plans | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Quantify Scope Items and Add Pricing | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Design Framework | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS\2024 Sprint 2 | Lighting Design - Linework | New | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | District 1/RTC-FAST Signal Coordination | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Design - Linework | New |  | 2 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Update Structure List and Estimate | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Generate 40:1 and 100:1 alignments | New |  | 1 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Preliminary 30% Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Design - Linework | New | Brittany Brickman <bbrickman@dot.nv.gov> | 2 | 32 | 18 | 14 |  | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New |  | 2 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Schedule & Structure List | New |  | 6 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Special Details | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 4 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  |  | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New |  |  | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New |  |  | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  |  | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  |  | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  |  | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  |  | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Review Specs | New |  | 4 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Respond to QC Comments on PS&E Shared Review (need A/C review) | New |  | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 2 | 8 | 0 | 8 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 8 | 0 | 8 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 2 | 8 | 0 | 8 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 8 | 0 | 8 | 2027-12-01 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 4 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Respond to QC Comments on PS&E Shared Review (need A/C review) | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Review Specs | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Update Schedules & Structure List | New |  | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  |  |  | 0 | 0 |  | TRUE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  |  | 0 | 0 |  | TRUE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  |  |  | 0 | 0 |  | TRUE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  |  |  | 0 | 0 |  | TRUE
66143 | EA 74363 / 61001 - US95, Searchlight- Pavement rehab | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  |  |  | 0 | 0 |  | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  |  | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  |  | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  |  | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 4 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New |  | 6 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm PS&E Internal Review Comments | New |  | 0.5 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  |  | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  |  | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 4 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 2 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New |  | 4 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New |  | 2 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New |  | 0.5 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New |  | 2 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments PS&E Internal Review | New |  | 6 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject IR comments | New |  | 1 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 0.5 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New |  | 1 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  |  | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LGT IR Comments | New |  | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject PS&E Shared Review comments | New |  | 1 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  | 0.5 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New |  | 1 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New |  | 2 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New |  | 2 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE
43326 | Standard Plans Updates | Actively Working | 9106 - 2026 Standard Plans Update | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Bridge Rail Expansion Joint Detail | New |  | 2 | 4 | 2 | 2 |  | TRUE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Trunkline Design | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cover/Key Map | New |  | 0.5 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  |  | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New |  | 2 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New |  | 2 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New |  | 0.5 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 4 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 2 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New |  | 0.5 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New |  | 0.5 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Sheets | New |  | 2 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review IMD Specs | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | IMD Shared Review - Comments | New |  | 2 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lead respond to IMD internal review comments | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review ITS Sheets | New |  | 4 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New |  | 1 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Collapsible RWIS Tower Detail | New |  | 2 | 37.5 | 0 | 37.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 2 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New |  | 1 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cleanup | New |  | 2 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New |  | 0.5 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New |  | 1 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New |  | 1 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS Details | New |  | 2 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New |  | 2 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New |  |  | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New |  | 2 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New |  | 4 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New |  | 4 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 2 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 1 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review QAQC Specs | New |  | 1 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Sheets | New |  | 2 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QAQC Shared Review - Comments | New |  | 2 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lead respond to QAQC internal review comments | New |  | 1 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review ITS Sheets | New |  | 4 | 35.5 | 0 | 35.5 |  | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New |  | 4 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 2 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 1 | 23.5 | 0 | 23.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Post-DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New |  | 0.5 | 0.5 | 0 | 0.5 | 2026-12-28 13:30 | FALSE
60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | Actively Working | Post-DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New |  |  | 0.5 | 0 | 0.5 | 2026-12-28 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 14 | 0 | 14 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting General Notes | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lead Designer Response to IMD IR comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review Comments & Responses | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Specs Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Design - Coversheet/Key Map | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Design - General Notes | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 15 | 0 | 15 | 2025-03-02 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0.5 | 5.5 | 0 | 5.5 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 5.5 | 0 | 5.5 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 5.5 | 0 | 5.5 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 5.5 | 0 | 5.5 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 5.5 | 0 | 5.5 | 2026-02-16 13:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review As-Built Plans | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | Preliminary 30% Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ORD Development | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 10 | 2 |  | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 0 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review Comments & Responses | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> |  | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Internal Review | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
62239 | EA 74496 / 61101 - (First ORD Project) Winnemucca US95 North of Reinhart Street to South of Paradise Road (DOC 11/27 - Most likely) - Curtis H. New Project | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 1 | 12 | 0 | 12 | 2025-10-20 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 0.5 | 19 | 13 | 6 | 2024-05-08 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile & Submit | New |  | 0.5 | 19 | 13 | 6 | 2024-05-08 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New |  | 0.5 | 19 | 13 | 6 | 2024-05-08 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New |  | 2 | 19 | 13 | 6 | 2024-05-08 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Signal Address Review Shared Comments | New |  | 0.5 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New |  | 0.5 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New |  | 2 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New |  | 0.5 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New |  | 0.5 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 0.5 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New |  | 2 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New |  | 0.5 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New |  | 0.5 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New |  | 1 | 9.5 | 0 | 9.5 | 2024-10-14 12:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address Signal IR comments | New |  | 1 | 7.5 | 0 | 7.5 | 2024-12-30 13:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New |  | 0.5 | 7.5 | 0 | 7.5 | 2024-12-30 13:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New |  | 1 | 7.5 | 0 | 7.5 | 2024-12-30 13:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New |  | 1 | 7.5 | 0 | 7.5 | 2024-12-30 13:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New |  | 0.5 | 7.5 | 0 | 7.5 | 2024-12-30 13:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New |  | 0.5 | 7.5 | 0 | 7.5 | 2024-12-30 13:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New |  | 2 | 7.5 | 0 | 7.5 | 2024-12-30 13:30 | FALSE
68958 | EA 74561 / xxxxx - D2 Kietzke Ln Ped Crossing | Actively Working | DOC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New |  | 1 | 7.5 | 0 | 7.5 | 2024-12-30 13:30 | FALSE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Framework | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P7 - #06 – on US95 at MM 95.26 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P1 - #17 – Yerington, Alt US-95 MM 10.96 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P2 - #13 – Fallon, US-95 MM 21.3 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P3 - #12 – Shurz, US-95 MM 0.05 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P4 - #03 – Indian Springs, US-95 MM 120 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P5 - #04 on US95 at MM 30.2 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 4 | 58 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Calculate Clearing & Grubbing/Seeding | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Framework | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coordinate with other Disciplines | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Schedules | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Sheet Cuts | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Design Linework | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | General Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Attend Meeting & Complete Review | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Labels & Construction Notes | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Create FHxx Sheets -2 | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Special Details | New |  | 4 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Contingency | New |  | 20 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Coversheet/Key Map | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review of Special Provisions | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Respond to comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Attend Meeting & Complete Review | New |  |  | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Intermediate Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Provide Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Internal Review - Address Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 62 | 3 | 59 |  | TRUE
71927 | Communication Building Design | Actively Working | P6 - #05 on US95 at MM 59.12 | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review - Address Review Comments | New |  | 1 | 62 | 3 | 59 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New |  | 1 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Design Framework | New |  | 2 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Cover/Key Map | New |  | 1 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS General Notes | New |  | 1 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New |  | 4 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Block Diagram | New |  | 2 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New |  | 1 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New |  | 2 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New |  | 1 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New |  | 2 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Internal Review | New |  | 2 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Intermediate Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Internal Review Comments | New |  | 2 | 26 | 5 | 21 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | PS&E Coordination Efforts | New |  | 1 | 6 | 0 | 6 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review | New |  | 2 | 6 | 0 | 6 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Update Schedules & Structure List & Estimate | New |  | 1 | 6 | 0 | 6 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | PS&E Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review Specifications | New |  | 2 | 6 | 0 | 6 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Doc Submittal | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address Changes From Submittal | New |  | 2 | 3 | 0 | 3 |  | TRUE
72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | Approved | Doc Submittal | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit | New |  | 1 | 3 | 0 | 3 |  | TRUE

## Anchor Projects
Project_ID | Project_title | Project_state | Epic_Title | Project_Assigned_To | Iteration Path | PBI_Title | PBI_State | PBI_Assigned_To | PBI_Efforts | Epic_TotalEfforts | Epic_Completed_Efforts | Epic_Pending_Efforts | Due_Date | Anchor Project | sprints left | cumulative efforts
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Lighting Internal Review | New | 0 | 4 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 4
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team Intermediate Coordination Meeting | New | 0 | 0.5 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 4.5
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Signal Internal Review | New | 0 | 4 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 8.5
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | 0 | 2 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 10.5
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 12.5
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0.5 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 13
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 14
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New | 0 | 0.5 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 14.5
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New | 0 | 0.5 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 15
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts - needs custom criteria when importing | New | 0 | 0 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 15
38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | 12 EP to be created into "Address Comments" PBI's | New | 0 | 13 | 28 | 0 | 28 | 2024-08-07 12:30 | TRUE | 1 | 28
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New | 0 | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 30
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New | 0 | 4 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 34
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | 0 | 1 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 35
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New | 0 | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 37
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New | 0 | 4 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 41
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New | 0 | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 43
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 44
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 45
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New | 0 | 0 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 45
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | 0 | 0 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 45
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | ITS QAQC IR | New | 0 | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 47
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | LTG QAQC IR | New | 0 | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 49
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0.5 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 49.5
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 51.5
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | QAQC Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | 0 | 0.5 | 24 | 0 | 24 | 2025-03-03 13:30 | TRUE | 16 | 52
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New | 0 | 2 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE | 15 | 54
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E Review comments | New | 0 | 2 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE | 15 | 56
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New | 0 | 1 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE | 15 | 57
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE | 15 | 58
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 1 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE | 15 | 59
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Additional Doc items needed for SLI Standalone project | New | 0 | 8 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE | 15 | 67
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Internal Review of QAQC Submittal | New | 0 | 2 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE | 15 | 69
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address QAQC Internal Review comments | New | 0 | 4 | 21 | 0 | 21 | 2025-02-24 13:30 | TRUE | 15 | 73
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E Review comments | New | 0 | 2 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE | 24 | 75
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Review | New | 0 | 1 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE | 24 | 76
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS QAQC IR comments | New | 0 | 2 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE | 24 | 78
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address LTG QAQC IR comments | New | 0 | 2 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE | 24 | 80
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E Review comments | New | 0 | 2 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE | 24 | 82
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE | 24 | 83
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 1 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE | 24 | 84
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Update Statewide ITS Spreadsheet | New | 0 | 0.5 | 11.5 | 0 | 11.5 | 2025-10-27 12:30 | TRUE | 24 | 84.5
7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | Actively Working | Post Doc Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New | 0 | 0.5 | 0.5 | 0 | 0.5 | 2025-10-27 12:30 | TRUE | 24 | 85
19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New | 0 | 0 | 0 | 0 | 0 | 2025-02-24 13:30 | TRUE | 15 | 85
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Coordination items | New | 0 | 4 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE | 24 | 89
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review ITS Plan sheets | New | 0 | 4 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE | 24 | 93
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review Lighting Plans & Schedules | New | 0 | 4 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE | 24 | 97
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Circuit Analysis | New | 0 | 2 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE | 24 | 99
7203 | EA 73928 - Tonopah CMAR Road Reconstruction | Actively Working | Intermediate Design | Frederick Tydeman <FTydeman@dot.nv.gov> | Signals Lighting and ITS | Review RRFB Design | New | 0 | 2 | 16 | 0 | 16 | 2030-01-01 13:30 | TRUE | 24 | 101
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New | 0 | 0.5 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE | 8 | 101.5
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QAQC Review Utility and UPRR Conflicts | New | 0 | 0.5 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE | 8 | 102
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | 0 | 4 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE | 8 | 106
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE | 8 | 107
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | 0 | 6 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE | 8 | 113
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | 0 | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE | 8 | 114
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE | 8 | 115
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE | 8 | 116
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | QA/QC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 30 | 10 | 20 | 2024-11-12 13:30 | TRUE | 8 | 117
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | 0 | 2 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE | 24 | 119
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE | 24 | 120
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | 0 | 2 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE | 24 | 122
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | 0 | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE | 24 | 123
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | 0 | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE | 24 | 124
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE | 24 | 124.5
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | 0 | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE | 24 | 125.5
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 1 | 9.5 | 0 | 9.5 | 2025-10-02 13:30 | TRUE | 24 | 126.5
38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | Actively Working | Post-DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New | 0 | 0.5 | 0.5 | 0 | 0.5 | 2025-10-02 13:30 | TRUE | 24 | 127
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Comment on PS&E Shared Review | New | 0 | 2 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE | 6 | 129
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting PS&E SR comments | New | 0 | 1 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE | 6 | 130
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Signals PS&E SR comments | New | 0 | 1 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE | 6 | 131
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS PS&E SR comments | New | 0 | 0 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE | 6 | 131
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Estimate | New | 0 | 1 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE | 6 | 132
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Compile and submit | New | 0 | 2 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE | 6 | 134
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Update Structure List | New | 0 | 1 | 15 | 7 | 8 | 2024-10-21 12:30 | TRUE | 6 | 135
45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | Actively Working | Post-DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 0.5 | 0 | 0.5 | 2024-10-21 12:30 | TRUE | 6 | 135.5
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting and Signal Address Shared Review Comments | New | 0 | 2 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE | 24 | 137.5
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0.5 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE | 24 | 138
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE | 24 | 139
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | 0 | 0.5 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE | 24 | 139.5
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE | 24 | 141.5
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | 0 | 2 | 60.5 | 50.5 | 10 | 2026-03-08 12:30 | TRUE | 24 | 143.5
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 144
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | 0 | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 146
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New | 0 | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 148
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | 0 | 1 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 149
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | 0 | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 151
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | 0 | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 153
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | 0 | 1 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 154
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 154.5
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 155
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 157
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 158
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | 0 | 1 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 159
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 159.5
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 161.5
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 163.5
46386 | EA 74454 (61076) US 93 and SR 173 (Boulder) Preservation | Actively Working | DOC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0.5 | 20.5 | 0 | 20.5 | 2026-12-21 13:30 | TRUE | 24 | 164
45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | Actively Working | Post-DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 0.5 | 0 | 0.5 | 2024-10-28 12:30 | TRUE | 7 | 164.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | 0 | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 166.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | 0 | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 168.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | 0 | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 170.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | 0 | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 171.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 172.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | 0 | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 174.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | 0 | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 175.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 177.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 178
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | 0 | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 179
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 180
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 182
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 1 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 183
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 185
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting cleanup | New | 0 | 2 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 187
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New | 0 | 4 | 26.5 | 0 | 26.5 | 2025-10-25 12:30 | TRUE | 24 | 191
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Pull Box Theft Mitigation | New | 0 | 0 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 191
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New | 0 | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 192
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | 0 | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 193
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | 0 | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 194
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | 0 | 0.5 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 194.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New | 0 | 0.5 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 195
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | 0 | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 196
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | 0 | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 197
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New | 0 | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 198
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New | 0 | 10 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 208
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | 0 | 2 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 210
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS design | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 4 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 214
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Intermediate Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Update & send SP request | New | 0 | 1 | 57 | 33 | 24 | 2025-03-01 13:30 | TRUE | 16 | 215
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE | 24 | 215.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | 0 | 0 | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE | 24 | 215.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | 0 | 2 | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE | 24 | 217.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | 0 | 1 | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE | 24 | 218.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | Post Doc Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | 0 | 2 | 5.5 | 0 | 5.5 | 2025-10-25 12:30 | TRUE | 24 | 220.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | 0 | 4 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 224.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | 0 | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 226.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | 0 | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 228.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 229.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | 0 | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 231.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 232.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | 0 | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 233.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 234.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | 0 | 10 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 244.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 246.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | 0 | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 248.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 249.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 250.5
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | 0 | 0.5 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 251
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New | 0 | 0 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 251
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Cleanup | New | 0 | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 253
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | RWIS Details | New | 0 | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 255
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Cleanup | New | 0 | 4 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 259
56358 | EA 74491 US-50 Carson to Spooner | Actively Working | QAQC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | 0 | 2 | 40.5 | 0 | 40.5 | 2025-08-20 12:30 | TRUE | 24 | 261
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0 | 13 | 9 | 4 | 2025-03-03 13:30 | TRUE | 16 | 261
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 13 | 9 | 4 | 2025-03-03 13:30 | TRUE | 16 | 263
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Compile and Submit (Review A/C) | New | 0 | 2 | 13 | 9 | 4 | 2025-03-03 13:30 | TRUE | 16 | 265
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE | 24 | 266
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Comments | New | 0 | 4 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE | 24 | 270
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | 0 | 2 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE | 24 | 272
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 0.5 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE | 24 | 272.5
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE | 24 | 274.5
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | 0 | 1 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE | 24 | 275.5
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE | 24 | 276
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 15 | 2 | 13 | 2025-06-30 12:30 | TRUE | 24 | 278
53336 | EA 74493 / 61098 - I-80 Oasis | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 0.5 | 0 | 0.5 | 2025-06-30 12:30 | TRUE | 24 | 278.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Linework/Labels/Construction Notes | New | 0 | 2 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 280.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Schedule & Structure List | New | 0 | 6 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 286.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signals Special Details | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 287.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Special Details | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 288.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 289.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Analysis | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 290.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Linework/Labels/Construction Notes | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 291.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Schedule & Structure List | New | 0 | 4 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 295.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 296.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New | 0 | 4 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 300.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Linework/Labels/Construction Notes | New | 0 | 2 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 302.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New | 0 | 0 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 302.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New | 0 | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 303
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | 0 | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 303.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 304.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 305.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | 0 | 2 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 307.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 308.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 309.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 310.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 311.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | 0 | 1 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 312.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Intermediate Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | 0 | 0.5 | 39.5 | 5 | 34.5 | 2024-12-13 13:30 | TRUE | 10 | 313
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | 0 | 4 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 317
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | 0 | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 319
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 321
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | 0 | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 323
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | 0 | 4 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 327
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | 0 | 4 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 331
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New | 0 | 0 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 331
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | SLI QAQC Coordination Meeting (Group Designers Only) | New | 0 | 0 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 331
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | 0 | 0 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 331
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 331
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | 0 | 0 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 331
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 333
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | 0 | 0 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 333
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | 0 | 2 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 335
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 336
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | QAQC Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 24 | 0 | 24 | 2025-07-21 12:30 | TRUE | 24 | 337
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 0 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 337
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 339
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 341
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 342
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 344
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 346
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 348
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 350
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 351
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 351
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 351.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 353.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 354.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 355.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 356
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 358
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 360
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0.5 | 23.5 | 0 | 23.5 | 2025-09-29 12:30 | TRUE | 24 | 360.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | 0 | 0 | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE | 24 | 360.5
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE | 24 | 361
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | 0 | 1 | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE | 24 | 362
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | 0 | 2 | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE | 24 | 364
62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | Actively Working | Post Doc Design | Brittany Brickman <bbrickman@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | 0 | 2 | 5.5 | 0 | 5.5 | 2025-09-29 12:30 | TRUE | 24 | 366
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | 0 | 0 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 366
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Special Details | New | 0 | 0 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 366
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Schedules & Structure List | New | 0 | 0 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 366
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | 0 | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 366.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | 0 | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 367.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New | 0 | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 368.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | 0 | 4 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 372.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New | 0 | 6 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 378.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | 0 | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 379.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Estimate | New | 0 | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 380.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Compile and Submit | New | 0 | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 381.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Structure List | New | 0 | 1 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 382.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Clearing and Grubbing/Seeding | New | 0 | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 383
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Intermediate Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New | 0 | 0.5 | 56.5 | 39 | 17.5 | 2024-09-17 12:30 | TRUE | 4 | 383.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm PS&E Internal Review Comments | New | 0 | 0.5 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 384
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | 0 | 0 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 384
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | 0 | 0 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 384
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | 0 | 4 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 388
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 2 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 390
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | 0 | 4 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 394
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | 0 | 2 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 396
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review | New | 0 | 0.5 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 396.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 397.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 399.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New | 0 | 2 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 401.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 402.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 403.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide Comments PS&E Internal Review | New | 0 | 6 | 26 | 0 | 26 | 2026-07-27 12:30 | TRUE | 24 | 409.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | 0 | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 411.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New | 0 | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 413.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | 0 | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 415.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject IR comments | New | 0 | 1 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 416.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 0.5 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 417
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 419
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 420
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | 0 | 1 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 421
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 421
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 423
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LGT IR Comments | New | 0 | 2 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 425
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject PS&E Shared Review comments | New | 0 | 1 | 16.5 | 0 | 16.5 | 2026-05-10 12:30 | TRUE | 24 | 426
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | 0 | 0.5 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE | 24 | 426.5
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE | 24 | 427
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | 0 | 1 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE | 24 | 428
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | 0 | 2 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE | 24 | 430
62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. New Project | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | 0 | 2 | 6 | 0 | 6 | 2026-05-10 12:30 | TRUE | 24 | 432

## Anchor sorted data
#NAME?
#NAME?

## Non-Anchor Projects
Project_ID | Project_title | Project_state | Epic_Title | Project_Assigned_To | Iteration Path | PBI_Title | PBI_State | PBI_Assigned_To | PBI_Efforts | Epic_TotalEfforts | Epic_Completed_Efforts | Epic_Pending_Efforts | Due_Date | Anchor Project | sprints left | cumulative efforts
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Clean up schedules | New | Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 2
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | PS&E Shared Review (need A/C review) | New | 0 | 1 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 3
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 5
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | 0 | 4 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 9
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 11
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | 0 | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 13
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | 0 | 4 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 17
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 18
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 19
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | 0 | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 21
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | 0 | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 23
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 24
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Accept/Reject Comments on QA/QC Internal Review | New | 0 | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 26
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Internal Review | New | 0 | 6 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 32
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Field Visit | New | 0 | 2 | 36 | 2 | 34 | 2024-09-23 12:30 | FALSE | 4 | 34
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | 0 | 2 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE | 24 | 36
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 2 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE | 24 | 38
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | 0 | 2 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE | 24 | 40
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | 0 | 2 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE | 24 | 42
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | 0 | 1 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE | 24 | 43
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 1 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE | 24 | 44
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | 0 | 1 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE | 24 | 45
46368 | EA 74346 - EA 69981 - US 50, Fallon, 3R - PH2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 4 | 15 | 0 | 15 | 2025-10-20 12:30 | FALSE | 24 | 49
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 27.5 | 22.5 | 5 | 2024-11-27 13:30 | FALSE | 9 | 51
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 27.5 | 22.5 | 5 | 2024-11-27 13:30 | FALSE | 9 | 52
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | QAQC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | K2-1 updates | New | 0 | 2 | 27.5 | 22.5 | 5 | 2024-11-27 13:30 | FALSE | 9 | 54
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Internal Review | New | 0 | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE | 13 | 56
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Internal Review Comments | New | 0 | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE | 13 | 58
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE | 13 | 60
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review Comments | New | 0 | 0 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE | 13 | 60
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review Comments | New | 0 | 0 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE | 13 | 60
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | ITS Devices added to Spreadsheet | New | 0 | 0.5 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE | 13 | 60.5
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | 0 | 1 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE | 13 | 61.5
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | Address Shared Review Comments | New | 0 | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE | 13 | 63.5
7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | Actively Working | DOC Design | Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | 0 | 2 | 11.5 | 0 | 11.5 | 2025-01-27 13:30 | FALSE | 13 | 65.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New | 0 | 4 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE | 24 | 69.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New | 0 | 2 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE | 24 | 71.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New | 0 | 4 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE | 24 | 75.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New | 0 | 2 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE | 24 | 77.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | 0 | 0 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE | 24 | 77.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit | New | 0 | 2 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE | 24 | 79.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE | 24 | 80.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE | 24 | 81.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | 0 | 1 | 17 | 0 | 17 | 2025-07-21 12:30 | FALSE | 24 | 82.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Coordination Efforts | New | 0 | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 82.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 83
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | 0 | 1 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 84
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | 0 | 1 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 85
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 87
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E SR Comments | New | 0 | 2 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 89
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E SR (need A/C review) | New | 0 | 0.5 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 89.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC IR | New | 0 | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 89.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC IR | New | 0 | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 89.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address SR Comments | New | 0 | 1 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 90.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG Address IR Comments | New | 0 | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 90.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address IR Comments | New | 0 | 0 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 90.5
48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | Actively Working | DOC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address SR Comments | New | 0 | 1 | 9 | 0 | 9 | 2025-10-20 12:30 | FALSE | 24 | 91.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | 0 | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 93.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | 0 | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 95.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | 0 | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 97.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | 0 | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 99.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | 0 | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 101.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 103.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 104.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | 0 | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 106.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 107.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | 0 | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 108.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | 0 | 4 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 112.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 113.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 1 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 114.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | QA/QC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 25 | 0 | 25 | 2026-04-13 12:30 | FALSE | 24 | 116.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Signal Internal Review Comments | New | 0 | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE | 24 | 118.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR ITS Comments | New | 0 | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE | 24 | 120.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address ITS Internal Review comments | New | 0 | 1 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE | 24 | 121.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR Signal Comments | New | 0 | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE | 24 | 123.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Internal Review Comments | New | 0 | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE | 24 | 125.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Address Lighting Shared Review Comments | New | 0 | 1 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE | 24 | 126.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Compile & Submit | New | 0 | 2 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE | 24 | 128.5
49534 | EA 74249 - EA 69980 - US-50 in East Lake Tahoe Ph2 | Actively Working | DOC Design | Pete Rosenberg <PRosenberg@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 1 | 13 | 0 | 13 | 2027-01-02 13:30 | FALSE | 24 | 129.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE | 23 | 130.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | 0 | 2 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE | 23 | 132.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | 0 | 2 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE | 23 | 134.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | 0 | 6 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE | 23 | 140.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE | 23 | 141.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 1 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE | 23 | 142.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | QAQC Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 26 | 5 | 21 | 2025-06-16 12:30 | FALSE | 23 | 144.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR ITS Comments | New | 0 | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 146.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 148.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 1 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 149.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | 0 | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 151.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | 0 | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 153.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | 0 | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 155.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Address PS&E SR Lighting Comments | New | 0 | 1 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 156.5
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 0.5 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 157
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 158
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 160
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit1 | New | 0 | 2 | 17.5 | 0 | 17.5 | 2025-09-15 12:30 | FALSE | 24 | 162
48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | Actively Working | Post Doc Design | Kaur, Navneet <nkaur@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 0.5 | 0 | 0.5 | 2025-09-15 12:30 | FALSE | 24 | 162.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 2 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 164.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Address Shared Review Comments | New | 0 | 2 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 166.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 1 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 167.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 168.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QAQC Internal Review | New | 0 | 0.5 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 169
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 4 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 173
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | 0 | 0.5 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 173.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 174.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 175.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | QAQC Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | QAQC Internal Review and PS&E Shared Review - Comment Revisions | New | 0 | 4 | 29.5 | 12.5 | 17 | 2025-09-15 12:30 | FALSE | 24 | 179.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 180.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 182.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 183.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 185.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 187.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 189.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 191.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 192.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 193.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 194
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 196
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 197
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 198
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 198.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 200.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 202.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0.5 | 23.5 | 0 | 23.5 | 2025-11-18 13:30 | FALSE | 24 | 203
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | 0 | 0 | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE | 24 | 203
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE | 24 | 203.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | 0 | 1 | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE | 24 | 204.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | 0 | 2 | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE | 24 | 206.5
51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | Actively Working | Post Doc Design | Alesha Jackson <ajackson@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | 0 | 2 | 5.5 | 0 | 5.5 | 2025-11-18 13:30 | FALSE | 24 | 208.5
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | Doc Coordination Efforts | New | 0 | 0.5 | 8.5 | 2 | 6.5 | 2024-09-27 12:30 | FALSE | 5 | 209
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Estimate | New | 0 | 1 | 8.5 | 2 | 6.5 | 2024-09-27 12:30 | FALSE | 5 | 210
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Structure List | New | 0 | 1 | 8.5 | 2 | 6.5 | 2024-09-27 12:30 | FALSE | 5 | 211
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 8.5 | 2 | 6.5 | 2024-09-27 12:30 | FALSE | 5 | 213
55804 | EA 74494 / 61099 - US-93 Lages Station | Actively Working | Post DOC Design | Alex Traeger <atraeger.ctr@dot.nv.gov> | Signals Lighting and ITS | BRAT Review | New | 0 | 1 | 1 | 0 | 1 | 2024-09-27 12:30 | FALSE | 5 | 214
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address ITS IR comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 216
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address LTG IR Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 218
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 220
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 221
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 223
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Address SIG IR Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 225
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 225
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 0 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 225
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 227
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Splice Diagrams | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 228
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 230
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 230.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 231.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | 0 | 1 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 232.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 233
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 235
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0.5 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 235.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 23.5 | 0 | 23.5 | 2025-10-27 12:30 | FALSE | 24 | 237.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Voltage Drop | New | 0 | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 238.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Coordination Efforts | New | 0 | 0 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 238.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Design Conflict Efforts | New | 0 | 0.5 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 239
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Intermediate Review Utility and UPRR Conflicts | New | 0 | 0.5 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 239.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team Intermediate Coordination Meeting | New | 0 | 0 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 239.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Internal Review | New | 0 | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 240.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | 0 | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 241.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - Intermediate Submittal (Tentative) | New | 0 | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 242.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments Intermediate Internal Review | New | 0 | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 243.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | 0 | 2 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 245.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Intermediate Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signals Special Details | New | 0 | 1 | 78.5 | 66 | 12.5 | 2025-01-13 13:30 | FALSE | 12 | 246.5
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE | 24 | 247
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Project Design Closeout | New | 0 | 0 | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE | 24 | 247
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | 0 | 2 | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE | 24 | 249
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | 0 | 1 | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE | 24 | 250
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | Post Doc Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | 0 | 2 | 5.5 | 0 | 5.5 | 2025-10-27 12:30 | FALSE | 24 | 252
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Internal Comments | New | 0 | 4 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 256
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | 0 | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 258
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Internal Review Comments | New | 0 | 4 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 262
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 264
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | LTG - Headframe Assemblies | New | 0 | 0 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 264
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address Internal Review Comments | New | 0 | 4 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 268
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | 0 | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 270
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | 0 | 0 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 270
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | SLI Team QAQC Coordination Meeting | New | 0 | 0 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 270
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 270
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on QA/QC Internal Review | New | 0 | 0 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 270
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 1 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 271
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide Comments QA/QC Internal Review | New | 0 | 0 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 271
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 273
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | 0 | 2 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 275
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 276
48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | Actively Working | QAQC Design | Shaza Elshazli <selshazli@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 25 | 0 | 25 | 2025-07-28 12:30 | FALSE | 24 | 277
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | 0 | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE | 24 | 277.5
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | 0 | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE | 24 | 278
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE | 24 | 278.5
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 1 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE | 24 | 279.5
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE | 24 | 280
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Plot & Submit to Roadway | New | 0 | 1 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE | 24 | 281
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | 0 | 1 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE | 24 | 282
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 0.5 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE | 24 | 282.5
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 1 | 7.5 | 1 | 6.5 | 2025-08-12 13:30 | FALSE | 24 | 283.5
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 0.5 | 0.5 | 0 | 0.5 | 2025-08-12 13:30 | FALSE | 24 | 284
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | 0 | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 285
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | 0 | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 286
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | 0 | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 287
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 0.5 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 287.5
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | 0 | 0.5 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 288
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 0.5 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 288.5
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm Specs review comments - QAQC Submittal | New | 0 | 0.5 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 289
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 291
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | 0 | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 292
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 293
60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 15 | 5 | 10 | 2025-08-27 12:30 | FALSE | 24 | 294
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Review Specs | New | 0 | 4 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 298
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review ITS Comments | New | 0 | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 300
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Lighting Comments | New | 0 | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 302
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Address PS&E Shared Review Signal Comments | New | 0 | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 304
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Respond to QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 306
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments $ | New | 0 | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 308
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DOC Compile and Submit | New | 0 | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 310
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Devices Added to Spreadsheet | New | 0 | 0.5 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 310.5
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Project Closeout | New | 0 | 1 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 311.5
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Review DOC Special Provisions | New | 0 | 0.5 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 312
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Structure List & Estimate | New | 0 | 2 | 20 | 0 | 20 | 2027-12-01 13:30 | FALSE | 24 | 314
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | BRAT Report Review | New | 0 | 2 | 8 | 0 | 8 | 2027-12-01 13:30 | FALSE | 24 | 316
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Bid item review for Change Order | New | 0 | 2 | 8 | 0 | 8 | 2027-12-01 13:30 | FALSE | 24 | 318
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | DRAFT Change Order | New | 0 | 2 | 8 | 0 | 8 | 2027-12-01 13:30 | FALSE | 24 | 320
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | Post Doc Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Finalize Change Order | New | 0 | 2 | 8 | 0 | 8 | 2027-12-01 13:30 | FALSE | 24 | 322
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | ITS Address Review Shared Comments | New | 0 | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 324
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Lighting Address Shared Review Comments | New | 0 | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 326
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Signal Address Shared Review Comments | New | 0 | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 328
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Coordination Efforts | New | 0 | 4 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 332
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Respond to QC Comments on PS&E Shared Review (need A/C review) | New | 0 | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 334
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide PS&E Shared Review Comments | New | 0 | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 336
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Compile and Submit (Review A/C) | New | 0 | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 338
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Estimate | New | 0 | 1 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 339
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | QA/QC Structure List | New | 0 | 1 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 340
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS\2023 Sprint 1 | Review Specs | New | 0 | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 342
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Confirm QC Comments on Intermediate Shared Review | New | 0 | 1 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 343
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Provide Intermediate Shared Review Comments | New | 0 | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 345
62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | Actively Working | QAQC Design | Fernando Torres <ftorres@dot.nv.gov> | Signals Lighting and ITS | Update Schedules & Structure List | New | 0 | 2 | 46.5 | 21.5 | 25 | 2026-01-11 13:30 | FALSE | 24 | 347

## upcoming sprint dates
Sprint | Start | End
2024 Sprint 17 | 2024-07-31 | 2024-08-13
2024 Sprint 18 | 2024-08-14 | 2024-08-27
2024 Sprint 19 | 2024-08-28 | 2024-09-10
2024 Sprint 20 | 2024-09-11 | 2024-09-24
2024 Sprint 21 | 2024-09-25 | 2024-10-08
2024 Sprint 22 | 2024-10-09 | 2024-10-22
2024 Sprint 23 | 2024-10-23 | 2024-11-05
2024 Sprint 24 | 2024-11-06 | 2024-11-19
2024 Sprint 25 | 2024-11-20 | 2024-12-03
2024 Sprint 26 | 2024-12-04 | 2024-12-17
2024 Sprint 27 | 2024-12-18 | 2024-12-31
2025 Sprint 1 | 2025-01-01 | 2025-01-14
2025 Sprint 2 | 2025-01-15 | 2025-01-28
2025 Sprint 3 | 2025-01-29 | 2025-02-11
2025 Sprint 4 | 2025-02-12 | 2025-02-25
2025 Sprint 5 | 2025-02-26 | 2025-03-11
2025 Sprint 6 | 2025-03-12 | 2025-03-25
2025 Sprint 7 | 2025-03-26 | 2025-04-08
2025 Sprint 8 | 2025-04-09 | 2025-04-22
2025 Sprint 9 | 2025-04-23 | 2025-05-06
2025 Sprint 10 | 2025-05-07 | 2025-05-20
2025 Sprint 11 | 2025-05-21 | 2025-06-03
2025 Sprint 12 | 2025-06-04 | 2025-06-17
2025 Sprint 13 | 2025-06-18 | 2025-07-01

## Resource leaves
Resource | 2024 Sprint 17 | 2024 Sprint 18 | 2024 Sprint 19 | 2024 Sprint 20 | 2024 Sprint 21 | 2024 Sprint 22 | 2024 Sprint 23 | 2024 Sprint 24 | 2024 Sprint 25 | 2024 Sprint 26 | 2024 Sprint 27 | 2025 Sprint 1 | 2025 Sprint 10 | 2025 Sprint 11 | 2025 Sprint 12 | 2025 Sprint 13 | 2025 Sprint 2 | 2025 Sprint 3 | 2025 Sprint 4 | 2025 Sprint 5 | 2025 Sprint 6 | 2025 Sprint 7 | 2025 Sprint 8 | 2025 Sprint 9
Alesha Jackson <ajackson@dot.nv.gov> | 1 | 2 | 0 | 2 | 2 | 0 | 1 | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 1
Alex Traeger <atraeger.ctr@dot.nv.gov> | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 2 | 1 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 2 | 1 | 2 | 2 | 1 | 2 | 0 | 0
Austin Hoekstra <ahoekstra@dot.nv.gov> | 2 | 2 | 2 | 0 | 2 | 1 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1
Brittany Brickman <bbrickman@dot.nv.gov> | 1 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 1 | 1 | 2 | 1 | 0 | 2 | 1 | 1 | 2 | 1 | 2
Eric Macgill <emacgill@dot.nv.gov> | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 0 | 2 | 2 | 2 | 2 | 0 | 1 | 1 | 2 | 2 | 0 | 2
Fernando Torres <ftorres@dot.nv.gov> | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 1
Frederick Tydeman <FTydeman@dot.nv.gov> | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 1 | 0 | 2 | 2 | 0 | 2
Katelyn Sasaki <ksasaki.ctr@dot.nv.gov> | 1 | 2 | 1 | 2 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 2 | 0 | 1 | 0 | 2 | 2 | 0 | 2 | 1 | 1 | 2 | 0 | 0
Kaur, Navneet <nkaur@dot.nv.gov> | 1 | 2 | 2 | 2 | 2 | 0 | 1 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0 | 0 | 2 | 2 | 2 | 1 | 2
Laura Vargo <lvargo@dot.nv.gov> | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 1 | 0 | 1 | 2 | 1 | 0 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2
Pete Rosenberg <PRosenberg@dot.nv.gov> | 2 | 1 | 2 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 0 | 2 | 2 | 1 | 0 | 2 | 0 | 0 | 1 | 2 | 0 | 1 | 2
Shaza Elshazli <selshazli@dot.nv.gov> | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 2 | 1 | 2 | 1
| 12 | 11 | 10 | 13 | 16 | 8 | 12 | 10 | 14 | 12 | 11 | 17 | 11 | 16 | 14 | 9 | 18 | 7 | 15 | 11 | 19 | 19 | 10 | 16

## Holidays
Sprint | Holidays
2024 Sprint 17 | 0
2024 Sprint 18 | 0
2024 Sprint 19 | 1
2024 Sprint 20 | 0
2024 Sprint 21 | 1
2024 Sprint 22 | 1
2024 Sprint 23 | 0
2024 Sprint 24 | 0
2024 Sprint 25 | 1
2024 Sprint 26 | 1
2024 Sprint 27 | 0
2025 Sprint 1 | 0
2025 Sprint 2 | 1
2025 Sprint 3 | 1
2025 Sprint 4 | 1
2025 Sprint 5 | 1
2025 Sprint 6 | 0
2025 Sprint 7 | 0
2025 Sprint 8 | 0
2025 Sprint 9 | 0
2025 Sprint 10 | 1
2025 Sprint 11 | 1
2025 Sprint 12 | 1
2025 Sprint 13 | 0