## Sheet1
epics_System_Id | epics_System_Title | total_effort_from_pbis | projects_Work_Item_ID | projects_Title | projects_EA_Number | projects_Iteration_Path | projects_Work_Item_Type | projects_State | projects_Scoping_30_Percent | projects_SeventyFivePercentComplete | projects_Intermediate_Date | projects_QAQC_Submittal_Date | projects_Document_Submittal_Date | projects_Priority_Traffic_Ops | projects_Fiscal_Year | projects_Funding_Source | projects_Route_Type | projects_Construction_EA_Number | projects_Official_DOC_Date | projects_Anchor_Project | projects_Complexity_Signals | projects_Complexity_Lighting | projects_Complexity_ITS | projects_Complexity_Power_Design | projects_Complexity_RoW_Coordination | projects_Complexity_SLI_Project_Lead | projects_Complexity_Solar_Design | projects_Complexity_Trunkline
90321 | DOC Design | 18 | 7203 | EA 73928 - Tonopah CMAR Road Reconstruction | 73928 | Signals Lighting and ITS | Project | Actively Working |  |  | 2030-01-01T08:00:00Z | 2023-01-01T08:00:00Z | 2023-01-01T08:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90322 | QA/QC Design | 12 | 7203 | EA 73928 - Tonopah CMAR Road Reconstruction | 73928 | Signals Lighting and ITS | Project | Actively Working |  |  | 2030-01-01T08:00:00Z | 2023-01-01T08:00:00Z | 2023-01-01T08:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90323 | Intermediate Design | 16 | 7203 | EA 73928 - Tonopah CMAR Road Reconstruction | 73928 | Signals Lighting and ITS | Project | Actively Working |  |  | 2030-01-01T08:00:00Z | 2023-01-01T08:00:00Z | 2023-01-01T08:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90324 | Archive - Internal design (void) | 39 | 7203 | EA 73928 - Tonopah CMAR Road Reconstruction | 73928 | Signals Lighting and ITS | Project | Actively Working |  |  | 2030-01-01T08:00:00Z | 2023-01-01T08:00:00Z | 2023-01-01T08:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90325 | Post Doc Design | 8 | 7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | 74153 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90326 | QA/QC Design | 29 | 7452 | EA 74151 - I-80 & Mote Road (3R) | 74151 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90327 | DOC Design | 8 | 7452 | EA 74151 - I-80 & Mote Road (3R) | 74151 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90328 | 30% Design | 11.5 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90329 | Intermediate Design | 19 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90330 | QAQC Design | 24 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90331 | Doc Design | 11.5 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90332 | Post Doc Design | 0.5 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90333 | QAQC Design | 5 | 7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | 73840 | Signals Lighting and ITS | Project | Actively Working |  |  | 2026-06-01T07:00:00Z | 2026-11-02T08:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | State | State Route | 60690 | 2027-02-15T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90334 | DOC Design | 11.5 | 7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | 73840 | Signals Lighting and ITS | Project | Actively Working |  |  | 2026-06-01T07:00:00Z | 2026-11-02T08:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | State | State Route | 60690 | 2027-02-15T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90335 | 30% Design | 7 | 8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | 74321 | Signals Lighting and ITS | Project | Actively Working | 2022-11-30T08:00:00Z | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90336 | Intermediate Design | 35 | 8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | 74321 | Signals Lighting and ITS | Project | Actively Working | 2022-11-30T08:00:00Z | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90337 | QAQC Design | 12 | 8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | 74321 | Signals Lighting and ITS | Project | Actively Working | 2022-11-30T08:00:00Z | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90338 | Doc Design | 13 | 8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | 74321 | Signals Lighting and ITS | Project | Actively Working | 2022-11-30T08:00:00Z | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90339 | Intermediate Design | 20.5 | 8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | 74471 | Signals Lighting and ITS | Project | On-Hold |  |  | 2024-02-06T08:00:00Z | 2024-07-30T07:00:00Z | 2024-10-29T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90340 | QAQC Design | 15 | 8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | 74471 | Signals Lighting and ITS | Project | On-Hold |  |  | 2024-02-06T08:00:00Z | 2024-07-30T07:00:00Z | 2024-10-29T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90341 | DOC Design | 10 | 8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | 74471 | Signals Lighting and ITS | Project | On-Hold |  |  | 2024-02-06T08:00:00Z | 2024-07-30T07:00:00Z | 2024-10-29T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90342 | Post DOC Design | 1 | 8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | 74471 | Signals Lighting and ITS | Project | On-Hold |  |  | 2024-02-06T08:00:00Z | 2024-07-30T07:00:00Z | 2024-10-29T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90343 | 30% Design | 6 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90344 | Intermediate Design | 37 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90345 | QAQC Design | 21.5 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90346 | Doc Design | 21 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90347 | Post Doc Design | 0 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90348 | Intermediate Design | 0 | 19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | 74309 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90349 | QAQC Design | 0 | 19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | 74309 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90350 | DOC Design | 0 | 19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | 74309 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90351 | Post-DOC Design | 2 | 23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | 69999 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2022-08-01T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90352 | Intermediate Design | 1 | 26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | 74361 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90353 | QA/QC Design | 26.5 | 26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | 74361 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90354 | DOC Design | 12 | 26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | 74361 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90355 | Post-DOC | 0.5 | 26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | 74361 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90356 | Intermediate Design | 17.5 | 30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | 60988 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90357 | QAQC Design | 16.5 | 30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | 60988 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90358 | DOC Design | 9 | 30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | 60988 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90359 | Intermediate Design | 57 | 33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | 74448 | Signals Lighting and ITS | Project | On-Hold |  |  | 2023-01-30T08:00:00Z | 2023-08-07T07:00:00Z | 2023-10-23T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90360 | QA/QC Design | 33 | 33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | 74448 | Signals Lighting and ITS | Project | On-Hold |  |  | 2023-01-30T08:00:00Z | 2023-08-07T07:00:00Z | 2023-10-23T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90361 | DOC Design | 16 | 33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | 74448 | Signals Lighting and ITS | Project | On-Hold |  |  | 2023-01-30T08:00:00Z | 2023-08-07T07:00:00Z | 2023-10-23T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90362 | Post-DOC | 0.5 | 33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | 74448 | Signals Lighting and ITS | Project | On-Hold |  |  | 2023-01-30T08:00:00Z | 2023-08-07T07:00:00Z | 2023-10-23T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90363 | 30% Design | 0.5 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90364 | Intermediate Design | 83 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90365 | QAQC Design | 28 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90366 | Doc Design | 16 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90367 | Post Doc Design | 0 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90368 | QA/QC Design | 6 | 38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | 74359 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2024-12-11T08:00:00Z | 2025-02-10T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90369 | DOC Design | 5.5 | 38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | 74359 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2024-12-11T08:00:00Z | 2025-02-10T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90370 | Post-DOC Design | 0.5 | 38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | 74359 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2024-12-11T08:00:00Z | 2025-02-10T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90371 | 30% Design | 33.5 | 38953 | EA 74375 - US 395 Carson Valley Phase 1 | 74375 | Signals Lighting and ITS | Project | Actively Working |  |  | 2022-11-14T08:00:00Z | 2023-03-20T07:00:00Z | 2023-06-05T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90372 | Intermediate Design | 85.25 | 38953 | EA 74375 - US 395 Carson Valley Phase 1 | 74375 | Signals Lighting and ITS | Project | Actively Working |  |  | 2022-11-14T08:00:00Z | 2023-03-20T07:00:00Z | 2023-06-05T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90373 | QA/QC Design | 35.5 | 38953 | EA 74375 - US 395 Carson Valley Phase 1 | 74375 | Signals Lighting and ITS | Project | Actively Working |  |  | 2022-11-14T08:00:00Z | 2023-03-20T07:00:00Z | 2023-06-05T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90374 | DOC Design | 14 | 38953 | EA 74375 - US 395 Carson Valley Phase 1 | 74375 | Signals Lighting and ITS | Project | Actively Working |  |  | 2022-11-14T08:00:00Z | 2023-03-20T07:00:00Z | 2023-06-05T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90375 | QA/QC Design | 96 | 38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | 74191 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2022-04-25T07:00:00Z | 2022-07-18T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90376 | DOC Design | 17 | 38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | 74191 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2022-04-25T07:00:00Z | 2022-07-18T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90377 | DOC Design | 7.5 | 38980 | EA 74178 / 69920 - SR-207 (Kingsbury grade) 3R | 74178 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-12-27T08:00:00Z | 3 | 2027 | Federal | State Route |  | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
90378 | Post-DOC | 0.5 | 38980 | EA 74178 / 69920 - SR-207 (Kingsbury grade) 3R | 74178 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-12-27T08:00:00Z | 3 | 2027 | Federal | State Route |  | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
90379 | QA/QC Design | 4 | 38980 | EA 74178 / 69920 - SR-207 (Kingsbury grade) 3R | 74178 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-12-27T08:00:00Z | 3 | 2027 | Federal | State Route |  | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
90380 | Intermediate Design | 85.25 | 38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | 74347 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90381 | QA/QC Design | 34.5 | 38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | 74347 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90382 | DOC Design | 14 | 38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | 74347 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90383 | 9106 - 2024 Standard Plans Update | 0 | 43326 | Standard Plans Updates | 9106 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90384 | 9106 - 2026 Standard Plans Update | 2 | 43326 | Standard Plans Updates | 9106 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90385 | Intermediate Design | 51 | 45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | 74357 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2025-01-06T08:00:00Z | 3 | 2025 | Federal | State Route | 61035 | 2025-01-20T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
90386 | DOC Design | 9 | 45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | 74357 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2025-01-06T08:00:00Z | 3 | 2025 | Federal | State Route | 61035 | 2025-01-20T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
90387 | Post-DOC Design | 0.5 | 45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | 74357 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2025-01-06T08:00:00Z | 3 | 2025 | Federal | State Route | 61035 | 2025-01-20T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
90388 | Intermediate Design | 67 | 45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | 74453 | Signals Lighting and ITS | Project | On-Hold |  |  | 2022-11-21T08:00:00Z | 2023-05-01T07:00:00Z | 2024-10-28T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90389 | QAQC Design | 45 | 45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | 74453 | Signals Lighting and ITS | Project | On-Hold |  |  | 2022-11-21T08:00:00Z | 2023-05-01T07:00:00Z | 2024-10-28T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90390 | Doc Design | 20 | 45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | 74453 | Signals Lighting and ITS | Project | On-Hold |  |  | 2022-11-21T08:00:00Z | 2023-05-01T07:00:00Z | 2024-10-28T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90391 | Post Doc Design | 0.5 | 45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | 74453 | Signals Lighting and ITS | Project | On-Hold |  |  | 2022-11-21T08:00:00Z | 2023-05-01T07:00:00Z | 2024-10-28T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90392 | QAQC Design | 0 | 45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | 74462 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-04T08:00:00Z | 5 | 2025 | Federal | Interstate | 61079 | 2024-11-11T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90393 | Post-DOC Design | 0.5 | 45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | 74462 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-04T08:00:00Z | 5 | 2025 | Federal | Interstate | 61079 | 2024-11-11T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90394 | Intermediate Design | 32 | 46165 | Fiber Hut - Trinity Rest Area | 9104 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2023-06-16T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90395 | QAQC Design | 14 | 46165 | Fiber Hut - Trinity Rest Area | 9104 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2023-06-16T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90396 | DOC Design | 7 | 46165 | Fiber Hut - Trinity Rest Area | 9104 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2023-06-16T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90397 | 30% Design | 9 | 46165 | Fiber Hut - Trinity Rest Area | 9104 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2023-06-16T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90398 | QA/QC Design | 37 | 46368 | EA 74346 / EA 69981 - US 50, Fallon, 3R - PH2 | 74346 | Signals Lighting and ITS | Project | Actively Working |  | 2024-10-22T07:00:00Z |  |  | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 69981 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
90399 | DOC Design | 15 | 46368 | EA 74346 / EA 69981 - US 50, Fallon, 3R - PH2 | 74346 | Signals Lighting and ITS | Project | Actively Working |  | 2024-10-22T07:00:00Z |  |  | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 69981 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
90400 | 75% Design | 6 | 46368 | EA 74346 / EA 69981 - US 50, Fallon, 3R - PH2 | 74346 | Signals Lighting and ITS | Project | Actively Working |  | 2024-10-22T07:00:00Z |  |  | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 69981 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
90401 | QAQC Design | 13.5 | 46386 | EA 74454 / 61076 - US 93 and SR 173 (Boulder) Preservation | 74454 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-08-03T07:00:00Z | 2026-12-21T08:00:00Z | 3 | 2027 | Federal | Highway | 61076 | 2027-01-04T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90402 | DOC Design | 20.5 | 46386 | EA 74454 / 61076 - US 93 and SR 173 (Boulder) Preservation | 74454 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-08-03T07:00:00Z | 2026-12-21T08:00:00Z | 3 | 2027 | Federal | Highway | 61076 | 2027-01-04T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90403 | Post-DOC | 1 | 46386 | EA 74454 / 61076 - US 93 and SR 173 (Boulder) Preservation | 74454 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-08-03T07:00:00Z | 2026-12-21T08:00:00Z | 3 | 2027 | Federal | Highway | 61076 | 2027-01-04T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90404 | Intermediate Design | 1 | 48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | 74463 | Signals Lighting and ITS | Project | Actively Working |  | 2025-01-13T08:00:00Z |  | 2025-06-16T07:00:00Z | 2025-09-15T07:00:00Z | 4 | 2026 | Federal | Interstate | 61080 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90405 | 75% Design | 21 | 48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | 74463 | Signals Lighting and ITS | Project | Actively Working |  | 2025-01-13T08:00:00Z |  | 2025-06-16T07:00:00Z | 2025-09-15T07:00:00Z | 4 | 2026 | Federal | Interstate | 61080 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90406 | Doc Design | 17.5 | 48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | 74463 | Signals Lighting and ITS | Project | Actively Working |  | 2025-01-13T08:00:00Z |  | 2025-06-16T07:00:00Z | 2025-09-15T07:00:00Z | 4 | 2026 | Federal | Interstate | 61080 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90407 | Post Doc Design | 0.5 | 48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | 74463 | Signals Lighting and ITS | Project | Actively Working |  | 2025-01-13T08:00:00Z |  | 2025-06-16T07:00:00Z | 2025-09-15T07:00:00Z | 4 | 2026 | Federal | Interstate | 61080 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90408 | Intermediate Design | 2 | 48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | 74458 | Signals Lighting and ITS | Project | Actively Working |  | 2024-11-18T08:00:00Z |  | 2025-07-21T07:00:00Z | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 61077 | 2025-12-08T08:00:00Z | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90409 | QAQC Design | 17 | 48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | 74458 | Signals Lighting and ITS | Project | Actively Working |  | 2024-11-18T08:00:00Z |  | 2025-07-21T07:00:00Z | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 61077 | 2025-12-08T08:00:00Z | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90410 | DOC Design | 9 | 48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | 74458 | Signals Lighting and ITS | Project | Actively Working |  | 2024-11-18T08:00:00Z |  | 2025-07-21T07:00:00Z | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 61077 | 2025-12-08T08:00:00Z | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90411 | Post-DOC | 0.5 | 48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | 74458 | Signals Lighting and ITS | Project | Actively Working |  | 2024-11-18T08:00:00Z |  | 2025-07-21T07:00:00Z | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 61077 | 2025-12-08T08:00:00Z | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90412 | Doc Design | 23.5 | 48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | 74488 | Signals Lighting and ITS | Project | Actively Working | 2024-09-02T07:00:00Z |  | 2025-01-13T08:00:00Z | 2025-07-28T07:00:00Z | 2025-10-27T07:00:00Z | 4 | 2026 | Federal | State Route | 61094 | 2025-12-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90413 | Intermediate Design | 7 | 48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | 74488 | Signals Lighting and ITS | Project | Actively Working | 2024-09-02T07:00:00Z |  | 2025-01-13T08:00:00Z | 2025-07-28T07:00:00Z | 2025-10-27T07:00:00Z | 4 | 2026 | Federal | State Route | 61094 | 2025-12-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90414 | Post Doc Design | 5.5 | 48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | 74488 | Signals Lighting and ITS | Project | Actively Working | 2024-09-02T07:00:00Z |  | 2025-01-13T08:00:00Z | 2025-07-28T07:00:00Z | 2025-10-27T07:00:00Z | 4 | 2026 | Federal | State Route | 61094 | 2025-12-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90415 | QAQC Design | 13 | 48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | 74488 | Signals Lighting and ITS | Project | Actively Working | 2024-09-02T07:00:00Z |  | 2025-01-13T08:00:00Z | 2025-07-28T07:00:00Z | 2025-10-27T07:00:00Z | 4 | 2026 | Federal | State Route | 61094 | 2025-12-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90416 | IMD Design | 29.5 | 48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | 74108 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-10T08:00:00Z |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | Highway | 69974 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90417 | QAQC Design | 32 | 48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | 74108 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-10T08:00:00Z |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | Highway | 69974 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90418 | DOC Design | 14.5 | 48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | 74108 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-10T08:00:00Z |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | Highway | 69974 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90419 | Post-DOC | 0.5 | 48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | 74108 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-10T08:00:00Z |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | Highway | 69974 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90420 | Intermediate | 22.5 | 49534 | EA 74249 / 69980 - US-50 in East Lake Tahoe Ph2 | 74249 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-09-29T07:00:00Z | 2026-03-28T07:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | Federal | Highway | 69980 | 2027-02-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90421 | QA/QC Design | 32 | 49534 | EA 74249 / 69980 - US-50 in East Lake Tahoe Ph2 | 74249 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-09-29T07:00:00Z | 2026-03-28T07:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | Federal | Highway | 69980 | 2027-02-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90422 | DOC Design | 13 | 49534 | EA 74249 / 69980 - US-50 in East Lake Tahoe Ph2 | 74249 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-09-29T07:00:00Z | 2026-03-28T07:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | Federal | Highway | 69980 | 2027-02-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90423 | Post-DOC | 2 | 49534 | EA 74249 / 69980 - US-50 in East Lake Tahoe Ph2 | 74249 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-09-29T07:00:00Z | 2026-03-28T07:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | Federal | Highway | 69980 | 2027-02-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90424 | QAQC Design | 17 | 51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | 74450 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-09-15T07:00:00Z | 2025-11-18T08:00:00Z | 3 | 2025 | Federal | Interstate | 61073 | 2025-02-02T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90425 | Doc Design | 21.5 | 51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | 74450 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-09-15T07:00:00Z | 2025-11-18T08:00:00Z | 3 | 2025 | Federal | Interstate | 61073 | 2025-02-02T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90426 | Post Doc Design | 5.5 | 51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | 74450 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-09-15T07:00:00Z | 2025-11-18T08:00:00Z | 3 | 2025 | Federal | Interstate | 61073 | 2025-02-02T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90427 | Intermediate Design | 27.5 | 51820 | EA 74477 / 61086 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | 74477 | Signals Lighting and ITS | Project | On-Hold |  |  | 2025-03-02T08:00:00Z | 2025-09-02T07:00:00Z | 2025-12-01T08:00:00Z |  | 2026 | Federal | Highway | 61086 | 2025-12-15T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90428 | QAQC Design | 25 | 51820 | EA 74477 / 61086 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | 74477 | Signals Lighting and ITS | Project | On-Hold |  |  | 2025-03-02T08:00:00Z | 2025-09-02T07:00:00Z | 2025-12-01T08:00:00Z |  | 2026 | Federal | Highway | 61086 | 2025-12-15T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90429 | Doc Design | 23.5 | 51820 | EA 74477 / 61086 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | 74477 | Signals Lighting and ITS | Project | On-Hold |  |  | 2025-03-02T08:00:00Z | 2025-09-02T07:00:00Z | 2025-12-01T08:00:00Z |  | 2026 | Federal | Highway | 61086 | 2025-12-15T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90430 | Post Doc Design | 5.5 | 51820 | EA 74477 / 61086 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | 74477 | Signals Lighting and ITS | Project | On-Hold |  |  | 2025-03-02T08:00:00Z | 2025-09-02T07:00:00Z | 2025-12-01T08:00:00Z |  | 2026 | Federal | Highway | 61086 | 2025-12-15T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90431 | Intermediate Design | 0 | 53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | 74505 | Signals Lighting and ITS | Project | Actively Working | [5 empty] | 3 | 2024 | State | Interstate |  | 2024-01-08T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90432 | Intermediate Design | 0 | 53336 | EA 74493 / 61098 - I-80 Oasis | 74493 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-06-30T07:00:00Z | 3 | 2026 | Federal | Interstate | 61098 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90433 | QAQC Design | 4 | 53336 | EA 74493 / 61098 - I-80 Oasis | 74493 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-06-30T07:00:00Z | 3 | 2026 | Federal | Interstate | 61098 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90434 | Doc Design | 13 | 53336 | EA 74493 / 61098 - I-80 Oasis | 74493 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-06-30T07:00:00Z | 3 | 2026 | Federal | Interstate | 61098 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90435 | Post Doc Design | 0.5 | 53336 | EA 74493 / 61098 - I-80 Oasis | 74493 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-06-30T07:00:00Z | 3 | 2026 | Federal | Interstate | 61098 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90436 | Intermediate Design | 10 | 54531 | EA 74449 / 61072 - US-50, Middlegate | 74449 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-06T08:00:00Z | 2025-11-10T08:00:00Z | 2026-01-12T08:00:00Z | 3 | 2026 | Federal | Highway | 61072 | 2026-01-26T08:00:00Z | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0
90437 | QAQC Design | 13.5 | 54531 | EA 74449 / 61072 - US-50, Middlegate | 74449 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-06T08:00:00Z | 2025-11-10T08:00:00Z | 2026-01-12T08:00:00Z | 3 | 2026 | Federal | Highway | 61072 | 2026-01-26T08:00:00Z | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0
90438 | DOC Design | 8.5 | 54531 | EA 74449 / 61072 - US-50, Middlegate | 74449 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-06T08:00:00Z | 2025-11-10T08:00:00Z | 2026-01-12T08:00:00Z | 3 | 2026 | Federal | Highway | 61072 | 2026-01-26T08:00:00Z | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0
90439 | Post DOC Design | 1 | 54531 | EA 74449 / 61072 - US-50, Middlegate | 74449 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-06T08:00:00Z | 2025-11-10T08:00:00Z | 2026-01-12T08:00:00Z | 3 | 2026 | Federal | Highway | 61072 | 2026-01-26T08:00:00Z | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0
90440 | Intermediate Design | 2 | 55804 | EA 74494 / 61099 - US-93 Lages Station | 74494 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-18T08:00:00Z | 3 | 2025 | Federal | Highway | 61099 | 2024-12-02T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90441 | QAQC Design | 1 | 55804 | EA 74494 / 61099 - US-93 Lages Station | 74494 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-18T08:00:00Z | 3 | 2025 | Federal | Highway | 61099 | 2024-12-02T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90442 | DOC Design | 5 | 55804 | EA 74494 / 61099 - US-93 Lages Station | 74494 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-18T08:00:00Z | 3 | 2025 | Federal | Highway | 61099 | 2024-12-02T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90443 | Post DOC Design | 1 | 55804 | EA 74494 / 61099 - US-93 Lages Station | 74494 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-18T08:00:00Z | 3 | 2025 | Federal | Highway | 61099 | 2024-12-02T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90444 | Doc Design | 26.5 | 56358 | EA 74491 / 61096 - US-50 Carson to Spooner | 74491 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-03T08:00:00Z | 2025-08-20T07:00:00Z | 2025-12-22T08:00:00Z |  |  |  |  | 61096 | 2026-01-05T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90445 | Intermediate Design | 24.5 | 56358 | EA 74491 / 61096 - US-50 Carson to Spooner | 74491 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-03T08:00:00Z | 2025-08-20T07:00:00Z | 2025-12-22T08:00:00Z |  |  |  |  | 61096 | 2026-01-05T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90446 | Post Doc Design | 5.5 | 56358 | EA 74491 / 61096 - US-50 Carson to Spooner | 74491 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-03T08:00:00Z | 2025-08-20T07:00:00Z | 2025-12-22T08:00:00Z |  |  |  |  | 61096 | 2026-01-05T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90447 | QAQC Design | 40.5 | 56358 | EA 74491 / 61096 - US-50 Carson to Spooner | 74491 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-03T08:00:00Z | 2025-08-20T07:00:00Z | 2025-12-22T08:00:00Z |  |  |  |  | 61096 | 2026-01-05T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90448 | Doc Design | 6.5 | 60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | 74486 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-08-27T07:00:00Z | 2025-12-08T08:00:00Z | 3 | 2025 | State | Highway | 61093 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90449 | Post Doc Design | 0.5 | 60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | 74486 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-08-27T07:00:00Z | 2025-12-08T08:00:00Z | 3 | 2025 | State | Highway | 61093 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90450 | QAQC Design | 10 | 60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | 74486 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-08-27T07:00:00Z | 2025-12-08T08:00:00Z | 3 | 2025 | State | Highway | 61093 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90451 | Intermediate Design | 39 | 60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | 74489 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2026-12-28T08:00:00Z | 3 | 2027 | Federal | State Route | 61095 | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90452 | QAQC Design | 35.5 | 60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | 74489 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2026-12-28T08:00:00Z | 3 | 2027 | Federal | State Route | 61095 | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90453 | DOC Design | 23.5 | 60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | 74489 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2026-12-28T08:00:00Z | 3 | 2027 | Federal | State Route | 61095 | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90454 | Post-DOC Design | 0.5 | 60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | 74489 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2026-12-28T08:00:00Z | 3 | 2027 | Federal | State Route | 61095 | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
90455 | Preliminary 30% Design | 14 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90456 | Intermediate Design | 21.5 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90457 | QAQC Design | 24 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90458 | Doc Design | 23.5 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90459 | Post Doc Design | 5.5 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90460 | Intermediate Design | 18.5 | 62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. | 74484 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-04T08:00:00Z | 2026-07-27T07:00:00Z | 2026-10-05T07:00:00Z |  |  |  |  | 61180 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90461 | QAQC Design | 26 | 62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. | 74484 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-04T08:00:00Z | 2026-07-27T07:00:00Z | 2026-10-05T07:00:00Z |  |  |  |  | 61180 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90462 | Doc Design | 16.5 | 62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. | 74484 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-04T08:00:00Z | 2026-07-27T07:00:00Z | 2026-10-05T07:00:00Z |  |  |  |  | 61180 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90463 | Post Doc Design | 6 | 62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. | 74484 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-04T08:00:00Z | 2026-07-27T07:00:00Z | 2026-10-05T07:00:00Z |  |  |  |  | 61180 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90464 | Preliminary Design | 4 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90465 | Intermediate Design | 48.5 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90466 | QAQC Design | 20 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90467 | DOC Design | 11 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90468 | Post-DOC Design | 0.5 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90469 | Doc Design | 20 | 62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | 74495 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-11-01T08:00:00Z | 2027-01-12T08:00:00Z | 4 | 2025 | Federal | Highway | 61100 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90470 | Post Doc Design | 8 | 62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | 74495 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-11-01T08:00:00Z | 2027-01-12T08:00:00Z | 4 | 2025 | Federal | Highway | 61100 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90471 | QAQC Design | 25 | 62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | 74495 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-11-01T08:00:00Z | 2027-01-12T08:00:00Z | 4 | 2025 | Federal | Highway | 61100 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90472 | Doc Design | 9 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
90473 | Intermediate Design | 28 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
90474 | Post Doc Design | 0.5 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
90475 | Preliminary Design | 4.5 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
90476 | QAQC Design | 18 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
90477 | Intermediate Design | 40 | 64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | 74432 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2027-07-19T07:00:00Z | [5 empty] | 2027-08-02T07:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90478 | QAQC Design | 25 | 64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | 74432 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2027-07-19T07:00:00Z | [5 empty] | 2027-08-02T07:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90479 | Doc Design | 23.5 | 64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | 74432 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2027-07-19T07:00:00Z | [5 empty] | 2027-08-02T07:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90480 | Post Doc Design | 5.5 | 64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | 74432 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2027-07-19T07:00:00Z | [5 empty] | 2027-08-02T07:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90481 | Doc Design | 14.5 | 67161 | EA 74527 - Compact Roundabout on US-95A at Cottonwood, Fernley | 74527 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-12-21T08:00:00Z |  | 3 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90482 | Intermediate Design | 18 | 67161 | EA 74527 - Compact Roundabout on US-95A at Cottonwood, Fernley | 74527 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-12-21T08:00:00Z |  | 3 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90483 | Post Doc Design | 0 | 67161 | EA 74527 - Compact Roundabout on US-95A at Cottonwood, Fernley | 74527 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-12-21T08:00:00Z |  | 3 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90484 | QAQC Design | 12 | 67161 | EA 74527 - Compact Roundabout on US-95A at Cottonwood, Fernley | 74527 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-12-21T08:00:00Z |  | 3 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90485 | QAQC Design | 4 | 68958 | EA 74561 / xxxxx - D2 Kietzke Ln PHB Ped Crossing | 74561 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-12-30T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90486 | DOC Design | 7.5 | 68958 | EA 74561 / xxxxx - D2 Kietzke Ln PHB Ped Crossing | 74561 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-12-30T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90487 | Doc Design | 23.5 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90488 | Intermediate Design | 26.5 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90489 | Post Doc Design | 5.5 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90490 | Preliminary 30% Design | 2 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90491 | QAQC Design | 25 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
90492 | Doc Design | 4.5 | 69531 | EA 61159 (No 70K#) - US95 / SR266 Highway Lighting | 61159 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-02-26T08:00:00Z |  | 2025-10-06T07:00:00Z | 3 |  |  | State Route | 61159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90493 | Intermediate Design | 9 | 69531 | EA 61159 (No 70K#) - US95 / SR266 Highway Lighting | 61159 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-02-26T08:00:00Z |  | 2025-10-06T07:00:00Z | 3 |  |  | State Route | 61159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90494 | Post Doc Design | 0.5 | 69531 | EA 61159 (No 70K#) - US95 / SR266 Highway Lighting | 61159 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-02-26T08:00:00Z |  | 2025-10-06T07:00:00Z | 3 |  |  | State Route | 61159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90495 | QAQC Design | 6.5 | 69531 | EA 61159 (No 70K#) - US95 / SR266 Highway Lighting | 61159 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-02-26T08:00:00Z |  | 2025-10-06T07:00:00Z | 3 |  |  | State Route | 61159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90496 | Doc Design | 23.5 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
90497 | Intermediate Design | 38.5 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
90498 | Post Doc Design | 5.5 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
90499 | Preliminary 30% Design | 0.5 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
90500 | QAQC Design | 25 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
90501 | P7 - #06 – on US95 at MM 95.26 | 59 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
90502 | P1 - #17 – Yerington, Alt US-95 MM 10.96 | 59 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
90503 | P2 - #13 – Fallon, US-95 MM 21.3 | 59 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
90504 | P3 - #12 – Shurz, US-95 MM 0.05 | 47 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
90505 | P4 - #03 – Indian Springs, US-95 MM 120 | 56 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
90506 | P5 - #04 on US95 at MM 30.2 | 47 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
90507 | P6 - #05 on US95 at MM 59.12 | 52 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
90508 | Intermediate Design | 20 | 72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | 9122x | Signals Lighting and ITS | Project | Approved |  |  |  |  | 2026-01-06T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90509 | PS&E Design | 6 | 72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | 9122x | Signals Lighting and ITS | Project | Approved |  |  |  |  | 2026-01-06T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90510 | Doc Submittal | 3 | 72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | 9122x | Signals Lighting and ITS | Project | Approved |  |  |  |  | 2026-01-06T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90511 | Design Schedules Update | 68 | 77403 | EA 9110 - Design Schedules Update | 9110 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90512 | Doc Design | 18 | 81069 | EA 74230 - I-15 S. - Construct Via Nobila Interchange | 74230 | Signals Lighting and ITS\2024 Sprint 22 | Project | Approved |  |  |  |  | 2026-11-01T08:00:00Z | 3 |  | State | Interstate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90513 | Intermediate Design | 40 | 81069 | EA 74230 - I-15 S. - Construct Via Nobila Interchange | 74230 | Signals Lighting and ITS\2024 Sprint 22 | Project | Approved |  |  |  |  | 2026-11-01T08:00:00Z | 3 |  | State | Interstate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90514 | Post Doc Design | 0 | 81069 | EA 74230 - I-15 S. - Construct Via Nobila Interchange | 74230 | Signals Lighting and ITS\2024 Sprint 22 | Project | Approved |  |  |  |  | 2026-11-01T08:00:00Z | 3 |  | State | Interstate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90515 | QAQC Design | 24 | 81069 | EA 74230 - I-15 S. - Construct Via Nobila Interchange | 74230 | Signals Lighting and ITS\2024 Sprint 22 | Project | Approved |  |  |  |  | 2026-11-01T08:00:00Z | 3 |  | State | Interstate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90516 | Preliminary 30% Design | 14 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2024-11-13T08:00:00Z |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90517 | Intermediate Design | 21.5 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90518 | QAQC Design | 24 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90519 | Doc Design | 23.5 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90520 | Post Doc Design | 5.5 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90521 | Preliminary 30% Design | 24 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2024-12-13T08:00:00Z |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90522 | Intermediate Design | 21.5 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90523 | QAQC Design | 24 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90524 | Doc Design | 23.5 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90525 | Post Doc Design | 5.5 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90526 | Preliminary 30% Design | 34 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2024-01-13T08:00:00Z |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90527 | Intermediate Design | 21.5 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90528 | QAQC Design | 24 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90529 | Doc Design | 23.5 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90530 | Post Doc Design | 5.5 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90531 | Preliminary 30% Design | 4 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-03-13T08:00:00Z |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90532 | Intermediate Design | 21.5 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90533 | QAQC Design | 24 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90534 | Doc Design | 23.5 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90535 | Post Doc Design | 5.5 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90536 | Preliminary 30% Design | 14 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-04-27T08:00:00Z |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90537 | Intermediate Design | 21.5 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90538 | QAQC Design | 24 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90539 | Doc Design | 23.5 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90540 | Post Doc Design | 5.5 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90541 | Preliminary 30% Design | 64 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-06-13T08:00:00Z |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90542 | Intermediate Design | 21.5 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90543 | QAQC Design | 24 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90544 | Doc Design | 23.5 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90545 | Post Doc Design | 5.5 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90546 | Preliminary 30% Design | 54 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-07-13T08:00:00Z |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90547 | Intermediate Design | 21.5 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90548 | QAQC Design | 24 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90549 | Doc Design | 23.5 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90550 | Post Doc Design | 5.5 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90551 | Preliminary 30% Design | 44 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-08-29T07:00:00Z |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90552 | Intermediate Design | 21.5 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90553 | QAQC Design | 24 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90554 | Doc Design | 23.5 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90555 | Post Doc Design | 5.5 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90556 | Preliminary 30% Design | 34 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-10-13T07:00:00Z |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90557 | Intermediate Design | 21.5 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90558 | QAQC Design | 24 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90559 | Doc Design | 23.5 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90560 | Post Doc Design | 5.5 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90561 | Preliminary 30% Design | 24 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-11-27T07:00:00Z |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90562 | Intermediate Design | 21.5 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90563 | QAQC Design | 24 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90564 | Doc Design | 23.5 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90565 | Post Doc Design | 5.5 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90566 | Preliminary 30% Design | 14 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90567 | Intermediate Design | 21.5 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90568 | QAQC Design | 24 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90569 | Doc Design | 23.5 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
90570 | Post Doc Design | 5.5 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0