## Sheet1
epics_System_Id | epics_System_Title | total_effort_from_pbis | projects_Work_Item_ID | projects_Title | projects_EA_Number | projects_Iteration_Path | projects_Work_Item_Type | projects_State | projects_Scoping_30_Percent | projects_SeventyFivePercentComplete | projects_Intermediate_Date | projects_QAQC_Submittal_Date | projects_Document_Submittal_Date | projects_Priority_Traffic_Ops | projects_Fiscal_Year | projects_Funding_Source | projects_Route_Type | projects_Construction_EA_Number | projects_Official_DOC_Date | projects_Anchor_Project | projects_Complexity_Signals | projects_Complexity_Lighting | projects_Complexity_ITS | projects_Complexity_Power_Design | projects_Complexity_RoW_Coordination | projects_Complexity_SLI_Project_Lead | projects_Complexity_Solar_Design | projects_Complexity_Trunkline
38658 | DOC Design | 18 | 7203 | EA 73928 - Tonopah CMAR Road Reconstruction | 73928 | Signals Lighting and ITS | Project | Actively Working |  |  | 2030-01-01T08:00:00Z | 2023-01-01T08:00:00Z | 2023-01-01T08:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38660 | QA/QC Design | 12 | 7203 | EA 73928 - Tonopah CMAR Road Reconstruction | 73928 | Signals Lighting and ITS | Project | Actively Working |  |  | 2030-01-01T08:00:00Z | 2023-01-01T08:00:00Z | 2023-01-01T08:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38661 | Intermediate Design | 16 | 7203 | EA 73928 - Tonopah CMAR Road Reconstruction | 73928 | Signals Lighting and ITS | Project | Actively Working |  |  | 2030-01-01T08:00:00Z | 2023-01-01T08:00:00Z | 2023-01-01T08:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44061 | Archive - Internal design (void) | 39 | 7203 | EA 73928 - Tonopah CMAR Road Reconstruction | 73928 | Signals Lighting and ITS | Project | Actively Working |  |  | 2030-01-01T08:00:00Z | 2023-01-01T08:00:00Z | 2023-01-01T08:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38617 | Post Doc Design | 8 | 7304 | C 3858 - EA 74153 - SR-431 (Mt Rose) 3R fm. SR 28 to 0.062 NE of summit. | 74153 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38478 | QA/QC Design | 29 | 7452 | EA 74151 - I-80 & Mote Road (3R) | 74151 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38480 | DOC Design | 8 | 7452 | EA 74151 - I-80 & Mote Road (3R) | 74151 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38582 | 30% Design | 11.5 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38591 | Intermediate Design | 19 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38603 | QAQC Design | 24 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38609 | Doc Design | 11.5 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38614 | Post Doc Design | 0.5 | 7617 | EA 74209 - US-395 N. Valleys Ph2 (Golden Valley to Stead) | 74209 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-10-27T07:00:00Z | [6 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38510 | QAQC Design | 5 | 7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | 73840 | Signals Lighting and ITS | Project | Actively Working |  |  | 2026-06-01T07:00:00Z | 2026-11-02T08:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | State | State Route | 60690 | 2027-02-15T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38511 | DOC Design | 11.5 | 7647 | EA 73840 / 60690 - FAST Pkg K2 - SR-163 from US-95 to Laughlin | 73840 | Signals Lighting and ITS | Project | Actively Working |  |  | 2026-06-01T07:00:00Z | 2026-11-02T08:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | State | State Route | 60690 | 2027-02-15T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38581 | 30% Design | 7 | 8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | 74321 | Signals Lighting and ITS | Project | Actively Working | 2022-11-30T08:00:00Z | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38590 | Intermediate Design | 35 | 8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | 74321 | Signals Lighting and ITS | Project | Actively Working | 2022-11-30T08:00:00Z | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38602 | QAQC Design | 12 | 8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | 74321 | Signals Lighting and ITS | Project | Actively Working | 2022-11-30T08:00:00Z | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38608 | Doc Design | 13 | 8030 | EA 74321 - Cheyenne Avenue and Jones Boulevard Safety Project | 74321 | Signals Lighting and ITS | Project | Actively Working | 2022-11-30T08:00:00Z | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38571 | Intermediate Design | 20.5 | 8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | 74471 | Signals Lighting and ITS | Project | On-Hold |  |  | 2024-02-06T08:00:00Z | 2024-07-30T07:00:00Z | 2024-10-29T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38573 | QAQC Design | 15 | 8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | 74471 | Signals Lighting and ITS | Project | On-Hold |  |  | 2024-02-06T08:00:00Z | 2024-07-30T07:00:00Z | 2024-10-29T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38574 | DOC Design | 10 | 8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | 74471 | Signals Lighting and ITS | Project | On-Hold |  |  | 2024-02-06T08:00:00Z | 2024-07-30T07:00:00Z | 2024-10-29T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38575 | Post DOC Design | 1 | 8120 | EA 74471/61082 (Ph1-EA 74247) - US-6 Mill & Fill fr CA/NV Line to MI/ES Line - Ph2 | 74471 | Signals Lighting and ITS | Project | On-Hold |  |  | 2024-02-06T08:00:00Z | 2024-07-30T07:00:00Z | 2024-10-29T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38579 | 30% Design | 6 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38589 | Intermediate Design | 37 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38601 | QAQC Design | 21.5 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38607 | Doc Design | 21 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38616 | Post Doc Design | 0 | 19358 | EA 74316 - I-580 fm College Pkwy to Damonte Ranch Pkwy, PCEMS 1-25001 | 74316 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2025-02-24T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39060 | Intermediate Design | 0 | 19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | 74309 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39062 | QAQC Design | 0 | 19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | 74309 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39067 | DOC Design | 0 | 19435 | Cancelled_EA 74309 - FAST Pkg J - SR-160 (Blue Diamond) fm I-15 to CL/NY line | 74309 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39095 | Post-DOC Design | 2 | 23624 | C3945 - EA 69999 - PCEMS 8-00251C - Adaptive / Managed Lighting Pilot Project Development | 69999 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2022-08-01T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38618 | Intermediate Design | 1 | 26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | 74361 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38619 | QA/QC Design | 26.5 | 26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | 74361 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38620 | DOC Design | 12 | 26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | 74361 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38662 | Post-DOC | 0.5 | 26338 | EA 74361 - 3R SR-294 (Grass Valley) in Winnemucca | 74361 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38578 | Intermediate Design | 17.5 | 30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | 60988 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38583 | QAQC Design | 16.5 | 30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | 60988 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38585 | DOC Design | 9 | 30819 | EA 60988 - SR160 Emergency Signal for Nye County Fire | 60988 | Signals Lighting and ITS | Project | On-Hold | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38466 | Intermediate Design | 57 | 33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | 74448 | Signals Lighting and ITS | Project | On-Hold |  |  | 2023-01-30T08:00:00Z | 2023-08-07T07:00:00Z | 2023-10-23T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38467 | QA/QC Design | 33 | 33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | 74448 | Signals Lighting and ITS | Project | On-Hold |  |  | 2023-01-30T08:00:00Z | 2023-08-07T07:00:00Z | 2023-10-23T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38468 | DOC Design | 16 | 33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | 74448 | Signals Lighting and ITS | Project | On-Hold |  |  | 2023-01-30T08:00:00Z | 2023-08-07T07:00:00Z | 2023-10-23T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38469 | Post-DOC | 0.5 | 33613 | EA 74448 - I-80/Exit 173 W. Winnemucca Interchange | 74448 | Signals Lighting and ITS | Project | On-Hold |  |  | 2023-01-30T08:00:00Z | 2023-08-07T07:00:00Z | 2023-10-23T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38245 | 30% Design | 0.5 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38247 | Intermediate Design | 83 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38250 | QAQC Design | 28 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38251 | Doc Design | 16 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38252 | Post Doc Design | 0 | 38241 | EA 74319 - SR 595 RAINBOW BLVD fm. W. TROP. to Silverstream DR (Test Feature Assignments) | 74319 | Signals Lighting and ITS | Project | Actively Working | 2023-01-17T08:00:00Z |  | 2023-08-14T07:00:00Z | 2024-07-08T07:00:00Z | 2024-11-04T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38879 | QA/QC Design | 6 | 38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | 74359 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2024-12-11T08:00:00Z | 2025-02-10T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38880 | DOC Design | 5.5 | 38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | 74359 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2024-12-11T08:00:00Z | 2025-02-10T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38881 | Post-DOC Design | 0.5 | 38871 | EA 74359 - EA 69963 - US-95A Yerington 3R - Ph 2 | 74359 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2024-12-11T08:00:00Z | 2025-02-10T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38954 | 30% Design | 33.5 | 38953 | EA 74375 - US 395 Carson Valley Phase 1 | 74375 | Signals Lighting and ITS | Project | Actively Working |  |  | 2022-11-14T08:00:00Z | 2023-03-20T07:00:00Z | 2023-06-05T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38955 | Intermediate Design | 85.25 | 38953 | EA 74375 - US 395 Carson Valley Phase 1 | 74375 | Signals Lighting and ITS | Project | Actively Working |  |  | 2022-11-14T08:00:00Z | 2023-03-20T07:00:00Z | 2023-06-05T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38956 | QA/QC Design | 35.5 | 38953 | EA 74375 - US 395 Carson Valley Phase 1 | 74375 | Signals Lighting and ITS | Project | Actively Working |  |  | 2022-11-14T08:00:00Z | 2023-03-20T07:00:00Z | 2023-06-05T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38957 | DOC Design | 14 | 38953 | EA 74375 - US 395 Carson Valley Phase 1 | 74375 | Signals Lighting and ITS | Project | Actively Working |  |  | 2022-11-14T08:00:00Z | 2023-03-20T07:00:00Z | 2023-06-05T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38969 | QA/QC Design | 96 | 38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | 74191 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2022-04-25T07:00:00Z | 2022-07-18T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38971 | DOC Design | 17 | 38973 | C 3947 - EA 74191 - I-80 fm CA/NV to Keystone | 74191 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2022-04-25T07:00:00Z | 2022-07-18T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38975 | DOC Design | 7.5 | 38980 | EA 74178 / 69920 - SR-207 (Kingsbury grade) 3R | 74178 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-12-27T08:00:00Z | 3 | 2027 | Federal | State Route |  | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
38977 | Post-DOC | 0.5 | 38980 | EA 74178 / 69920 - SR-207 (Kingsbury grade) 3R | 74178 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-12-27T08:00:00Z | 3 | 2027 | Federal | State Route |  | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
38979 | QA/QC Design | 4 | 38980 | EA 74178 / 69920 - SR-207 (Kingsbury grade) 3R | 74178 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-12-27T08:00:00Z | 3 | 2027 | Federal | State Route |  | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
39000 | Intermediate Design | 85.25 | 38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | 74347 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39001 | QA/QC Design | 34.5 | 38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | 74347 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39002 | DOC Design | 14 | 38998 | EA 74347 / 69979 - D1 Lamb Blvd 3R | 74347 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54682 | 9106 - 2024 Standard Plans Update | 0 | 43326 | Standard Plans Updates | 9106 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64869 | 9106 - 2026 Standard Plans Update | 2 | 43326 | Standard Plans Updates | 9106 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45285 | Intermediate Design | 51 | 45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | 74357 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2025-01-06T08:00:00Z | 3 | 2025 | Federal | State Route | 61035 | 2025-01-20T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
45287 | DOC Design | 9 | 45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | 74357 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2025-01-06T08:00:00Z | 3 | 2025 | Federal | State Route | 61035 | 2025-01-20T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
45288 | Post-DOC Design | 0.5 | 45020 | EA 74357 / 61035 - Sunset (SR562) and SR-171 Mill and Overlay | 74357 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2025-01-06T08:00:00Z | 3 | 2025 | Federal | State Route | 61035 | 2025-01-20T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
45614 | Intermediate Design | 67 | 45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | 74453 | Signals Lighting and ITS | Project | On-Hold |  |  | 2022-11-21T08:00:00Z | 2023-05-01T07:00:00Z | 2024-10-28T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45619 | QAQC Design | 45 | 45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | 74453 | Signals Lighting and ITS | Project | On-Hold |  |  | 2022-11-21T08:00:00Z | 2023-05-01T07:00:00Z | 2024-10-28T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45623 | Doc Design | 20 | 45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | 74453 | Signals Lighting and ITS | Project | On-Hold |  |  | 2022-11-21T08:00:00Z | 2023-05-01T07:00:00Z | 2024-10-28T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45625 | Post Doc Design | 0.5 | 45239 | EA 74453 (61075) I-15 Northbound Paving CA/NV Line to 3.725 Miles North of Jean Interchange | 74453 | Signals Lighting and ITS | Project | On-Hold |  |  | 2022-11-21T08:00:00Z | 2023-05-01T07:00:00Z | 2024-10-28T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48181 | QAQC Design | 0 | 45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | 74462 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-04T08:00:00Z | 5 | 2025 | Federal | Interstate | 61079 | 2024-11-11T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
48183 | Post-DOC Design | 0.5 | 45827 | EA 74462 / 61079 - IR215 Windmill to South Valley View | 74462 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-04T08:00:00Z | 5 | 2025 | Federal | Interstate | 61079 | 2024-11-11T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
47276 | Intermediate Design | 32 | 46165 | Fiber Hut - Trinity Rest Area | 9104 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2023-06-16T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47277 | QAQC Design | 14 | 46165 | Fiber Hut - Trinity Rest Area | 9104 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2023-06-16T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47278 | DOC Design | 7 | 46165 | Fiber Hut - Trinity Rest Area | 9104 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2023-06-16T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47897 | 30% Design | 9 | 46165 | Fiber Hut - Trinity Rest Area | 9104 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2023-06-16T07:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38482 | QA/QC Design | 37 | 46368 | EA 74346 / EA 69981 - US 50, Fallon, 3R - PH2 | 74346 | Signals Lighting and ITS | Project | Actively Working |  | 2024-10-22T07:00:00Z |  |  | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 69981 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
38484 | DOC Design | 15 | 46368 | EA 74346 / EA 69981 - US 50, Fallon, 3R - PH2 | 74346 | Signals Lighting and ITS | Project | Actively Working |  | 2024-10-22T07:00:00Z |  |  | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 69981 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
79111 | 75% Design | 6 | 46368 | EA 74346 / EA 69981 - US 50, Fallon, 3R - PH2 | 74346 | Signals Lighting and ITS | Project | Actively Working |  | 2024-10-22T07:00:00Z |  |  | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 69981 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
47247 | QAQC Design | 13.5 | 46386 | EA 74454 / 61076 - US 93 and SR 173 (Boulder) Preservation | 74454 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-08-03T07:00:00Z | 2026-12-21T08:00:00Z | 3 | 2027 | Federal | Highway | 61076 | 2027-01-04T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
47268 | DOC Design | 20.5 | 46386 | EA 74454 / 61076 - US 93 and SR 173 (Boulder) Preservation | 74454 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-08-03T07:00:00Z | 2026-12-21T08:00:00Z | 3 | 2027 | Federal | Highway | 61076 | 2027-01-04T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
47269 | Post-DOC | 1 | 46386 | EA 74454 / 61076 - US 93 and SR 173 (Boulder) Preservation | 74454 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-08-03T07:00:00Z | 2026-12-21T08:00:00Z | 3 | 2027 | Federal | Highway | 61076 | 2027-01-04T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
51299 | Intermediate Design | 1 | 48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | 74463 | Signals Lighting and ITS | Project | Actively Working |  | 2025-01-13T08:00:00Z |  | 2025-06-16T07:00:00Z | 2025-09-15T07:00:00Z | 4 | 2026 | Federal | Interstate | 61080 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
51415 | 75% Design | 21 | 48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | 74463 | Signals Lighting and ITS | Project | Actively Working |  | 2025-01-13T08:00:00Z |  | 2025-06-16T07:00:00Z | 2025-09-15T07:00:00Z | 4 | 2026 | Federal | Interstate | 61080 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
51436 | Doc Design | 17.5 | 48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | 74463 | Signals Lighting and ITS | Project | Actively Working |  | 2025-01-13T08:00:00Z |  | 2025-06-16T07:00:00Z | 2025-09-15T07:00:00Z | 4 | 2026 | Federal | Interstate | 61080 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
51452 | Post Doc Design | 0.5 | 48702 | EA 74463 / 61080 IR15 Garnet to South of Valley of Fire | 74463 | Signals Lighting and ITS | Project | Actively Working |  | 2025-01-13T08:00:00Z |  | 2025-06-16T07:00:00Z | 2025-09-15T07:00:00Z | 4 | 2026 | Federal | Interstate | 61080 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
49348 | Intermediate Design | 2 | 48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | 74458 | Signals Lighting and ITS | Project | Actively Working |  | 2024-11-18T08:00:00Z |  | 2025-07-21T07:00:00Z | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 61077 | 2025-12-08T08:00:00Z | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
49349 | QAQC Design | 17 | 48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | 74458 | Signals Lighting and ITS | Project | Actively Working |  | 2024-11-18T08:00:00Z |  | 2025-07-21T07:00:00Z | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 61077 | 2025-12-08T08:00:00Z | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
49350 | DOC Design | 9 | 48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | 74458 | Signals Lighting and ITS | Project | Actively Working |  | 2024-11-18T08:00:00Z |  | 2025-07-21T07:00:00Z | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 61077 | 2025-12-08T08:00:00Z | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
49351 | Post-DOC | 0.5 | 48703 | EA 74458 / 61077 US95, Indian Springs, from North of SR157 to Indian Springs PDFS | 74458 | Signals Lighting and ITS | Project | Actively Working |  | 2024-11-18T08:00:00Z |  | 2025-07-21T07:00:00Z | 2025-10-20T07:00:00Z | 3 | 2026 | Federal | Highway | 61077 | 2025-12-08T08:00:00Z | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
57702 | Doc Design | 23.5 | 48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | 74488 | Signals Lighting and ITS | Project | Actively Working | 2024-09-02T07:00:00Z |  | 2025-01-13T08:00:00Z | 2025-07-28T07:00:00Z | 2025-10-27T07:00:00Z | 4 | 2026 | Federal | State Route | 61094 | 2025-12-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
57724 | Intermediate Design | 7 | 48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | 74488 | Signals Lighting and ITS | Project | Actively Working | 2024-09-02T07:00:00Z |  | 2025-01-13T08:00:00Z | 2025-07-28T07:00:00Z | 2025-10-27T07:00:00Z | 4 | 2026 | Federal | State Route | 61094 | 2025-12-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
57761 | Post Doc Design | 5.5 | 48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | 74488 | Signals Lighting and ITS | Project | Actively Working | 2024-09-02T07:00:00Z |  | 2025-01-13T08:00:00Z | 2025-07-28T07:00:00Z | 2025-10-27T07:00:00Z | 4 | 2026 | Federal | State Route | 61094 | 2025-12-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
57769 | QAQC Design | 13 | 48704 | EA 74488 / 61094 - SR-445 fm Golden View to Egyptian 3R | 74488 | Signals Lighting and ITS | Project | Actively Working | 2024-09-02T07:00:00Z |  | 2025-01-13T08:00:00Z | 2025-07-28T07:00:00Z | 2025-10-27T07:00:00Z | 4 | 2026 | Federal | State Route | 61094 | 2025-12-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
42326 | IMD Design | 29.5 | 48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | 74108 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-10T08:00:00Z |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | Highway | 69974 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
42327 | QAQC Design | 32 | 48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | 74108 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-10T08:00:00Z |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | Highway | 69974 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
49569 | DOC Design | 14.5 | 48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | 74108 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-10T08:00:00Z |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | Highway | 69974 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
49570 | Post-DOC | 0.5 | 48723 | EA 74108 / 69974 Waterloo Ph2 - US-395 from Waterloo Ln. to 1st St. | 74108 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-10T08:00:00Z |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | Highway | 69974 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
50105 | Intermediate | 22.5 | 49534 | EA 74249 / 69980 - US-50 in East Lake Tahoe Ph2 | 74249 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-09-29T07:00:00Z | 2026-03-28T07:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | Federal | Highway | 69980 | 2027-02-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
50353 | QA/QC Design | 32 | 49534 | EA 74249 / 69980 - US-50 in East Lake Tahoe Ph2 | 74249 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-09-29T07:00:00Z | 2026-03-28T07:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | Federal | Highway | 69980 | 2027-02-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
50354 | DOC Design | 13 | 49534 | EA 74249 / 69980 - US-50 in East Lake Tahoe Ph2 | 74249 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-09-29T07:00:00Z | 2026-03-28T07:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | Federal | Highway | 69980 | 2027-02-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
50355 | Post-DOC | 2 | 49534 | EA 74249 / 69980 - US-50 in East Lake Tahoe Ph2 | 74249 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-09-29T07:00:00Z | 2026-03-28T07:00:00Z | 2027-02-01T08:00:00Z | 3 | 2027 | Federal | Highway | 69980 | 2027-02-15T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
53145 | QAQC Design | 17 | 51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | 74450 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-09-15T07:00:00Z | 2025-11-18T08:00:00Z | 3 | 2025 | Federal | Interstate | 61073 | 2025-02-02T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53146 | Doc Design | 21.5 | 51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | 74450 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-09-15T07:00:00Z | 2025-11-18T08:00:00Z | 3 | 2025 | Federal | Interstate | 61073 | 2025-02-02T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53148 | Post Doc Design | 5.5 | 51583 | EA 74450 / 61073 - IR 80, Fernley, Painted Rock Interchange to East Fernley Grade Separation | 74450 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-09-15T07:00:00Z | 2025-11-18T08:00:00Z | 3 | 2025 | Federal | Interstate | 61073 | 2025-02-02T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56700 | Intermediate Design | 27.5 | 51820 | EA 74477 / 61086 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | 74477 | Signals Lighting and ITS | Project | On-Hold |  |  | 2025-03-02T08:00:00Z | 2025-09-02T07:00:00Z | 2025-12-01T08:00:00Z |  | 2026 | Federal | Highway | 61086 | 2025-12-15T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
56733 | QAQC Design | 25 | 51820 | EA 74477 / 61086 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | 74477 | Signals Lighting and ITS | Project | On-Hold |  |  | 2025-03-02T08:00:00Z | 2025-09-02T07:00:00Z | 2025-12-01T08:00:00Z |  | 2026 | Federal | Highway | 61086 | 2025-12-15T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
56734 | Doc Design | 23.5 | 51820 | EA 74477 / 61086 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | 74477 | Signals Lighting and ITS | Project | On-Hold |  |  | 2025-03-02T08:00:00Z | 2025-09-02T07:00:00Z | 2025-12-01T08:00:00Z |  | 2026 | Federal | Highway | 61086 | 2025-12-15T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
56735 | Post Doc Design | 5.5 | 51820 | EA 74477 / 61086 - US-93 fm 0.85 miles north of Broadway Ave to Pahrock Summit | 74477 | Signals Lighting and ITS | Project | On-Hold |  |  | 2025-03-02T08:00:00Z | 2025-09-02T07:00:00Z | 2025-12-01T08:00:00Z |  | 2026 | Federal | Highway | 61086 | 2025-12-15T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
53595 | Intermediate Design | 0 | 53326 | C 4509 / EA 74505 / (No60K) - Carlin Tunnel Relight Project | 74505 | Signals Lighting and ITS | Project | Actively Working | [5 empty] | 3 | 2024 | State | Interstate |  | 2024-01-08T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56659 | Intermediate Design | 0 | 53336 | EA 74493 / 61098 - I-80 Oasis | 74493 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-06-30T07:00:00Z | 3 | 2026 | Federal | Interstate | 61098 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
57099 | QAQC Design | 4 | 53336 | EA 74493 / 61098 - I-80 Oasis | 74493 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-06-30T07:00:00Z | 3 | 2026 | Federal | Interstate | 61098 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
57125 | Doc Design | 13 | 53336 | EA 74493 / 61098 - I-80 Oasis | 74493 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-06-30T07:00:00Z | 3 | 2026 | Federal | Interstate | 61098 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
57128 | Post Doc Design | 0.5 | 53336 | EA 74493 / 61098 - I-80 Oasis | 74493 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-03-03T08:00:00Z | 2025-06-30T07:00:00Z | 3 | 2026 | Federal | Interstate | 61098 | 2025-11-03T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
57205 | Intermediate Design | 10 | 54531 | EA 74449 / 61072 - US-50, Middlegate | 74449 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-06T08:00:00Z | 2025-11-10T08:00:00Z | 2026-01-12T08:00:00Z | 3 | 2026 | Federal | Highway | 61072 | 2026-01-26T08:00:00Z | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0
57206 | QAQC Design | 13.5 | 54531 | EA 74449 / 61072 - US-50, Middlegate | 74449 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-06T08:00:00Z | 2025-11-10T08:00:00Z | 2026-01-12T08:00:00Z | 3 | 2026 | Federal | Highway | 61072 | 2026-01-26T08:00:00Z | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0
57207 | DOC Design | 8.5 | 54531 | EA 74449 / 61072 - US-50, Middlegate | 74449 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-06T08:00:00Z | 2025-11-10T08:00:00Z | 2026-01-12T08:00:00Z | 3 | 2026 | Federal | Highway | 61072 | 2026-01-26T08:00:00Z | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0
57208 | Post DOC Design | 1 | 54531 | EA 74449 / 61072 - US-50, Middlegate | 74449 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-06T08:00:00Z | 2025-11-10T08:00:00Z | 2026-01-12T08:00:00Z | 3 | 2026 | Federal | Highway | 61072 | 2026-01-26T08:00:00Z | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0
57131 | Intermediate Design | 2 | 55804 | EA 74494 / 61099 - US-93 Lages Station | 74494 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-18T08:00:00Z | 3 | 2025 | Federal | Highway | 61099 | 2024-12-02T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
57141 | QAQC Design | 1 | 55804 | EA 74494 / 61099 - US-93 Lages Station | 74494 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-18T08:00:00Z | 3 | 2025 | Federal | Highway | 61099 | 2024-12-02T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
57142 | DOC Design | 5 | 55804 | EA 74494 / 61099 - US-93 Lages Station | 74494 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-18T08:00:00Z | 3 | 2025 | Federal | Highway | 61099 | 2024-12-02T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
57143 | Post DOC Design | 1 | 55804 | EA 74494 / 61099 - US-93 Lages Station | 74494 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-11-18T08:00:00Z | 3 | 2025 | Federal | Highway | 61099 | 2024-12-02T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
56822 | Doc Design | 26.5 | 56358 | EA 74491 / 61096 - US-50 Carson to Spooner | 74491 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-03T08:00:00Z | 2025-08-20T07:00:00Z | 2025-12-22T08:00:00Z |  |  |  |  | 61096 | 2026-01-05T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
56844 | Intermediate Design | 24.5 | 56358 | EA 74491 / 61096 - US-50 Carson to Spooner | 74491 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-03T08:00:00Z | 2025-08-20T07:00:00Z | 2025-12-22T08:00:00Z |  |  |  |  | 61096 | 2026-01-05T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
56881 | Post Doc Design | 5.5 | 56358 | EA 74491 / 61096 - US-50 Carson to Spooner | 74491 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-03T08:00:00Z | 2025-08-20T07:00:00Z | 2025-12-22T08:00:00Z |  |  |  |  | 61096 | 2026-01-05T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
56889 | QAQC Design | 40.5 | 56358 | EA 74491 / 61096 - US-50 Carson to Spooner | 74491 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-01-03T08:00:00Z | 2025-08-20T07:00:00Z | 2025-12-22T08:00:00Z |  |  |  |  | 61096 | 2026-01-05T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
60574 | Doc Design | 6.5 | 60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | 74486 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-08-27T07:00:00Z | 2025-12-08T08:00:00Z | 3 | 2025 | State | Highway | 61093 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60633 | Post Doc Design | 0.5 | 60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | 74486 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-08-27T07:00:00Z | 2025-12-08T08:00:00Z | 3 | 2025 | State | Highway | 61093 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60673 | QAQC Design | 10 | 60078 | EA 74486 / 61093 - US-6 PIP - BlueJay | 74486 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2025-08-27T07:00:00Z | 2025-12-08T08:00:00Z | 3 | 2025 | State | Highway | 61093 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66294 | Intermediate Design | 39 | 60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | 74489 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2026-12-28T08:00:00Z | 3 | 2027 | Federal | State Route | 61095 | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
66295 | QAQC Design | 35.5 | 60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | 74489 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2026-12-28T08:00:00Z | 3 | 2027 | Federal | State Route | 61095 | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
66296 | DOC Design | 23.5 | 60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | 74489 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2026-12-28T08:00:00Z | 3 | 2027 | Federal | State Route | 61095 | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
66297 | Post-DOC Design | 0.5 | 60441 | EA 74489 / 61095 SR-28 between Spooner and incline Project (Tyler Wood) - Current DOC date 2027 | 74489 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2026-12-28T08:00:00Z | 3 | 2027 | Federal | State Route | 61095 | 2027-01-11T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
62597 | Preliminary 30% Design | 14 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 62169 | EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-07-21T07:00:00Z | 2025-09-29T07:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
64711 | Intermediate Design | 18.5 | 62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. | 74484 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-04T08:00:00Z | 2026-07-27T07:00:00Z | 2026-10-05T07:00:00Z |  |  |  |  | 61180 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64712 | QAQC Design | 26 | 62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. | 74484 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-04T08:00:00Z | 2026-07-27T07:00:00Z | 2026-10-05T07:00:00Z |  |  |  |  | 61180 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64713 | Doc Design | 16.5 | 62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. | 74484 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-04T08:00:00Z | 2026-07-27T07:00:00Z | 2026-10-05T07:00:00Z |  |  |  |  | 61180 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64714 | Post Doc Design | 6 | 62238 | EA 74484 / No60K - US-50 E. Carson City (DOC 11/26) - Dennis F. | 74484 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-04T08:00:00Z | 2026-07-27T07:00:00Z | 2026-10-05T07:00:00Z |  |  |  |  | 61180 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64982 | Preliminary Design | 4 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
65183 | Intermediate Design | 48.5 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
65279 | QAQC Design | 20 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
65297 | DOC Design | 11 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
65416 | Post-DOC Design | 0.5 | 62240 | EA 74476 / 61085 - SR-439 Fm 4.244 mls N. of LY/ST Line to the Jct. of Ramps 3&4 at IR-80 Doc 11/02/26 - New Chris Deal Project | 74476 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-10-19T07:00:00Z | 4 | 2027 | Federal | State Route | 61085 | 2026-11-02T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
63095 | Doc Design | 20 | 62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | 74495 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-11-01T08:00:00Z | 2027-01-12T08:00:00Z | 4 | 2025 | Federal | Highway | 61100 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63154 | Post Doc Design | 8 | 62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | 74495 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-11-01T08:00:00Z | 2027-01-12T08:00:00Z | 4 | 2025 | Federal | Highway | 61100 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63194 | QAQC Design | 25 | 62241 | EA 74495 / 61100 - FRHU20 Fm 0.46 W. of West Winnemucca Intch. Ramp 3 to W. Winnemucca Ramp 3. US-95 Fm W. Winnemucca Interch. ramp 3 to 3.549 mls N. of Reinhart Ln. Doc 11/04/24 - New Chris Deal Proj. | 74495 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-11-01T08:00:00Z | 2027-01-12T08:00:00Z | 4 | 2025 | Federal | Highway | 61100 | 2024-11-04T08:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62847 | Doc Design | 9 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
62869 | Intermediate Design | 28 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
62906 | Post Doc Design | 0.5 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
62914 | Preliminary Design | 4.5 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
62946 | QAQC Design | 18 | 62400 | EA 74483 / 61091 - US 50 East of Austin to SR 376 PIP - DOC 8/3/2026 - Vic Peters (Will need ROW) | 74483 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2026-01-18T08:00:00Z | 3 | 2027 | Federal | Highway | 61091 | 2027-02-01T08:00:00Z | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
65841 | Intermediate Design | 40 | 64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | 74432 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2027-07-19T07:00:00Z | [5 empty] | 2027-08-02T07:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65843 | QAQC Design | 25 | 64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | 74432 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2027-07-19T07:00:00Z | [5 empty] | 2027-08-02T07:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65844 | Doc Design | 23.5 | 64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | 74432 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2027-07-19T07:00:00Z | [5 empty] | 2027-08-02T07:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65845 | Post Doc Design | 5.5 | 64454 | EA 74432 Boulder L&A, SLI, and SSTC - DOC FY 2027 | 74432 | Signals Lighting and ITS | Project | On-Hold |  |  |  |  | 2027-07-19T07:00:00Z | [5 empty] | 2027-08-02T07:00:00Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67164 | Doc Design | 14.5 | 67161 | EA 74527 - Compact Roundabout on US-95A at Cottonwood, Fernley | 74527 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-12-21T08:00:00Z |  | 3 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67186 | Intermediate Design | 18 | 67161 | EA 74527 - Compact Roundabout on US-95A at Cottonwood, Fernley | 74527 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-12-21T08:00:00Z |  | 3 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67223 | Post Doc Design | 0 | 67161 | EA 74527 - Compact Roundabout on US-95A at Cottonwood, Fernley | 74527 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-12-21T08:00:00Z |  | 3 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67263 | QAQC Design | 12 | 67161 | EA 74527 - Compact Roundabout on US-95A at Cottonwood, Fernley | 74527 | Signals Lighting and ITS | Project | Actively Working |  |  |  | 2026-12-21T08:00:00Z |  | 3 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70347 | QAQC Design | 4 | 68958 | EA 74561 / xxxxx - D2 Kietzke Ln PHB Ped Crossing | 74561 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-12-30T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70348 | DOC Design | 7.5 | 68958 | EA 74561 / xxxxx - D2 Kietzke Ln PHB Ped Crossing | 74561 | Signals Lighting and ITS | Project | Actively Working |  |  |  |  | 2024-12-30T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69410 | Doc Design | 23.5 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
69432 | Intermediate Design | 26.5 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
69469 | Post Doc Design | 5.5 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
69477 | Preliminary 30% Design | 2 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
69509 | QAQC Design | 25 | 69407 | EA 74319 - PHB/Ped Signal Design | 74319 | Signals Lighting and ITS | Project | On-Hold | [5 empty] | 4 | 2025 | Federal |  | 61175 | 2025-02-24T08:00:00Z | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0
69534 | Doc Design | 4.5 | 69531 | EA 61159 (No 70K#) - US95 / SR266 Highway Lighting | 61159 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-02-26T08:00:00Z |  | 2025-10-06T07:00:00Z | 3 |  |  | State Route | 61159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69556 | Intermediate Design | 9 | 69531 | EA 61159 (No 70K#) - US95 / SR266 Highway Lighting | 61159 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-02-26T08:00:00Z |  | 2025-10-06T07:00:00Z | 3 |  |  | State Route | 61159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69593 | Post Doc Design | 0.5 | 69531 | EA 61159 (No 70K#) - US95 / SR266 Highway Lighting | 61159 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-02-26T08:00:00Z |  | 2025-10-06T07:00:00Z | 3 |  |  | State Route | 61159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69633 | QAQC Design | 6.5 | 69531 | EA 61159 (No 70K#) - US95 / SR266 Highway Lighting | 61159 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-02-26T08:00:00Z |  | 2025-10-06T07:00:00Z | 3 |  |  | State Route | 61159 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69658 | Doc Design | 23.5 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
69680 | Intermediate Design | 38.5 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
69717 | Post Doc Design | 5.5 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
69725 | Preliminary 30% Design | 0.5 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
69757 | QAQC Design | 25 | 69655 | EA 74444 / 61070 - US93 Wells, from Roadside Park to Thousand Spring Creek PDFS | 74444 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-01T08:00:00Z | 2025-09-29T07:00:00Z | 2025-12-29T08:00:00Z | [6 empty] | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
72078 | P7 - #06 – on US95 at MM 95.26 | 59 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
72079 | P1 - #17 – Yerington, Alt US-95 MM 10.96 | 59 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
72080 | P2 - #13 – Fallon, US-95 MM 21.3 | 59 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
72081 | P3 - #12 – Shurz, US-95 MM 0.05 | 47 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
72082 | P4 - #03 – Indian Springs, US-95 MM 120 | 56 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
72083 | P5 - #04 on US95 at MM 30.2 | 47 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
72084 | P6 - #05 on US95 at MM 59.12 | 52 | 71927 | Communication Building Design | 9120x | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-18T08:00:00Z | 2025-08-25T07:00:00Z | 2025-11-17T08:00:00Z | 4 | 2026 |  | Highway |  |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
73537 | Intermediate Design | 20 | 72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | 9122x | Signals Lighting and ITS | Project | Approved |  |  |  |  | 2026-01-06T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73553 | PS&E Design | 6 | 72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | 9122x | Signals Lighting and ITS | Project | Approved |  |  |  |  | 2026-01-06T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73554 | Doc Submittal | 3 | 72612 | EA xxxxx / xxxxx - District 2 DMS and TTS panel replacements | 9122x | Signals Lighting and ITS | Project | Approved |  |  |  |  | 2026-01-06T08:00:00Z | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77406 | Design Schedules Update | 68 | 77403 | EA 9110 - Design Schedules Update | 9110 | Signals Lighting and ITS | Project | Actively Working | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81143 | Doc Design | 18 | 81069 | EA 74230 - I-15 S. - Construct Via Nobila Interchange | 74230 | Signals Lighting and ITS\2024 Sprint 22 | Project | Approved |  |  |  |  | 2026-11-01T08:00:00Z | 3 |  | State | Interstate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81165 | Intermediate Design | 40 | 81069 | EA 74230 - I-15 S. - Construct Via Nobila Interchange | 74230 | Signals Lighting and ITS\2024 Sprint 22 | Project | Approved |  |  |  |  | 2026-11-01T08:00:00Z | 3 |  | State | Interstate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81202 | Post Doc Design | 0 | 81069 | EA 74230 - I-15 S. - Construct Via Nobila Interchange | 74230 | Signals Lighting and ITS\2024 Sprint 22 | Project | Approved |  |  |  |  | 2026-11-01T08:00:00Z | 3 |  | State | Interstate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81242 | QAQC Design | 24 | 81069 | EA 74230 - I-15 S. - Construct Via Nobila Interchange | 74230 | Signals Lighting and ITS\2024 Sprint 22 | Project | Approved |  |  |  |  | 2026-11-01T08:00:00Z | 3 |  | State | Interstate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62597 | Preliminary 30% Design | 14 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2024-11-13T08:00:00Z |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 12345 | test EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-11-13T08:00:00Z | 2024-12-21T07:00:00Z | 2025-12-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 24 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2024-12-13T08:00:00Z |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 123456 | test 1EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-01-10T07:00:00Z | 2025-01-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 34 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2024-01-13T08:00:00Z |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 1234567 | test3EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-01-13T08:00:00Z | 2025-02-12T07:00:00Z | 2025-02-28T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 4 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-03-13T08:00:00Z |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 12345678 | test 4EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-03-13T08:00:00Z | 2025-03-27T08:00:00Z | 2025-04-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 14 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-04-27T08:00:00Z |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 123456789 | test 5EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-04-27T08:00:00Z | 2025-05-13T08:00:00Z | 2025-05-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 64 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-06-13T08:00:00Z |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 2340 | test6EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-06-13T08:00:00Z | 2025-06-27T08:00:00Z | 2025-06-29T07:00:00Z | 3 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 54 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-07-13T08:00:00Z |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 2341 | test7EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-07-13T08:00:00Z | 2025-07-29T07:00:00Z | 2025-08-13T08:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 44 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-08-29T07:00:00Z |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 2342 | test8EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-08-29T07:00:00Z | 2025-09-13T08:00:00Z | 2025-09-29T07:00:00Z | 2 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 34 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-10-13T07:00:00Z |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 2343 | test9EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-10-13T07:00:00Z | 2025-10-29T07:00:00Z | 2025-11-13T07:00:00Z | 0 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 24 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working | 2025-11-27T07:00:00Z |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 2344 | test10EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and ADA | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2025-11-27T07:00:00Z | 2025-12-13T07:00:00Z | 2025-12-29T07:00:00Z | 1 | 2025 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62597 | Preliminary 30% Design | 14 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62599 | Intermediate Design | 21.5 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62602 | QAQC Design | 24 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62603 | Doc Design | 23.5 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
62604 | Post Doc Design | 5.5 | 2345 | test11EA 74482 / 61090 - US95 MLK Blvd. to W. Lake Mead Blvd 3R and AD | 74482 | Signals Lighting and ITS | Project | Actively Working |  |  | 2024-12-13T08:00:00Z | 2025-12-29T07:00:00Z | 2026-01-13T08:00:00Z | 3 | 2026 | Federal | Highway | 61090 | 2025-11-03T08:00:00Z | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0